## Sheet1
Id | Trust ID | Submission ID | Meta Submission ID | Research Ethics Committee Reference Number | Name of Trial | Date of Receipt of Valid Research Application | Date of NHS Permission | First Patient Recruited? | Date of First Patient Recruited | Duration between VRA and NHS Permission | Duration between NHS Permission and First Patient | Duration between VRA and First Patient | Benchmark Met | Added By User ID | Amended By User ID | Date Added | Date Amended | A - Permissions delayed/denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | K - Not Used | L - Not Used | M - Not Used | N - Not Used | O - Not Used | Comments | Reasons for delay correspond to:
62004 | 926 | 2590 | 33 | 14/WM/0159 | SNIFFLE 2 Study | 2014-10-09 | 2014-10-10 | Yes | 2014-11-24 | 1 | 45 | 46 | Yes | Unknown | Unknown | 2015-01-27 | 2015-10-29 | [16 empty] | Please Select...
62005 | 926 | 2590 | 33 | 14/LO/0565 | Lubiprostone for the treatment of paediatric functional constipation | 2014-10-16 | 2014-11-24 | Yes | 2015-02-18 | 39 | 86 | 125 | No | Unknown | Unknown | 2015-01-27 | 42306 |  |  |  | Y | [11 empty] | Contracting delays held up NHS permission and exceeded the 30 day target. In addition the site has yet to be activated by the sponsor the is SIV planned for 23/01/2015 so any recruitment will be outside of the 70 day target | Sponsor
62006 | 926 | 2590 | 33 | 14/EM/1071 | D5136C00007 Ticagrelor for sickle cell disease in paediatric patients | 2014-11-05 | 2014-11-27 | Yes | 2015-05-05 | 22 | 159 | 181 | No | Unknown | Unknown | 2015-01-27 | 42306 | [5 empty] | Y | [9 empty] | Difficult paediatric group to recruit from no eligible patients seen to date | Neither
62007 | 926 | 2590 | 33 | 06/Q0703/40 | NV25361 | 2014-10-29 | 2014-10-29 | No |  | 0 |  |  |  | Unknown | Unknown | 2015-01-27 | 42306 | [6 empty] | Y | [8 empty] | Small study population approached one participant who did not want to take part in the study. | Neither
62008 | 926 | 2590 | 33 | 06/Q0201/66 | ACST-2 version 3.2 | 2014-11-06 | 2014-11-06 | No |  | 0 |  |  |  | Unknown | Unknown | 2015-01-27 | 42306 |  |  |  | Y | [11 empty] | Study is still in set up site is waiting for sponsor activation | Sponsor
62009 | 926 | 2590 | 33 | 14/EE/1120 | MK5172/MK8742 in HCV G1, 4, 6 with Inherited Blood Disorders | 2014-11-03 | 2014-11-12 | Yes | 2014-12-10 | 9 | 28 | 37 | Yes | Unknown | Unknown | 2015-01-27 | 42306 | [16 empty] | Please Select...
62010 | 926 | 2590 | 33 | 14/SC/1030 | G-TOG - Gentamicin in the Treatment of Gonorrhoea | 2014-09-26 | 2014-10-30 | Yes | 2015-01-08 | 34 | 70 | 104 | No | Unknown | Unknown | 2015-01-27 | 42306 |  |  |  | Y | [11 empty] | NHS permission was slightly delayed from the 30 day target. Site activation was delayed by the sponsor due to the availability of sponsor and site staff for training and availability of the IMP shipment to pharmacy. | Sponsor
62011 | 926 | 2590 | 33 | 14/LO/0185 | CSF neurofilaments - a Novel phase 2a neuroprotective trial in early SPMS (PROXIMUS) | 2014-04-23 | 2014-10-31 | Yes | 2015-03-05 | 191 | 125 | 316 | No | Unknown | Unknown | 2015-01-27 | 42306 | [6 empty] | Y | [8 empty] | Delay from VRA to NHS permission as the sponsor requested several protocol amendments which delayed NHS permission. Three patients have been screened and first patient was recruited 05/03/2015 | Sponsor
62012 | 926 | 2590 | 33 | 13/LO/1579 | SPOT | 2014-08-26 | 2014-10-22 | Yes | 2014-12-10 | 57 | 49 | 106 | No | Unknown | Unknown | 2015-01-27 | 42306 | [9 empty] | Y | [5 empty] | VRA to NHS permission was caused by a delay in internal approval process. Once NHS permission was granted the site was not formally activated by the sponsor until 01/12/2014 which was outside of the 70 day target. The first recruit was 10 days later. | Both
62013 | 926 | 2590 | 33 | 14/LO/0521 | Switching to, then stopping treatment with nilotinib for CML patients. | 2014-10-20 | 2014-11-11 | Yes | 2015-02-04 | 22 | 85 | 107 | No | Unknown | Unknown | 2015-01-27 | 42306 | [9 empty] | Y | [5 empty] | The study has recruited 2 patients in the UK in one year and is 300 patients behind globally. Site has approached one patient who has declined the study and has three more patients who are considering the trial. | Neither
62014 | 926 | 2590 | 33 | 14/NW/1144 | MLN0264 in Pancreatic Adenocarcinoma | 2014-12-02 | 2014-12-02 | No |  | 0 |  |  |  | Unknown | Unknown | 2015-01-27 | 42306 | [6 empty] | Y | [8 empty] | Four patients were screen failures | Neither
62015 | 926 | 2590 | 33 | 14/LO/0673 | MLN9708 in Multiple Myeloma after Autologous Stem Cell Transplant | 2014-07-07 | 2014-11-14 | Yes | 2015-04-15 | 130 | 152 | 282 | No | Unknown | Unknown | 2015-01-27 | 42306 | [7 empty] | Y | [7 empty] | Delay between VRA and NHS permission were due to costing and contracting issues the study could not be approved until this was finalised. The sponsor fully activated site on 09/03. | Sponsor
62016 | 926 | 2590 | 33 | 14/SC/1014 | The JANUS 1 Study Incyte INCB 18424362 | 2014-11-24 | 2014-11-27 | Yes | 2015-04-13 | 3 | 137 | 140 | No | Unknown | Unknown | 2015-01-27 | 42306 | [8 empty] | Y | [6 empty] | Study met the VRA time lines Study did not meet 70 day benchmark for recruitment due to small population eligible for the study however one patient now recruited. | Neither
62017 | 926 | 2590 | 33 | 14/NW/1143 | MLN0264 in Adenocarcinoma of the Stomach or Gastroesophageal Junction | 2014-11-26 | 2014-12-03 | No |  | 7 |  |  |  | Unknown | Unknown | 2015-01-27 | 42306 | [6 empty] | Y | [8 empty] | Four patients were screen failures | Neither
62018 | 926 | 2590 | 33 | 13/SC/0332 | Takeda TOMM40_301 Alzheimer's Disease study | 2014-11-10 | 2014-11-20 | Yes | 2015-01-29 | 10 | 70 | 80 | No | Unknown | Unknown | 2015-01-27 | 42306 | [6 empty] | Y | [8 empty] | High screen fail rate in this study began screening on 24/11 six failed screening have now recruited seven patients | Neither
62019 | 926 | 2590 | 33 | 14/LO/1444 | 520-215 AfFIRM A Phase 2 Trial of Filanesib in Relapsed/Refractory MM | 2014-11-14 | 2014-12-03 | Yes | 2015-06-02 | 19 | 181 | 200 | No | Unknown | Unknown | 2015-01-27 | 42306 |  |  |  | Y | [11 empty] | Site waiting for formal activation by the sponsor | Sponsor
62020 | 926 | 2590 | 33 | 14/EE/0102 | DU176b-F-E308 | 2014-11-25 | 2014-12-09 | Yes | 2015-07-07 | 14 | 210 | 224 | No | Unknown | Unknown | 2015-01-27 | 42306 |  |  |  | Y | [11 empty] | Site waiting for formal activation by the sponsor | Sponsor
62021 | 926 | 2590 | 33 | 14/EM/0160 | AEGIS-I, Phase II, dose ranging study of CSL112 in Acute (MICSLCTHDL1277) | 2014-10-15 | 2014-10-21 | No |  | 6 |  |  |  | Unknown | Unknown | 2015-01-27 | 42306 |  |  |  | Y | [11 empty] | VRA to NHSpermission was within the 30 day time however sponsor delayed activation until their previous safety feasibility study had been completed. Site was finally activated by the sponsor 19/01/2015 therefore all recruitment will be outside of the 70 day window. However site still on hold due to delays with IMP. | Sponsor
62022 | 926 | 2590 | 33 | 10/H1010/31 | HPV-062 EXT:015 | 2014-09-19 | 2014-10-01 | Yes | 2014-11-26 | 12 | 56 | 68 | Yes | Unknown | Unknown | 2015-01-27 | 42306 | [16 empty] | Please Select...
62023 | 926 | 2590 | 33 | 14/LO/0392 | Randomised study of ABT-494 in subjects with Rheumatoid Arthritis | 2014-10-15 | 2014-10-16 | Yes | 2014-11-25 | 1 | 40 | 41 | Yes | Unknown | Unknown | 2015-01-27 | 42306 | [16 empty] | Please Select...
62024 | 926 | 2590 | 33 | 14/YH/1025 | Prodigy-I | 2014-11-24 | 2014-12-10 | Yes | 2015-01-09 | 16 | 30 | 46 | Yes | Unknown | Unknown | 2015-01-27 | 42306 | [16 empty] | Please Select...
62025 | 926 | 2590 | 33 | 14/NW/1239 | Guselkumab in Psoriasis following inadequate Ustekinumab response | 2014-12-03 | 2014-12-15 | Yes | 2015-02-19 | 12 | 66 | 78 | No | Unknown | Unknown | 2015-01-27 | 42306 |  |  |  | Y | [11 empty] | There were delays by the sponsor in activating our site (post R&D approval). These delays included equipment and supplies Sit was set up in February recruited four patients sponsor closed site to further recruitment. | Sponsor
62026 | 926 | 2590 | 33 | 14/NI/0043 | Study Reference KIT-302-03-01 | 2014-09-18 | 2014-10-09 | Yes | 2014-11-18 | 21 | 40 | 61 | Yes | Unknown | Unknown | 2015-01-27 | 42306 | [16 empty] | Please Select...
62027 | 926 | 2590 | 33 | 14/SC/1252 | NEXUS - 24 week Study to investigate new medicine Namilumab in patients | 2014-12-16 | 2014-12-16 | Yes | 2015-07-23 | 0 | 219 | 219 | No | Unknown | Unknown | 2015-01-27 | 42306 |  |  |  | Y | [11 empty] | Sponsor delayed site activation SIV now held screened first patient 23/03/2015 | Sponsor
62028 | 926 | 2590 | 33 | 14/NS/0089 | Hip 'Op | 2014-11-03 | 2014-11-06 | No |  | 3 |  |  |  | Unknown | Unknown | 2015-01-27 | 42306 | [6 empty] | Y | [8 empty] | Two patients have been screened but were not eligible | Neither
62029 | 926 | 2590 | 33 | 14/LO/1195 | 997HA306 | 2014-11-18 | 2014-11-20 | No |  | 2 |  |  |  | Unknown | Unknown | 2015-01-27 | 42306 | [6 empty] | Y | [8 empty] | This is a follow up study 5 Patients will then roll over so waiting for the first patient to complete the first study. | Neither
62030 | 926 | 2590 | 33 | 14/NE/1001 | ReActiv8 | 2014-12-19 | 2014-12-19 | Yes | 2015-01-16 | 0 | 28 | 28 | Yes | Unknown | Unknown | 2015-01-27 | 42306 | [16 empty] | Please Select...
62031 | 926 | 2590 | 33 | 14/EM/1035 | Prospective Outcomes of Secondline Therapy in Acute GraftversusHost Study including ECP (POSTAGE) | 2014-12-18 | 2014-12-18 | No |  | 0 |  |  |  | Unknown | Unknown | 2015-01-27 | 42306 |  |  |  | Y | [11 empty] | SIV delayed by sponsor Site opened officially on 20/02/2015 no patients eligible to date. | Sponsor
62032 | 926 | 2590 | 33 | 13/LO/1886 | IPI-145 in subjects with refractory iNHL | 2014-10-24 | 2014-11-10 | No |  | 17 |  |  |  | Unknown | Unknown | 2015-01-27 | 42306 |  |  |  |  | Y | [10 empty] | VRA to NHS permission was within 30 days However staff availability is an issue site is still in set up and will be unable to meet the 70 day metric | NHS Provider
62033 | 926 | 2590 | 33 | 14/EM/1059 | 047 FIT (Fostamatinib for Immune Thrombocytopenia) Study | 2014-12-18 | 2014-12-19 | Yes | 2015-04-08 | 1 | 110 | 111 | No | Unknown | Unknown | 2015-01-27 | 42306 |  |  |  | Y | [11 empty] | SIV held on 28/01/2015 site fully set up 05/02 /15 one patient approached for the study. | Sponsor
62034 | 926 | 2590 | 33 | 14/LO/0566 | Olaparib therapy in high risk HER2 negative BRCA mutated breast cancer | 2014-09-05 | 2014-12-03 | Yes | 2015-03-26 | 89 | 113 | 202 | No | Unknown | Unknown | 2015-01-27 | 42306 |  |  |  | Y | [11 empty] | Sponsor delays in contracting, sponsor set up activities at site were slow, this delayed NHS permission which was issued after the 70 day benchmark. Site was finally activated by sponsor 19/12/2014 | Sponsor
62035 | 926 | 2590 | 33 | 14/LO/1468 | SPL7013-018Starpharma Phase 3 study of VivaGel® in Bacterial Vaginosis | 2014-11-24 | 2015-02-04 | Yes | 2015-07-27 | 72 | 173 | 245 | No | Unknown | Unknown | 2015-04-29 | 42306 | [9 empty] | Y | [5 empty] | Delay from VRA to NHS permission was due to delay in internal approvals SIV was held on 4/03/2015 site still in set up | NHS Provider
62036 | 926 | 2590 | 33 | 14/LO/1459 | Study of MMX® Mesalamine/Mesalazine in Paediatric Ulcerative Colitis | 2015-02-04 | 2015-02-05 | Yes | 2015-03-11 | 1 | 34 | 35 | Yes | Unknown | Unknown | 2015-04-29 | 42306 | [16 empty] | Please Select...
62037 | 926 | 2590 | 33 | 14/WS/1078 | M11290, Adalimumbab Paediatric Ulcerative Colitis Study | 2015-02-06 | 2015-02-09 | Yes | 2015-04-21 | 3 | 71 | 74 | No | Unknown | Unknown | 2015-04-29 | 42306 | [6 empty] | Y | [8 empty] | Study met the 30 day VRA to NHS permission target but did not meet the 70 day benchmark as there were no eligible patients seen who met the entry criteria. One patient has now been recruited. | Neither
62038 | 926 | 2590 | 33 | 15/LO/0034 | OPuS-2 - Preventing HAE attacks | 2015-02-12 | 2015-02-20 | Yes | 2015-03-30 | 8 | 38 | 46 | Yes | Unknown | Unknown | 2015-04-29 | 42306 | [16 empty] | Please Select...
62039 | 926 | 2590 | 33 | 14/LO/1604 | Open-Label Extension Study in Rheumatoid Arthritis (ABT-494 Extension) | 2015-02-11 | 2015-02-24 | Yes | 2015-03-09 | 13 | 13 | 26 | Yes | Unknown | Unknown | 2015-04-29 | 42306 | [16 empty] | Please Select...
62040 | 926 | 2590 | 33 | 13/YH/0147 | ELAD for Treatment of SAAH (VTI210) | 2014-11-05 | 2015-01-22 | No |  | 78 |  |  |  | Unknown | Unknown | 2015-04-29 | 42306 | [7 empty] | Y | [7 empty] | VRA to NHS permission exceeded 30 days due to major delay in the contract review stage by the sponsor. Small patient population so recruitment will be slow no eligible patients seen to date. | Sponsor
62041 | 926 | 2590 | 33 | 14/WM/1209 | CENTAUR-CVC | 2015-02-18 | 2015-02-23 | Yes | 2015-04-16 | 5 | 52 | 57 | Yes | Unknown | Unknown | 2015-04-29 | 42306 | [16 empty] | Please Select...
62042 | 926 | 2590 | 33 | 14/LO/1708 | Effect of dietary nitrate ingestion in stable angina | 2015-02-13 | 2015-02-17 | No |  | 4 |  |  |  | Unknown | Unknown | 2015-04-29 | 42306 | [9 empty] | Y | [5 empty] | Study is in set up. An amendment was required as manufacturer of the dietry supplement could no longer supply it so the formulation of the product was changed. The study is currently on hold until this is approved. | Sponsor
62043 | 926 | 2590 | 33 | 14/EE/1165 | MK5172/MK3682 with MK8742 or MK8408 in HCV GT1, GT2 and GT3 Infected Subjects | 2015-01-28 | 2015-02-05 | Yes | 2015-02-12 | 8 | 7 | 15 | Yes | Unknown | Unknown | 2015-04-29 | 42306 | [16 empty] | Please Select...
62044 | 926 | 2590 | 33 | 13/EE/0214 | A Long Term Follow-up Study of Subjects previously treated with MK-5172 | 2015-01-05 | 2015-02-09 | Yes | 2015-06-29 | 35 | 140 | 175 | No | Unknown | Unknown | 2015-04-29 | 42306 | [9 empty] | Y | [5 empty] | Delay from the VRA to NHS permission as the contracts negotiations. This study is a long Term Follow-up Study of Subjects previously treated with MK-5172 we can only recruit when the patients are ready to move from the first phase into the extension phase. | Neither
62045 | 926 | 2590 | 33 | 14/LO/1786 | CapaCiTY Study 1- Chronic Constipation Treatment Pathway | 2015-01-15 | 2015-01-20 | Yes | 2015-03-26 | 5 | 65 | 70 | Yes | Unknown | Unknown | 2015-04-29 | 42306 | [16 empty] | Please Select...
62046 | 926 | 2590 | 33 | 14/SW/1029 | 218MS305 - Fampridine in Subjects with Multiple Sclerosis (ENHANCE) | 2015-01-06 | 2015-01-08 | Yes | 2015-02-24 | 2 | 47 | 49 | Yes | Unknown | Unknown | 2015-04-29 | 42306 | [16 empty] | Please Select...
62047 | 926 | 2590 | 33 | 14/WM/1188 | 4054 - REAL 1 NNC0195-0092 in adults with growth hormone deficiency | 2015-01-08 | 2015-02-02 | No |  | 25 |  |  |  | Unknown | Unknown | 2015-04-29 | 42306 | [5 empty] | Y | [9 empty] | No eligible patients seen | Neither
62048 | 926 | 2590 | 33 | 14/SC/1059 | 28431754DNE3001: The CREDENCE Trial (28431754DNE3001) | 2014-10-14 | 2015-02-05 | Yes | 2015-09-29 | 114 | 236 | 350 | No | Unknown | Unknown | 2015-04-29 | 42306 | [7 empty] | Y | [7 empty] | VRA to NHS permission did not met the 30 day target as costing and contacting issues took 7 month to be finalised. Contract was signed on 04/02/2015 NHS permission was issued on 05/02/2015 SIV was held on 09/02/2015. Three patients consented to screening but were all screen failures | Sponsor
62049 | 926 | 2590 | 33 | 14/EE/1113 | TOPAZ | 2015-02-04 | 2015-02-05 | Yes | 2015-02-26 | 1 | 21 | 22 | Yes | Unknown | Unknown | 2015-04-29 | 42306 | [16 empty] | Please Select...
62050 | 926 | 2590 | 33 | 14/WS/1105 | 101MS408 Multicenter study of Natalizumab v Fingolimod in MS | 2015-02-09 | 2015-02-18 | Yes | 2015-02-24 | 9 | 6 | 15 | Yes | Unknown | Unknown | 2015-04-29 | 42306 | [16 empty] | Please Select...
62051 | 926 | 2590 | 33 | 14/LO/1798 | GO29294 Anti-PDL1 Bladder Cancer Phase III Version 1.0 | 2014-11-13 | 2015-02-19 | Yes | 2015-02-20 | 98 | 1 | 99 | No | Unknown | Unknown | 2015-04-29 | 42306 | [7 empty] | Y | [7 empty] | VRA to NHS permission was delayed due to costing and contacting issues which took 120 days for this process to be finalised. The first patient was recruited on 20/02/2015 and the team have now recruited 9 patients which exceeded their target by 50%. | Sponsor
62052 | 926 | 2590 | 33 | 14/WM/1218 | 4043 - REAL 2 NNC0195-0092 in adults with growth hormone deficiency | 2015-02-09 | 2015-02-20 | Yes | 2015-03-28 | 11 | 36 | 47 | Yes | Unknown | Unknown | 2015-04-29 | 42306 | [16 empty] | Please Select...
62053 | 926 | 2590 | 33 | 13/NI/0143 | SIEGE | 2015-02-04 | 2015-02-26 | Yes | 2015-05-05 | 22 | 68 | 90 | No | Unknown | Unknown | 2015-04-29 | 42306 | [6 empty] | Y | [8 empty] | Study met the VRA to NHS permission 30 day metric however the first patient was consented outside of the 70 day target as no patients were eligible for the study (there were three screen failures) first patient now recruited. | Neither
62054 | 926 | 2590 | 33 | 14/LO/1597 | Phase 2a/2b study of alkaline phosphatase in patients with SAAKI | 2014-11-26 | 2015-01-06 | No |  | 41 |  |  |  | Unknown | Unknown | 2015-04-29 | 42306 | [9 empty] | Y | [5 empty] | VRA to NHS permission was 41 days the 30 day target occurred during the Christmas holidays whilst the office was closed the permission was given on 06/01/15. Site was activated on 09/02/2015 by sponsor as there were drug supply issues. 30 patients have since been screened but none were eligible. | Both
62055 | 926 | 2590 | 33 | 14/EM/1003 | Study to evaluate safety & efficacy of Blisibimod in IgA Nephropathy | 2015-01-26 | 2015-02-11 | Yes | 2015-07-07 | 16 | 146 | 162 | No | Unknown | Unknown | 2015-04-29 | 42306 | [6 empty] | Y | [8 empty] | VRA to NHS permission was within the 30 day target three patients were approached but declined to take part in the study. | Neither
62056 | 926 | 2590 | 33 | 13/YH/0333 | Long term study for participants completing SIRROUND-D and SIRROUND-T | 2014-05-22 | 2015-01-16 | Yes | 2015-04-15 | 239 | 89 | 328 | No | Unknown | Unknown | 2015-04-29 | 42306 |  |  |  | Y | [11 empty] | Delay in VRA to NHS permission was caused as this was a follow up study where patients were not due to enter until 2015. However the study team submitted their SSIF very early and the sponsor requested a hold on the process until the transition from one phase to another was planned. One patient is due to move into the extension phase in April 2015. | Sponsor
62057 | 926 | 2590 | 33 | 15/LO/0119 | Neuromuscular Electrical Stimulation | 2015-01-27 | 2015-03-11 | Yes | 2015-03-14 | 43 | 3 | 46 | Yes | Unknown | Unknown | 2015-04-29 | 42306 | [16 empty] | Please Select...
62058 | 926 | 2590 | 33 | 14/NW/1292 | CA209-214 Nivolumab combined with Ipilimumab versus Sunitinib in RCC | 2015-02-23 | 2015-03-12 | Yes | 2015-04-27 | 17 | 46 | 63 | Yes | Unknown | Unknown | 2015-04-29 | 42306 | [16 empty] | Please Select...
62059 | 926 | 2590 | 33 | 14/LO/1837 | ARPEGGIO: Laquinimod for Primary Progressive Multiple Sclerosis (PPMS) | 2015-03-10 | 2015-03-17 | Yes | 2015-06-09 | 7 | 84 | 91 | No | Unknown | Unknown | 2015-04-29 | 42306 |  |  |  | Y | [11 empty] | VRA to NHS permission met 30 day target. Sponsor caused a delay to set up as the imaging protocol for this study supplied to site for dummy scans was incorrect so the site activation was delayed. First patient has now been recruited | Sponsor
62060 | 926 | 2590 | 33 | 14/LO/1927 | M14-567 Study in Subjects with Genotype 3 Chronic HCV infection | 2015-03-23 | 2015-03-24 | Yes | 2015-04-02 | 1 | 9 | 10 | Yes | Unknown | Unknown | 2015-04-29 | 42306 | [16 empty] | Please Select...
62061 | 926 | 2590 | 33 | 14/EM/1249 | ABT-333 TOPAZ-I | 2015-02-24 | 2015-02-26 | Yes | 2015-03-27 | 2 | 29 | 31 | Yes | Unknown | Unknown | 2015-04-29 | 42306 | [16 empty] | Please Select...
62062 | 926 | 2590 | 33 | 14/LO/1617 | Type I DM Study | 2015-03-05 | 2015-03-05 | Yes | 2015-06-19 | 0 | 106 | 106 | No | Unknown | Unknown | 2015-04-29 | 42306 | [6 empty] | Y | [8 empty] | VRA to NHS permission was within the 30 day target 9 patients were screened who were screen failures one patient gave consent on 19 June and randomised into the study. Recruitment arget now met. | Neither
62063 | 926 | 2590 | 33 | 14/WM/1210 | HIV Once Daily ARV Single Tablet bPI Regimen | 2015-02-06 | 2015-02-10 | Yes | 2015-07-14 | 4 | 154 | 158 | No | Unknown | Unknown | 2015-04-29 | 42306 |  |  |  | Y | [11 empty] | VRA to NHS permission met the 30 day target however sponsor has not activated the site whci is planned for July | Sponsor
62064 | 926 | 2590 | 33 | 14/NW/1076 | RESCUE-ASDH trial. Version 1.0 | 2014-10-20 | 2015-03-25 | Yes | 2015-04-18 | 156 | 24 | 180 | No | Unknown | Unknown | 2015-04-29 | 42306 |  |  |  |  | Y | [10 empty] | Delay in VRA to NHS permission was caused by staff availability for imaging review. The site has now been activated and has one participant in screening. | NHS Provider
62065 | 926 | 2590 | 33 | 14/WM/1262 | Open Label Efficacy and Safety of SOF/GS5816 | 2015-02-28 | 2015-03-30 | Yes | 2015-05-07 | 30 | 38 | 68 | Yes | Unknown | Unknown | 2015-04-29 | 42306 | [16 empty] | Please Select...
62066 | 926 | 2590 | 33 | 14/NE/1175 | Study in Adult Subjects with Primary Immune Thrombocytopenia (ITP) | 2015-03-10 | 2015-03-13 | Yes | 2015-04-22 | 3 | 40 | 43 | Yes | Unknown | Unknown | 2015-04-29 | 42306 | [16 empty] | Please Select...
62067 | 926 | 2590 | 33 | 14/NE/1063 | GA28950 PHASE III TRIAL OF ETROLIZUMAB IN MODERATE TO SEVERE ACTIVE UC | 2015-04-07 | 2015-04-07 | No |  | 0 |  |  |  | Unknown | Unknown | 2015-07-28 | 42306 |  |  |  | Y | [11 empty] | VRA to NHS permission 30 day target was met however the sponsor did not supply the correct kits so site activation was delayed so the study could not meet the 70 day target. One participant was screened 15 June but was a screen failure | Sponsor
62068 | 926 | 2590 | 33 | 14/LO/2235 | Trial of Electronic Cigarettes (TEC) | 2015-03-27 | 2015-04-01 | Yes | 2015-05-12 | 5 | 41 | 46 | Yes | Unknown | Unknown | 2015-07-28 | 42306 | [16 empty] | Please Select...
62069 | 926 | 2590 | 33 | 14/NE/1099 | GA29103 - PATIENTS WITH MODERATE TO SEVERE ACTIVE ULCERATIVE COLITIS | 2015-04-13 | 2015-04-16 | Yes | 2015-07-27 | 3 | 102 | 105 | No | Unknown | Unknown | 2015-07-28 | 42306 |  |  |  | Y | [11 empty] | VRA to NHS permission 30 day target was met. However the sponsor delayed the shipment of kits and site unable to be activated and is still in set up | Sponsor
62070 | 926 | 2590 | 33 | 14/NE/1169 | Impact of RA characteristics on outcome of study drug dose tapering | 2015-04-15 | 2015-04-17 | No |  | 2 |  |  |  | Unknown | Unknown | 2015-07-28 | 42306 | [7 empty] | Y | [7 empty] | VRA to NHS permission met the 30 day target however sponsor has not activated the site as additional scanning requested by sponsor required a new contract which is to be drafted. | Sponsor
62071 | 926 | 2590 | 33 | 13/LO/1878 | Dietary interventions for IBD | 2015-04-22 | 2015-04-22 | Yes | 2015-06-02 | 0 | 41 | 41 | Yes | Unknown | Unknown | 2015-07-28 | 42306 | [16 empty] | Please Select...
62072 | 926 | 2590 | 33 | 14/LO/1428 | Adjunctive Steroid Combination in Ocular Trauma (ASCOT) Study | 2015-03-30 | 2015-04-17 | No |  | 18 |  |  |  | Unknown | Unknown | 2015-07-28 | 42306 | [9 empty] | Y | [5 empty] | VRA to NHS permission met the 30 day target delays to site activation by sponsor and site have accrued so study will miss the 70 day target | Both
62073 | 926 | 2590 | 33 | 14/LO/0816 | Long term efficacy of Lubiprostone for paed. functional constipation | 2015-04-30 | 2015-05-08 | Yes | 2015-05-29 | 8 | 21 | 29 | Yes | Unknown | Unknown | 2015-07-28 | 42306 | [16 empty] | Please Select...
62074 | 926 | 2590 | 33 | 13/EE/0270 | RELIEF Registry | 2015-05-20 | 2015-05-29 | Yes | 2015-06-19 | 9 | 21 | 30 | Yes | Unknown | Unknown | 2015-07-28 | 42306 | [16 empty] | Please Select...
62075 | 926 | 2590 | 33 | 14/SW/1164 | MEDI4736 in Recurrent or Metastatic PD-L1 Positive SCCHN | 2015-05-15 | 2015-05-15 | No |  | 0 |  |  |  | Unknown | Unknown | 2015-07-28 | 42306 | [6 empty] | Y | [8 empty] | VRA to NHS permission was within 30 days however to date there has been one person screened who was a screen failure and could not be randomised the team are continuing to search for eligible participants but none have presented to date. | Neither
62076 | 926 | 2590 | 33 | 14/LO/1834 | SAD and MAD study of GBT440 in healthy volunteers and SCD Patients | 2015-05-06 | 2015-05-06 | Yes | 2015-06-02 | 0 | 27 | 27 | Yes | Unknown | Unknown | 2015-07-28 | 42306 | [16 empty] | Please Select...
62077 | 926 | 2590 | 33 | 14/NE/1253 | D5160C00019 Phase I Open Label, PK, EGFRm+ NSCLC (Rosuvastatin) | 2015-03-31 | 2015-03-31 | Yes | 2015-04-22 | 0 | 22 | 22 | Yes | Unknown | Unknown | 2015-07-28 | 42306 | [16 empty] | Please Select...
62078 | 926 | 2590 | 33 | 14/SC/0075 | Pfizer B3461028 Study for patients with TTR CM | 2015-04-23 | 2015-04-30 | No |  | 7 |  |  |  | Unknown | Unknown | 2015-07-28 | 42306 | [9 empty] | Y | [5 empty] | Study transferred from UCLH heart hospital to Barts NHS Trust as part of the NHS cardiac service reconfiguration in London. We have taken over the follow up visits for this study there will be no further recruitment into this study. Barts NHS Trust as opened as a site so that the follow up visits can take place. | Neither
62079 | 926 | 2590 | 33 | 12/LO/1078 | MUK five | 2014-12-18 | 2014-12-29 | Yes | 2015-06-15 | 11 | 168 | 179 | No | Unknown | Unknown | 2015-07-28 | 42306 | [5 empty] | Y | [9 empty] | VRA to NHS permission was within the 30 day target, however no patient seen who fit the eligibility criteria | Neither
62080 | 926 | 2590 | 33 | 15/WM/0050 | Ingenol Mebutate vs. Diclofenac in subjects with AK on face or scalp | 2015-05-12 | 2015-05-18 | Yes | 2015-07-21 | 6 | 64 | 70 | Yes | Unknown | Unknown | 2015-07-28 | 42306 | [16 empty] | Please Select...
62081 | 926 | 2590 | 33 | 14/LO/2041 | GU111: AZD6094 in patients with papillary renal cell carcinoma | 2015-02-23 | 2015-05-11 | Yes | 2015-08-18 | 77 | 99 | 176 | No | Unknown | Unknown | 2015-07-28 | 42306 | [7 empty] | Y | [7 empty] | VRA to NHS permission 30 day target was not met due to costing and contracting delays with the sponsor this meant the 70 day target could not be met. No eligible patients have been seen to date. | Sponsor
62082 | 926 | 2590 | 33 | 14/WM/0182 | CFZ533 in patients with primary Sjögren's syndrome | 2015-04-08 | 2015-04-08 | Yes | 2015-06-03 | 0 | 56 | 56 | Yes | Unknown | Unknown | 2015-07-28 | 42306 | [16 empty] | Please Select...
62083 | 926 | 2590 | 33 | 14/YH/1124 | EXTEND (2819-MA-1002) | 2014-12-05 | 2014-12-09 | Yes | 2015-04-08 | 4 | 120 | 124 | No | Unknown | Unknown | 2015-07-28 | 42306 | [6 empty] | Y | [8 empty] | VRA to NHS permission was within the 30 day target however no eligible patients were seen one has since been recruited outside of the 70 day window | Neither
62084 | 926 | 2590 | 33 | 14/EE/1279 | Latella 2 | 2015-06-10 | 2015-06-12 | Yes | 2015-06-16 | 2 | 4 | 6 | Yes | Unknown | Unknown | 2015-07-28 | 42306 | [16 empty] | Please Select...
62085 | 926 | 2590 | 33 | 11/NE/0228 | ION– Is ablative radiOiodine Necessary for low risk differentiated thyroid cancer patients | 2014-10-13 | 2014-10-23 | No |  | 10 |  |  |  | Unknown | Unknown | 2015-07-28 | 42306 | [5 empty] | Y | [9 empty] | VRA to NHS permission was within the 30 day target however no eligible patients were seen within the 70 day window | Neither
62086 | 926 | 2590 | 33 | 15/LO/0104 | Albumin To prevenT Infection in chronic liveR failurE (ATTIRE) | 2015-06-03 | 2015-06-19 | Yes | 2015-08-07 | 16 | 49 | 65 | Yes | Unknown | Unknown | 2015-07-28 | 42306 | [16 empty] | Please Select...
62087 | 926 | 2590 | 33 | 13/LO/1666 | The HALT-LTBI | 2015-05-25 | 2015-06-10 | No |  | 16 |  |  |  | Unknown | Unknown | 2015-07-28 | 42306 | [9 empty] | Y | [5 empty] | VRA to NHS permission was within 30 days however there is a shortage of IMP so site is temporarily unable to screen any further participants. | Sponsor
62088 | 926 | 2590 | 33 | 14/LO/2036 | Erlotinib in ADVANCED NON-SMALL CELL LUNG | 2015-04-07 | 2015-04-10 | Yes | 2015-05-27 | 3 | 47 | 50 | Yes | Unknown | Unknown | 2015-07-28 | 42306 | [16 empty] | Please Select...
62089 | 926 | 2590 | 33 | 11/LO/1722 | Bioflow III Registry (CIP No: C1011 Version 2.0) | 2015-05-06 | 2015-06-18 | No |  | 43 |  |  |  | Unknown | Unknown | 2015-07-28 | 42306 | [9 empty] | Y | [5 empty] | Study transferred from UCLH heart hospital to Barts NHS Trust as part of the NHS cardiac service reconfiguration in London. We have taken over the follow up visits for this study there will be no further recruitment into this study. Barts NHS Trust as opened as a site so that the follow up visits can take place. | Neither
62090 | 926 | 2590 | 33 | 15/LO/0634 | LONGEVITY Study | 2015-06-03 | 2015-06-09 | Yes | 2015-07-28 | 6 | 49 | 55 | Yes | Unknown | Unknown | 2015-07-28 | 42306 | [16 empty] | Please Select...
62091 | 926 | 2590 | 33 | 09/H0703/28 | CASTLE-AF | 2015-05-18 | 2015-05-20 | No |  | 2 |  |  |  | Unknown | Unknown | 2015-07-28 | 42306 | [5 empty] | Y | [9 empty] | Study transferred from UCLH Heart Hospital as part of the London cardiac service reconfiguration. Barts Health has opened as a site and is treating transferred patients for their follow up visits. To date no new Barts Health participants have been recruited. | Neither
62092 | 926 | 2590 | 33 | 14/WA/1209 | Stratification of Biologic Therapies for RA by Pathobiology (STRAP) | 2015-04-30 | 2015-05-14 | Yes | 2015-06-08 | 14 | 25 | 39 | Yes | Unknown | Unknown | 2015-07-28 | 42306 | [16 empty] | Please Select...
62093 | 926 | 2590 | 33 | 14/LO/1193 | Epanova in High Cardiovascular Risk Patients with Hypertriglyceridemia | 2015-03-16 | 2015-06-24 | Yes | 2015-08-01 | 100 | 38 | 138 | No | Unknown | Unknown | 2015-07-28 | 42306 | [7 empty] | Y | [7 empty] | VRA was validated on 16/03/2015 sponsor submitted four substantial amendments which required additional costing and contracting review to occur. NHS permission granted outside of the 70 day window site still waiting for full activation by sponsor. | Sponsor
62094 | 926 | 2590 | 33 | 15/LO/0834 | WO 29522-A Study of MPDL3280A and Nabpaclitaxel in Breast Cancer | 2015-06-12 | 2015-06-16 | Yes | 2015-06-23 | 4 | 7 | 11 | Yes | Unknown | Unknown | 2015-07-28 | 42306 | [16 empty] | Please Select...
62095 | 926 | 2590 | 33 | 15/YH/0005 | Liberty AD SOLO | 2015-04-30 | 2015-04-30 | No |  | 0 |  |  |  | Unknown | Unknown | 2015-07-28 | 42306 |  |  | Y | [12 empty] | VRA to NHS permission was within 30 days, 2 participants were screened however before they could be randomised the sponsor closed recruitment in the UK as their target was met. | Sponsor
62096 | 926 | 2590 | 33 | 15/LO/0581 | CLFX453X2201 | 2015-05-21 | 2015-06-29 | Yes | 2015-08-20 | 39 | 52 | 91 | No | Unknown | Unknown | 2015-07-28 | 42306 | [6 empty] | Y | [8 empty] | VRA to NHS permission was outside of the 30 day window as the global study review was not finalised until 25 /06/2015. NHS permission was granted on 29/06/2015. The site screened three participants in July, two failed screening one was randomised on 20/08/2015, and the study has now been closed to further recruitment by the sponsor. | Neither
62097 | 926 | 2590 | 33 | 15/LO/0496 | EFV/FTC/TDF switch to FTC/RPV/TAF in HIV-1 Patients | 2015-05-27 | 2015-06-11 | Yes | 2015-07-07 | 15 | 26 | 41 | Yes | Unknown | Unknown | 2015-07-28 | 42306 | [16 empty] | Please Select...
62098 | 926 | 2590 | 33 | 15/LO/0495 | FTC/RPV/TAF switch from FTC/RPV/TDF in HIV1 | 2015-05-22 | 2015-06-11 | Yes | 2015-07-14 | 20 | 33 | 53 | Yes | Unknown | Unknown | 2015-07-28 | 42306 | [16 empty] | Please Select...
62099 | 926 | 2590 | 33 | 14/WS/1014 | Wave IV study | 2015-04-29 | 2015-05-21 | Yes | 2015-07-06 | 22 | 46 | 68 | Yes | Unknown | Unknown | 2015-07-28 | 42306 | [16 empty] | Please Select...
62100 | 926 | 2590 | 33 | 14/LO/2200 | CSL830_3002 | 2015-04-23 | 2015-04-28 | Yes | 2015-06-16 | 5 | 49 | 54 | Yes | Unknown | Unknown | 2015-07-28 | 42306 | [16 empty] | Please Select...
65755 | 926 | 2590 | 33 | 14/LO/0165 | SCAPE | 2015-03-19 | 2015-08-24 | Yes | 2015-09-26 | 158 | 33 | 191 | No | Unknown | Unknown | 2015-10-28 | 42306 |  |  |  | Y | [11 empty] | The delay between VRA and NHS permission exceeded the 30 day target. The site submitted their SSIF before the sponsor was able to give final declaration of sponsorship and hence indemnity for the study. Site has now recruited the first participant within one month of NHS permission being granted but this was outside of the 70 benchmark. | Sponsor
65756 | 926 | 2590 | 33 | 15/LO/0404 | Torcmek | 2015-06-11 | 2015-06-27 | Yes | 2015-07-24 | 16 | 27 | 43 | Yes | Unknown | Unknown | 2015-10-28 | 42306 | [16 empty] | Please Select...
65757 | 926 | 2590 | 33 | 14/YH/0038 | VERISMART trial | 2015-08-20 | 2015-08-20 | No |  | 0 |  |  |  | Unknown | Unknown | 2015-10-28 | 42306 | [16 empty] | Please Select...
65764 | 926 | 2590 | 33 | 14/NE/1100 | GA28951 – Open-label extension & safety monitoring study | 2015-08-26 | 2015-08-27 | No |  | 1 |  |  |  | Unknown | Unknown | 2015-10-28 | 42306 | [16 empty] | Please Select...
65765 | 926 | 2590 | 33 | 14/YH/1204 | Phase2 Gilead Study Safety&Efficacy of Idela&Rituximab in CLL patients | 2015-08-26 | 2015-08-27 | No |  | 1 |  |  |  | Unknown | Unknown | 2015-10-28 | 42306 | [16 empty] | Please Select...
65766 | 926 | 2590 | 33 | 14/LO/1939 | Octreotide as prophylaxis for lapatinib-capecitabine related diarrhoea | 2015-07-14 | 2015-07-15 | No |  | 1 |  |  |  | Unknown | Unknown | 2015-10-28 | 42306 |  |  |  | Y | [11 empty] | VRA to NHS permission was within the 30 day window however the site has not yet been activated by the sponsor and is in set up. | Sponsor
65767 | 926 | 2590 | 33 | 15/LO/0799 | Air pollution exposure on asthmatic children | 2015-07-14 | 2015-07-21 | Yes | 2015-09-03 | 7 | 44 | 51 | Yes | Unknown | Unknown | 2015-10-28 | 42306 | [16 empty] | Please Select...
65768 | 926 | 2590 | 33 | 15/LO/1447 | Biomechanically determined interventions for patellofemoral pain | 2015-09-01 | 2015-09-01 | No |  | 0 |  |  |  | Unknown | Unknown | 2015-10-28 | 42306 | [16 empty] | Please Select...
65933 | 926 | 2590 | 33 | 14/EM/1173 | HI-Light Vitiligo Trial | 2015-07-14 | 2015-07-14 | Yes | 2015-08-24 | 0 | 41 | 41 | Yes | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
65934 | 926 | 2590 | 33 | 13/NW/0134 | NEOBLADE Version: 2 | 2015-07-20 | 2015-07-20 | No |  | 0 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [5 empty] | Y | [9 empty] | VRA to NHS permission met the 30 day benchmark however there have been no eligible participants presenting in clinic to date who can be screened for the study. | Neither
65935 | 926 | 2590 | 33 | 14/YH/1202 | PREVAIL Version 1.0 | 2015-08-25 | 2015-08-25 | Yes | 2015-09-27 | 0 | 33 | 33 | Yes | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
65936 | 926 | 2590 | 33 | 14/EE/1282 | The ANSeR Clinical Investigation | 2015-07-24 | 2015-07-24 | Yes | 2015-08-05 | 0 | 12 | 12 | Yes | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
65937 | 926 | 2590 | 33 | 14/LO/2011 | DUAL antithrombotic therapy with dabigatran etexilate (RE-DUAL PCI) | 2015-08-20 | 2015-08-20 | No |  | 0 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66100 | 926 | 2590 | 33 | 15/NS/0076 | Evaluating the accuracy of commercially available pulse oximeters v1 | 2015-08-14 | 2015-08-14 | No |  | 0 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66101 | 926 | 2590 | 33 | 15/EE/0227 | Non-invasive cardiac output measurement in the Emergency Department | 2015-08-10 | 2015-08-13 | Yes | 2015-08-14 | 3 | 1 | 4 | Yes | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66102 | 926 | 2590 | 33 | 14/LO/1403 | DEferiprone Evaluation in Paediatrics | 2015-03-25 | 2015-07-29 | Yes | 2015-09-30 | 126 | 63 | 189 | No | Unknown | Unknown | 2015-10-29 | 42306 |  |  |  | Y | [11 empty] | VRA to NHS permission exceeded the 30 day target due to delay in costing and contracting with the sponsor this meant that the 70 day benchmark for recruitment could not be met. The site was initiated by the sponsor on the 10 September 2015. The first patient was recruited on 30/09/2015. | Sponsor
66103 | 926 | 2590 | 33 | 12/SC/0107 | EAST - Early treatment of AF for Stroke prevention Trial | 2015-05-22 | 2015-05-27 | No |  | 5 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [5 empty] | Y | [9 empty] | Study transferred from UCLH Heart Hospital as part of the London cardiac service reconfiguration. Barts Health has opened as a site and is treating transferred patients for their follow up visits. To date no new Barts Health participants have been recruited. | Neither
66104 | 926 | 2590 | 33 | 14/ES/1064 | LOGS | 2015-07-27 | 2015-07-27 | No |  | 0 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66105 | 926 | 2590 | 33 | 13/EE/0444 | Boston Scientific Rally X4 | 2015-09-01 | 2015-09-04 | No |  | 3 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [5 empty] | Y | [9 empty] | Study transferred from UCLH Heart Hospital as part of the London cardiac service reconfiguration. Barts Health has opened as a site and is treating transferred patients for their follow up visits. To date no new Barts Health participants have been recruited. | Neither
66106 | 926 | 2590 | 33 | 15/YH/0108 | FUTURE 4 | 2015-07-23 | 2015-08-10 | Yes | 2015-08-27 | 18 | 17 | 35 | Yes | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66107 | 926 | 2590 | 33 | 15/LO/0090 | Safety & efficacy of AMG557/MEDI5872 in Sjogren's syndrome | 2015-05-13 | 2015-07-06 | Yes | 2015-08-25 | 54 | 50 | 104 | No | Unknown | Unknown | 2015-10-29 | 42306 | [7 empty] | Y | [7 empty] | The VRA to NHS permission exceeded the 30 day target as there were delays with the contracting process. The team have since screened several participants and have now recruited into the study. | Sponsor
66108 | 926 | 2590 | 33 | 14/NE/1129 | PICSO as an adjunct to PCI in acute coronary syndrome | 2015-08-04 | 2015-08-25 | Yes | 2015-09-28 | 21 | 34 | 55 | Yes | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66109 | 926 | 2590 | 33 | 15/EE/0130 | Phase 3 study in patients with lung infections- protocol INS212 | 2015-06-17 | 2015-07-23 | No |  | 36 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [7 empty] | Y | [7 empty] | VRA to NHS permission exceeded the 30 day target to date the team have not seen any eligible participants. The target recruitment is 1 as this is a difficult group to recruit from. | Neither
66110 | 926 | 2590 | 33 | 15/SC/0280 | 1160.204 RE-CIRCUIT:Dabigatran vs warfarin in AF Ablation | 2015-09-03 | 2015-09-10 | No |  | 7 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66111 | 926 | 2590 | 33 | 15/LO/0282 | I1F-MC-RHBE Ixekizumab in patients with active psoriatic arthritis | 2015-07-02 | 2015-07-20 | Yes | 2015-08-26 | 18 | 37 | 55 | Yes | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66112 | 926 | 2590 | 33 | 15/WA/0047 | Gammanorm in immunodeficient pts using infusion by pump or rapid push | 2015-07-02 | 2015-07-07 | No |  | 5 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [8 empty] | Y | [6 empty] | VRA to NHS permission was within thirty days however this is a rare patient group and to date no eligible patients have been seen | Neither
66113 | 926 | 2590 | 33 | 13/LO/0980 | Investigation into the role of GTN and RIPC in Cardiac Surgery | 2015-06-16 | 2015-07-08 | No |  | 22 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [9 empty] | Y | [5 empty] | Study transferred from UCLH heart hospital to Barts NHS Trust as part of the NHS cardiac service reconfiguration in London. We have taken over the follow up visits for this study there will be no further recruitment into this study. Barts NHS Trust as opened as a site so that the follow up visits can take place. | Neither
66114 | 926 | 2590 | 33 | 15/LO/0684 | LEVALS | 2015-07-06 | 2015-07-07 | Yes | 2015-09-22 | 1 | 77 | 78 | No | Unknown | Unknown | 2015-10-29 | 42306 | [6 empty] | Y | [8 empty] | Three participants were approached during August 2015 the first on 12 August but were all screen failures. The first participant was formally enrolled on 22/09/2015 which was unfortunately outside of the 70 day window. The study has rerutied 2 participants to date. | Neither
66130 | 926 | 2590 | 33 | 15/SC/0146 | Secukinumab in patients with active Ankylosing Spondylitis | 2015-08-05 | 2015-08-05 | Yes | 2015-09-03 | 0 | 29 | 29 | Yes | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66131 | 926 | 2590 | 33 | 15/EM/0229 | PROFILE (2819MA1003) | 2015-07-29 | 2015-08-05 | No |  | 7 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66132 | 926 | 2590 | 33 | 15/LO/0853 | Switch Study of Dolutegravir + Rilpivirine in HIV infected adults636 | 2015-07-13 | 2015-07-28 | Yes | 2015-07-29 | 15 | 1 | 16 | Yes | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66133 | 926 | 2590 | 33 | 15/LO/0652 | BMS AI468038:Phase 2b HIV1 Maturation Inhibitor study | 2015-07-23 | 2015-07-31 | No |  | 8 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66134 | 926 | 2590 | 33 | 15/YH/0239 | Comparison of dupilumab to dummy drug when added to asthma treatment | 2015-08-10 | 2015-08-10 | No |  | 0 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66135 | 926 | 2590 | 33 | 15/LO/1138 | SVR SOF Cirrhosis Registry Study | 2015-08-06 | 2015-08-14 | Yes | 2015-09-28 | 8 | 45 | 53 | Yes | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66136 | 926 | 2590 | 33 | 15/LO/0599 | Phase 1b of MPDL3280A + Obinutuzumab in Folicular and B-cell lymphoma | 2015-08-11 | 2015-08-19 | No |  | 8 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66137 | 926 | 2590 | 33 | 15/SC/0242 | BMN 270-201: Gene Therapy Study in Severe Haemophilia A Patients | 2015-07-29 | 2015-08-11 | Yes | 2015-09-29 | 13 | 49 | 62 | Yes | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66138 | 926 | 2590 | 33 | 15/SC/0306 | RANGE- Ramucirumab in Advanced Bladder Cancer (JVDC Study) | 2015-08-03 | 2015-08-07 | Yes | 2015-08-25 | 4 | 18 | 22 | Yes | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66139 | 926 | 2590 | 33 | 15/LO/0743 | Safety and effects of FP-02.2 -first doses in humans;v1 | 2015-08-19 | 2015-08-28 | No |  | 9 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66271 | 926 | 2590 | 33 | 15/SC/0065 | MEDI4736 and Tremelimumab in NSCLC (D4191C00004, ARCTIC Study) | 2015-05-20 | 2015-06-09 | Yes | 2015-08-25 | 20 | 77 | 97 | No | Unknown | Unknown | 2015-10-29 | 42306 | [9 empty] | Y | [5 empty] | VRA to NHS permission was within the 30 days. The study team had two directly competing studies with the same sponsor there was an agreement in place with the sponsor that recruitment would occur in this study only after their other directly competing study had closed to recruitment this meant that the 70 day target could not be achieved. The study has now fully opened and the team have exceeded their target. | Sponsor
66272 | 926 | 2590 | 33 | 15/LO/0523 | Efficacy & safety of PT003, PT005 and PT001 in moderate to severe COPD | 2015-08-11 | 2015-08-28 | Yes | 2015-09-25 | 17 | 28 | 45 | Yes | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66273 | 926 | 2590 | 33 | 14/YH/1175 | Ibrutinib in Chronic Lymphocytic Leukaemia/Small Lymphocytic Lymphoma | 2015-04-10 | 2015-05-11 | Yes | 2015-09-02 | 31 | 114 | 145 | No | Unknown | Unknown | 2015-10-29 | 42306 |  |  |  |  | Y | [10 empty] | VRA to NHS permission was 31 just out of the 30 day window. However lack of staff at site meant that the first recruit was outside of the 70 day target the site has now been closed by the sponsor to any further recruitment. | NHS Provider
66274 | 926 | 2590 | 33 | 15/LO/0145 | MONARCH | 2015-04-22 | 2015-04-24 | No |  | 2 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 |  |  | Y | [12 empty] | Two patients were screened but study closed by sponsor before any participants could be enrolled so the team could not meet their target | Sponsor
66275 | 926 | 2590 | 33 | 12/LO/1798 | Edwards SAPIEN 3 | 2015-09-10 | 2015-09-10 | No |  | 0 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [9 empty] | Y | [5 empty] | Study transferred from UCLH heart hospital to Barts NHS Trust as part of the NHS cardiac service reconfiguration in London. We have taken over the follow up visits for this study there will be no further recruitment into this study. Barts NHS Trust as opened as a site so that the follow up visits can take place. | Neither
66278 | 926 | 2590 | 33 | 11/LO/1514 | Direct Flow Medical Percutaneous Aortic Valve 18F System IP 010 | 2015-09-10 | 2015-09-11 | No |  | 1 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [9 empty] | Y | [5 empty] | Study transferred from UCLH heart hospital to Barts NHS Trust as part of the NHS cardiac service reconfiguration in London. We have taken over the follow up visits for this study there will be no further recruitment into this study. Barts NHS Trust as opened as a site so that the follow up visits can take place. | Neither
66279 | 926 | 2590 | 33 | 15/LO/0897 | A PHASE III, OPEN-LABEL, RANDOMIZED STUDY OF MPDL3280A (Anti PD-L1 ANTIBODY) IN COMBINATION | 2015-07-22 | 2015-07-23 | Yes | 2015-08-18 | 1 | 26 | 27 | Yes | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66280 | 926 | 2590 | 33 | 14/LO/2024 | A phase I, first-in-human study of escalating doses of oral tvb-2640 in patients with solid tumors | 2015-05-11 | 2015-07-13 | No |  | 63 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 |  |  |  | Y | [11 empty] | VRA to NHS permisison was outside of the 30 day window as the sponsor was unable to provide the phramacy manual so NHS permission could not be granted. Site remained in set up so no recruitment could take palce within the 70 day window and was activated finally by the the sponsor on 19 /10/2015 | Sponsor
66281 | 926 | 2590 | 33 | 14/NE/1215 | IPI-145 with Rituximab vs Rituximab in Follicular Lymphoma | 2015-05-08 | 2015-05-08 | No |  | 0 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 |  |  |  | Y | [11 empty] | VRA to NHS permission was within the 30 day benchmark however the site remained in set up and opened to recruitment by the sponsor outside of the 70 day window. To date no participants have been recruited | Sponsor
66282 | 926 | 2590 | 33 | 15/LO/0236 | A Phase II Trial of MK-3475 in Subjects with Bladder Cancer | 2015-06-22 | 2015-07-08 | No |  | 16 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 |  |  |  | Y | [11 empty] | VRA to NHS permission was within the 30 day window, however the site activation was delayed by the sponsor and as of 30/09/2015 the site had not been activated and remained in setup. | Sponsor
66283 | 926 | 2590 | 33 | 15/NE/0149 | Phase 2 study in Patients with Recurrent or Metastatic SCCHN | 2015-09-02 | 2015-09-16 | No |  | 14 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66284 | 926 | 2590 | 33 | 14/LO/1514 | An Open Label Study of COR—003 on the treatment of Cushing's syndrome | 2015-07-29 | 2015-09-14 | No |  | 47 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66285 | 926 | 2590 | 33 | 15/SW/0086 | Daratumumab + rd vs rd in subjects with previously untreated MM | 2015-08-27 | 2015-08-27 | No |  | 0 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66286 | 926 | 2590 | 33 | 15/NW/0505 | Switch to MK1439A from Ritonavir-boosted Protease Inhibitor regimen in HIV-1 infected subjects | 2015-09-23 | 2015-09-24 | No |  | 1 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66287 | 926 | 2590 | 33 | 15/LO/1163 | 1717- Phase 3b switch study with F/TAF in HIV-1 infected subjects | 2015-09-21 | 2015-09-23 | No |  | 2 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66288 | 926 | 2590 | 33 | 15/LO/0881 | MK-1439A versus ATRIPLA in treatment-naïve HIV1 infected subjects | 2015-09-14 | 2015-09-14 | No |  | 0 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66289 | 926 | 2590 | 33 | 15/LO/0212 | A study to see if GS-6615 shortens QT interval in patients with LQT3 | 2015-07-22 | 2015-09-21 | No |  | 61 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [7 empty] | Y | [7 empty] | Delays with the sponsor contracting process contract only signed off by sponsor on 11/09/2015 site signed on 15/09/2015 NHS permission issued on 21/09/2015. Site in set up | Sponsor
66290 | 926 | 2590 | 33 | 11/WM/0279 | NECTAR-HF Research Study | 2015-09-18 | 2015-09-22 | No |  | 4 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [9 empty] | Y | [5 empty] | Study transferred from UCLH heart hospital to Barts NHS Trust as part of the NHS cardiac service reconfiguration in London. We have taken over the follow up visits for this study there will be no further recruitment into this study. Barts NHS Trust as opened as a site so that the follow up visits can take place. | Neither
66292 | 926 | 2590 | 33 | 15/SW/0194 | Phase III study with Finerenone in Type II Diabetes and DKD, Renal | 2015-09-28 | 2015-09-29 | No |  | 1 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66293 | 926 | 2590 | 33 | 15/SC/0448 | Phase III study with Finerenone in Type II Diabetes and DKD, CV | 2015-09-29 | 2015-09-29 | No |  | 0 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66294 | 926 | 2590 | 33 | 15/LO/1063 | M14004 AbbVie DAA's +Ribavirin in HCV Gt1 or 4/HIV Type 1 Coinfection | 2015-08-04 | 2015-08-18 | Yes | 2015-08-25 | 14 | 7 | 21 | Yes | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66295 | 926 | 2590 | 33 | 15/LO/1132 | A Phase II Clinical Trial of Pembrolizumab (MK3475) as Monotherapy for Metastatic TripleNegative Breast Cancer (mTNBC) â€“ (KEYNOTE | 2015-09-30 | 2015-09-30 | No |  | 0 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | [16 empty] | Please Select...
66296 | 926 | 2590 | 33 | 14/LO/2160 | Improving the detection of active TB in A&E departments (ACE Study) | 2015-05-21 | 2015-09-14 | No |  | 116 |  |  |  | Unknown | Unknown | 2015-10-29 | 42306 | Y | [14 empty] | SSIF was submitted on 12/05/2015 however the studywide review was not completed until 16/07/2016 therefore NHS permission could not be given within the target time. The study is in set up. | Neither