## Sheet1
ID | TrustId | SubmissionId | MetaSubmissionId | Research Ethics Committee Reference Number | Name of Trial | Date of Receipt of Valid Research Application | Date of NHS Permission | First Patient Recruited? | Date of First Patient Recruited | Duration between VRA and NHS Permission | Duration between NHS Permission and First Patient | Duration between VRA and First Patient | Benchmark Met | A - Permissions delayed/ denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | K - Not Used | L - Not Used | M - Not Used | N - Not Used | O - Not Used | Comments | Reasons for delay correspond to:
46442 | 926 | 1469 | 28 | 12/LO/1319 | A Phase 2 study for older adults with Acute Lymphoblastic Leukaemia | 2013-12-03 | 2014-01-27 | No |  | 55 | [11 empty] | Y | [6 empty] | Delays in VRA to NHS permission was due to the delay in obtaining fully signed contracts from sponsor as this is a rare condition and difficult to recruit to accrual will be slow. | Sponsor
46443 | 926 | 1469 | 28 | 13/EM/0349 | MANTA | 2014-01-08 | 2014-01-08 | Yes | 2014-04-08 | 0 | 90 | 90 | No | [6 empty] | Y | [8 empty] | No eligible patient difficult study to recruit to, 1 patient consented on 08-Apr-2014 | Neither
46444 | 926 | 1469 | 28 | 13/SC/0558 | CAIN457A3301 | 2014-01-14 | 2014-01-21 | Yes | 2014-05-28 | 7 | 127 | 134 | No | [6 empty] | Y | [8 empty] | No eligible patient before the 70 days benchmark, 2 (+1 screen fail) | Neither
46445 | 926 | 1469 | 28 | 13/SC/0486 | NOVAP | 2014-01-27 | 2014-01-27 | Yes | 2014-03-05 | 0 | 37 | 37 | Yes | [16 empty] | Please Select...
46446 | 926 | 1469 | 28 | 04/MRE07/35 | STAMPEDE | 2014-01-09 | 2014-01-28 | Yes | 2014-06-19 | 19 | 142 | 161 | No | [9 empty] | Y | [5 empty] | The reason for the delay is that as we opened the majority of the arms of Stampede (for which we had plenty of eligible patients) closed and there is currently only one arm open with narrow eligibility criteria. | Neither
46447 | 926 | 1469 | 28 | 13/LO/1199 | JADY Extension | 2014-01-15 | 2014-01-29 | Yes | 2014-02-24 | 14 | 26 | 40 | Yes | [16 empty] | Please Select...
46448 | 926 | 1469 | 28 | 13/LO/1115 | PIVOTAL | 2014-02-07 | 2014-02-14 | Yes | 2014-04-16 | 7 | 61 | 68 | Yes | [16 empty] | Please Select...
46449 | 926 | 1469 | 28 | 13/LO/0669 | MINIMISE STEMI trial version 1 | 2014-02-24 | 2014-03-20 | Yes | 2014-04-22 | 24 | 33 | 57 | Yes | [16 empty] | Please Select...
46450 | 926 | 1469 | 28 | 13/LO/0576 | Evaluating an automated diabetic retinopathy screening tool | 2013-11-25 | 2014-01-22 | Yes | 2014-01-30 | 58 | 8 | 66 | Yes | [16 empty] | Please Select...
46451 | 926 | 1469 | 28 | 10/H0302/51 | TB-REACH | 2014-01-13 | 2014-01-16 | Yes | 2014-10-17 | 3 | 274 | 277 | No | [9 empty] | Y | [5 empty] | Recruited delayed initially as a substantial amendment was submitted by the sponsor and approved by the Ethics Committee. The site has now met its recruitment target | Sponsor
46452 | 926 | 1469 | 28 | 12/EM/0095 | TOTAL | 2014-01-29 | 2014-01-29 | Yes | 2014-03-17 | 0 | 47 | 47 | Yes | [16 empty] | Please Select...
46453 | 926 | 1469 | 28 | 13/SW/0186 | EFFECT Efficacy of Fluticasone/Formoterol in COPD Treatment FLT3509 | 2014-01-08 | 2014-01-13 | Yes | 2014-06-03 | 5 | 141 | 146 | No | [6 empty] | Y | [8 empty] | 2 screened. 1 failed screening and the other was discontinued early due to health reasons. | Neither
46454 | 926 | 1469 | 28 | 12/NW/0509 | RELIEF | 2014-03-12 | 2014-03-13 | Yes | 2014-03-28 | 1 | 15 | 16 | Yes | [16 empty] | Please Select...
46455 | 926 | 1469 | 28 | 13/LO/1284 | ROX Registry | 2014-01-08 | 2014-01-31 | No |  | 23 | [6 empty] | Y | [11 empty] | Recruitment was put on hold whilst a sub study was prepared by the sponsor recruitment has now been extended until December 2015 | Sponsor
46456 | 926 | 1469 | 28 | 13/LO/1881 | OPUS 1 (Biocryst) | 2014-02-04 | 2014-02-20 | Yes | 2014-02-24 | 16 | 4 | 20 | Yes | [16 empty] | Please Select...
46457 | 926 | 1469 | 28 | 13/LO/1766 | EMR 100070-001: MSB0010718C in subjects with solid tumours | 2014-01-20 | 2014-02-18 | Yes | 2014-06-09 | 29 | 111 | 140 | No | [9 empty] | Y | [5 empty] | Initial delay caused as the Investigator was not satisfied at initial SIV and raised issues relating to the toxicity of the drug and requested review and further information from sponsor. Site now fully activated since 29th April however this is a very small patient population first patient has now been recruited. | Both
46458 | 926 | 1469 | 28 | 13/LO/1513 | CC-5013-NHL-007 Indolent lymphoma: Augment trial | 2013-12-20 | 2014-02-10 | No |  | 52 | [6 empty] | Y | [11 empty] | The sponsor submitted a substantial amendment after initial permission this has delayed the opening of the study it is still in set up. | Sponsor
46459 | 926 | 1469 | 28 | 13/YH/0174 | Adalimumab in Non-Radiographic Axial Spondyloarthritis | 2014-03-18 | 2014-03-18 | Yes | 2014-05-15 | 0 | 58 | 58 | Yes | [16 empty] | Please Select...
46460 | 926 | 1469 | 28 | 13/NW/0791 | GSK1278863 in CKD PHI113633 Dialysis study in anemia associated with Chronic Kidney Disease | 2014-03-11 | 2014-03-20 | Yes | 2014-06-26 | 9 | 98 | 107 | No | [6 empty] | Y | [8 empty] | Recruitment was difficult complex study design; patient approached but did not want to take part in this study. The study was closed to recruitment early by the sponsor. | Neither
46461 | 926 | 1469 | 28 | 13/NI/0148 | WB28182 | 2013-11-27 | 2014-02-11 | Yes | 2014-05-15 | 76 | 93 | 169 | No |  |  |  | Y | [11 empty] | Delay in set up by Sponsor CRA at SIV damaged the equipment which had to be replaced which took one month in addition patients entering this study are rolling over from the first phase of the study and can only enter when phase 1 visits are complete | Sponsor
46462 | 926 | 1469 | 28 | 13/LO/1490 | GS-US-320-0110 | 2014-02-12 | 2014-03-25 | Yes | 2014-06-27 | 41 | 94 | 135 | No | [9 empty] | Y | [5 empty] | The sponsor would not release the BH contracts whilst resolving the UCLH/Royal Free contracts so we were unable to issue NHS permission within 30 days of a complete SSIF submission then No eligible patients were seen to meet the 70 day benchmark | Both
46463 | 926 | 1469 | 28 | 13/NE/0260 | OPTI-MIND 2 Protocol 07-12 | 2014-02-18 | 2014-02-20 | Yes | 2014-04-25 | 2 | 64 | 66 | Yes | [16 empty] | Please Select...
46464 | 926 | 1469 | 28 | 13/LO/1752 | Atopic Dermatitis CIM003JG | 2014-02-18 | 2014-02-24 | Yes | 2014-08-05 | 6 | 162 | 168 | No | [6 empty] | Y | [8 empty] | 3 screen failures and all referred patients are ineligible as have asthma which is an exclusion to entry in the study | Neither
46465 | 926 | 1469 | 28 | 13/SC/0325 | GENA-21 | 2013-11-05 | 2014-01-15 | Yes | 2014-04-22 | 71 | 97 | 168 | No | [7 empty] | Y | [7 empty] | VRA to NHS permission was 71 days due to contracting delays with the sponsor the contact was returned on 14/01/2014 (day 70) NHS permission was issued the following day 15/01/2014 (day 71). | Sponsor
46466 | 926 | 1469 | 28 | 12/LO/1759 | OuTSMART | 2014-01-13 | 2014-01-24 | Yes | 2014-03-24 | 11 | 59 | 70 | Yes | [16 empty] | Please Select...
46467 | 926 | 1469 | 28 | 13/WM/0114 | SHINE MCL3002 | 2014-01-14 | 2014-04-03 | Yes | 2014-04-23 | 79 | 20 | 99 | No | [7 empty] | Y | [7 empty] | Contract delays caused by the sponsor resulted in a delay to NHS permission so the 70 days benchmark could not be met. The study has now recruited one patient the target was two. | Sponsor
46468 | 926 | 1469 | 28 | 13/EE/0257 | MK 5172047 | 2014-01-17 | 2014-01-17 | Yes | 2014-02-03 | 0 | 17 | 17 | Yes | [16 empty] | Please Select...
46469 | 926 | 1469 | 28 | 08/H1102/92 | TARDIS | 2014-01-31 | 2014-01-31 | Yes | 2014-03-19 | 0 | 47 | 47 | Yes | [16 empty] | Please Select...
46470 | 926 | 1469 | 28 | 13/LO/1489 | GS-US-320-0108 | 2014-02-12 | 2014-03-25 | Yes | 2014-04-24 | 41 | 30 | 71 | No | [9 empty] | Y | [5 empty] | The sponsor would not release the BH contracts whilst resolving the UCLH/Royal Free contracts so we were unable to issue NHS permission within 30 days of a complete SSIF submission then No eligible patients were seen to meet the 70 day benchmark | Both
46471 | 926 | 1469 | 28 | 13/SC/0384 | Tremelimumab in PMM | 2014-02-13 | 2014-02-13 | Yes | 2014-03-04 | 0 | 19 | 19 | Yes | [16 empty] | Please Select...
46472 | 926 | 1469 | 28 | 13/NI/0093 | Givinostat in JAK2V617F | 2014-02-24 | 2014-02-24 | No |  | 0 | [11 empty] | Y | [6 empty] | Rare disease | Neither
46473 | 926 | 1469 | 28 | 11/H0722/8 | Rapid Identification via Interferon Gamma test for Active Tuberculosis | 2014-03-03 | 2014-03-13 | Yes | 2014-04-14 | 10 | 32 | 42 | Yes | [16 empty] | Please Select...
46474 | 926 | 1469 | 28 | 13/LO/1323 | LA38-0411 Iron Overload | 2014-03-03 | 2014-03-07 | Yes | 2014-07-14 | 4 | 129 | 133 | No |  |  |  | Y | [11 empty] | Sponsor delayed IMP release to site. Set up also delayed through late provision of documentation from sponsor. Scans were outsourced to another site and an additional contract with sponsor required. To date site has screened 3 participants all screen failures. | Sponsor
46475 | 926 | 1469 | 28 | 13/EM/0375 | Triple 6 A Phase III Study of CHF5993 in Patients with Severe COPD | 2014-03-07 | 2014-03-07 | Yes | 2014-04-14 | 0 | 38 | 38 | Yes | [16 empty] | Please Select...
46476 | 926 | 1469 | 28 | 13/NW/0793 | GSK1278863 in CKD | 2014-03-11 | 2014-03-12 | Yes | 2014-05-18 | 1 | 67 | 68 | Yes | [16 empty] | Please Select...
46477 | 926 | 1469 | 28 | 13/LO/1906 | SAR153191 in RA LTS11210 | 2014-03-11 | 2014-03-14 | Yes | 2014-04-24 | 3 | 41 | 44 | Yes | [16 empty] | Please Select...
46478 | 926 | 1469 | 28 | 13/LO/1795 | CSL830_3001 in HAE | 2014-02-27 | 2014-03-12 | Yes | 2014-06-17 | 13 | 97 | 110 | No |  |  |  |  | Y | [10 empty] | Staff issue and availability | NHS Provider
46479 | 926 | 1469 | 28 | 13/LO/1111 | eSTI2 chlamydia clinical care pathway pilot study | 2014-03-14 | 2014-03-17 | Yes | 2014-07-24 | 3 | 129 | 132 | No |  |  |  | Y | [11 empty] | Study set up delayed until 23.6.14 collaborator who was providing IT support to the sponsor had delays in implementing the infrastructure required to support the study. The sponsor could not fully activate the site recruitment was then delayed. | Sponsor
46480 | 926 | 1469 | 28 | 14/SC/0032 | B1481022 | 2014-03-17 | 2014-05-02 | Yes | 2014-06-05 | 46 | 34 | 80 | No | [7 empty] | Y | [7 empty] | SSIF validated put study on hold due to outstanding contract signature by sponsor which delayed NHS permission | Sponsor
46481 | 926 | 1469 | 28 | 14/NW/0006 | Calcipotriol in Psoriasis LP0076-1017 | 2014-03-17 | 2014-03-18 | Yes | 2014-07-23 | 1 | 127 | 128 | No | [9 empty] | Y | [5 empty] | Only 1 possible patient identified, and she was not able to go ahead as still at school (this is an adolescent study) and taking her exams. To be contacted once exams are finished | Neither
46482 | 926 | 1469 | 28 | 14/SC/0033 | B1481038 | 2014-03-17 | 2014-05-02 | No |  | 46 | [8 empty] | Y | [9 empty] | VRA to NHS permission exceeded 30 days due to contracting negotiations being protracted sponsor delays. Contracts signed by sponsor on 30/04/2014 sent back to site NHS permission issued 02/05/2014. To date no eligible patients seen this is a hard to recruit to study with very strict eligibility criteria as most patients have their LDL levels under control. The sponsor is now reviewing the protocol with a view to amending these criteria to help national recruitment. | Neither
46483 | 926 | 1469 | 28 | 13/EE/0433 | LEADLESS Observational Study | 2014-04-02 | 2014-04-03 | Yes | 2014-04-09 | 1 | 6 | 7 | Yes | [16 empty] | Please Select...
46484 | 926 | 1469 | 28 | 14/EM/0024 | CAIN457F2318 | 2014-04-03 | 2014-04-07 | Yes | 2014-05-23 | 4 | 46 | 50 | Yes | [16 empty] | Please Select...
46485 | 926 | 1469 | 28 | 14/LO/0083 | CV risk in HIV patients switching from a boosted PI to DTG | 2014-04-04 | 2014-04-14 | Yes | 2014-06-24 | 10 | 71 | 81 | No | [9 empty] | Y | [5 empty] | Difficulty with getting local lab sign off Sponsor authorisation to open recruitment was finally given on 10 JUN2014 | Both
46486 | 926 | 1469 | 28 | 14/EM/0086 | CAIN2314- 16-week Efficacy and 3-year Safety, Tolerability and Efficacy of Secuk | 2014-04-15 | 2014-04-25 | Yes | 2014-05-12 | 10 | 17 | 27 | Yes | [16 empty] | Please Select...
46487 | 926 | 1469 | 28 | 11/AL/0319 | Fractures and Bisphosphonates the FaB trial | 2014-05-12 | 2014-05-12 | Yes | 2014-06-03 | 0 | 22 | 22 | Yes | [16 empty] | Please Select...
46488 | 926 | 1469 | 28 | 14/LO/0451 | Electrical Stimulation use with pelvic fracture rehabilitation Vrs 1 | 2014-05-27 | 2014-05-28 | Yes | 2014-05-28 | 1 | 0 | 1 | Yes | [16 empty] | Please Select...
46489 | 926 | 1469 | 28 | 14/LO/0358 | Electronic cigarettes: Nicotine delivery in users- PK | 2014-05-28 | 2014-05-28 | Yes | 2014-06-25 | 0 | 28 | 28 | Yes | [16 empty] | Please Select...
46490 | 926 | 1469 | 28 | 14/SC/0225 | GSUS3111089 Phase 3 double-blind study of F/TAF in HIV-1 positive patients | 2014-06-09 | 2014-06-27 | Yes | 2014-07-10 | 18 | 13 | 31 | Yes | [16 empty] | Please Select...
46491 | 926 | 1469 | 28 | 13/SC/0495 | RES117287 | 2014-04-09 | 2014-04-10 | Yes | 2014-04-15 | 1 | 5 | 6 | Yes | [16 empty] | Please Select...
46492 | 926 | 1469 | 28 | 13/SS/0051 | TRIOphysio | 2014-05-16 | 2014-05-19 | Yes | 2014-07-10 | 3 | 52 | 55 | Yes | [16 empty] | Please Select...
46493 | 926 | 1469 | 28 | 13/SC/0581 | VIOLA (Version 1.0 15Oct2013) | 2014-05-19 | 2014-05-22 | Yes | 2014-08-06 | 3 | 76 | 79 | No | [5 empty] | Y | [9 empty] | No eligible patients seen hard to recruit to study | Neither
46494 | 926 | 1469 | 28 | 13/EE/0151 | CD-IA-CAM-3001-1109 | 2014-06-11 | 2014-06-12 | Yes | 2014-09-23 | 1 | 103 | 104 | No | [6 empty] | Y | [8 empty] | This is the extension study (The core study is CD-IA-CAM-3001-1107). No patient has moved from core to the extension study yet. | Neither
46495 | 926 | 1469 | 28 | 14/LO/0121 | A Phase II, randomized, placebo-controlled study of paclitaxel in combination with the Akt inhibitor AZD5363 in triple-negative advanced or metastatic breast cancer -PAKT | 2014-06-11 | 2014-06-13 | No |  | 2 | [7 empty] | Y | [10 empty] | Study still in set up. The study does not have sufficient nursing infrastructure support to open the study | Neither
46496 | 926 | 1469 | 28 | 14/WS/0002 | AMVISION1: 20090406 | 2014-06-19 | 2014-06-20 | Yes | 2014-11-06 | 1 | 139 | 140 | No | [6 empty] | Y | [8 empty] | The first patient pre-screened was ineligible and 2nd patient pre-screened and has yet to return back to site. The study is actively open for recruitment. | Neither
46497 | 926 | 1469 | 28 | 13/YH/0162 | HABSelect – Hyaluronic Acid Binding Sperm selection_V1.0 | 2014-06-06 | 2014-06-06 | Yes | 2014-06-24 | 0 | 18 | 18 | Yes | [16 empty] | Please Select...
46498 | 926 | 1469 | 28 | 14/SC/0104 | D5613C00001 AZD1722 for phosphate lowering in dialysis patients | 2014-04-16 | 2014-06-05 | Yes | 2014-06-25 | 50 | 20 | 70 | Yes | [16 empty] | Please Select...
46499 | 926 | 1469 | 28 | 13/SC/0554 | TRP Novonordisk NN8226-4064 | 2014-04-01 | 2014-06-26 | No |  | 86 | [5 empty] | Y | [12 empty] | The Novonordisk study has been discontinued prior to opening at Barts Health. The compound under investigation was found to have non-significant activity against its target in late phase II studies; therefore this study has been cancelled | Sponsor
46500 | 926 | 1469 | 28 | 09/H0709/56 | PEXIVAS | 2014-04-04 | 2014-04-07 | Yes | 2014-07-21 | 3 | 105 | 108 | No | [5 empty] | Y | [9 empty] | No eligible patients presented to the unit in time to meet the 70 day target but the team have now recruited 2 patients | Neither
46501 | 926 | 1469 | 28 | 13/YH/0282 | ACT MOVE ML28641 | 2014-04-04 | 2014-06-05 | Yes | 2014-09-30 | 62 | 117 | 179 | No |  |  |  | Y | [11 empty] | The sponsor submitted an amendment this meant that NHS permission was delayed until the amendment was approved. Sponsor requested activation of site to be delayed until the amendment approval was in place. The SIV took place on 14/07/14. Site pre-screened 13 patients ( this means patients were identified and approached to take part in the trial) and 3 were randomised which was their target | Sponsor
46502 | 926 | 1469 | 28 | 14/LO/0132 | RAFT-Robotic surgery after focal ablation therapy | 2014-05-01 | 2014-05-01 | No |  | 0 | [6 empty] | Y | [11 empty] | Site not yet activated sponsor has requested an amendment to the study prior to site activation | Neither
46503 | 926 | 1469 | 28 | 14/NW/0008 | MK8259-032 Go Colitis | 2014-05-01 | 2014-05-19 | Yes | 2014-09-15 | 18 | 119 | 137 | No |  |  |  | Y | [11 empty] | Study set up delayed due to issues with the home delivery system of IMP to patients required additional contracts to be set up | Sponsor
46504 | 926 | 1469 | 28 | 13/EM/0423 | GWP42004 in Type 2 diabetes | 2014-05-06 | 2014-06-05 | No |  | 30 | [9 empty] | Y | [8 empty] | No eligible patient has been recruited to this study due to screen failures | Neither
46505 | 926 | 1469 | 28 | 13/LO/0881 | NOCTURNAL HYPOGLYCAEMIA | 2014-05-09 | 2014-05-15 | Yes | 2014-10-21 | 6 | 159 | 165 | No |  |  |  |  | Y | [10 empty] | There were delays in appointing a researcher to undertake the study so no patients could be approached. Staffing issues have been resolved and the team have now recruited 4 patients | NHS Provider
46506 | 926 | 1469 | 28 | 14/LO/0022 | WO29074 Randomised Phase II study in untreated advanced renal cell carcinoma | 2014-05-20 | 2014-05-30 | Yes | 2014-07-15 | 10 | 46 | 56 | Yes | [16 empty] | Please Select...
46507 | 926 | 1469 | 28 | 14/SC/0100 | Assessment of Patients Treated With JETREA® for Vitreomacular Traction | 2014-06-16 | 2014-06-16 | Yes | 2014-07-23 | 0 | 37 | 37 | Yes | [16 empty] | Please Select...
46508 | 926 | 1469 | 28 | 12/SS/0138 | RESTART | 2014-05-16 | 2014-05-23 | No |  | 7 | [8 empty] | Y | [9 empty] | No eligible patients seen. The study requires the clinician to be in equipoise concerning the treatment pathway of patients with a bleed in the brain. 5 patients screened however there was a definite treatment path so the patients were not eligible for the trial as dictated by the protocol. | Neither
46509 | 926 | 1469 | 28 | 11/SC/0528 | INTERLACE | 2014-05-01 | 2014-05-01 | No |  | 0 | [9 empty] | Y | [8 empty] | Several patients have been screened but were screen failures so no participants have been randomised to date | Neither
46510 | 926 | 1469 | 28 | 13/YH/0229 | GO2 - Alternative chemotherapy for frailer patients with advanced gastric or oesophageal cancer | 2014-01-28 | 2014-02-12 | No |  | 15 | [6 empty] | Y | [11 empty] | Our site was activated by the sponsor on the 14/04/2014 which meant that the site could not recruit within the 70 day benchmark. Difficult to recruit participants for this study due to strict inclusion criteria 5 patients screened to date, but none been eligible to proceed. | Sponsor
46511 | 926 | 1469 | 28 | 12/LO/1822 | PANTHER | 2014-03-20 | 2014-03-20 | Yes | 2014-07-16 | 0 | 118 | 118 | No |  |  |  | Y | [11 empty] | Sponsor delayed the SIV which was held on the 3/6/2014 which was past the 70 day benchmark 2 patients have now been recruited | Sponsor
46512 | 926 | 1469 | 28 | 11/WS/0039 | A Phase I/IIa Trial of AZD4547 in combination with CX: The FACING Study | 2014-03-20 | 2014-03-20 | No |  | 0 | [6 empty] | Y | [11 empty] | Site not activated by the sponsor and is still in set up. | Sponsor
46513 | 926 | 1469 | 28 | 14/SC/0034 | 997HA307 - Previously Treated Subjects With Severe Haemophilia A | 2014-03-18 | 2014-06-30 | Yes | 2014-08-18 | 104 | 49 | 153 | No | [7 empty] | Y | [7 empty] | NHS permission delayed due to contacting issues with the sponsor. The site has since exceeded its target and is now in follow up | Sponsor
46514 | 926 | 1469 | 28 | 14/EE/1048 | ESTEEM | 2014-07-16 | 2014-08-29 | Yes | 2014-09-12 | 44 | 14 | 58 | Yes | [16 empty] | Please Select...
46515 | 926 | 1469 | 28 | 14/LO/0418 | CEDAR | 2014-06-27 | 2014-07-01 | Yes | 2014-07-18 | 4 | 17 | 21 | Yes | [16 empty] | Please Select...
46516 | 926 | 1469 | 28 | 13/EM/0266 | Low dose cyclophosphamide +/- nintedanib in advanced ovarian cancer | 2014-08-12 | 2014-08-13 | No |  | 1 | [6 empty] | Y | [11 empty] | Site activated by sponsor on 23/12/14 outside of the 70 day window. | Sponsor
46517 | 926 | 1469 | 28 | 14/LO/0438 | Cook MyoSite AMDC Fecal Incontinence Clinical Study 09025 | 2014-06-25 | 2014-07-07 | Yes | 2014-08-01 | 12 | 25 | 37 | Yes | [16 empty] | Please Select...
46518 | 926 | 1469 | 28 | 14/NW/0138 | OPTIMIZE RO2455302RD | 2014-06-18 | 2014-07-04 | Yes | 2014-08-18 | 16 | 45 | 61 | Yes | [16 empty] | Please Select...
46519 | 926 | 1469 | 28 | 13/LO/1517 | DOLOMITES 1517-CL-0610 Phase 3 Study of ASP1517 (FG-4592) | 2014-06-18 | 2014-07-04 | Yes | 2014-12-09 | 16 | 158 | 174 | No | [5 empty] | Y | [9 empty] | No eligible patients seen | Neither
46520 | 926 | 1469 | 28 | 13/NW/0496 | Pregabalin in subjects with Primary Generalised TonicClonic | 2014-07-01 | 2014-07-17 | No |  | 16 | [8 empty] | Y | [9 empty] | No eligible patients seen | Neither
46521 | 926 | 1469 | 28 | 14/NW/0055 | Pregabalin Open Label Follow up study of A0081105 | 2014-07-02 | 2014-07-25 | No |  | 23 | [8 empty] | Y | [9 empty] | No eligible patients seen | Neither
46522 | 926 | 1469 | 28 | 14/SC/0178 | GSUS3120123 | 2014-06-12 | 2014-08-11 | No |  | 60 | [6 empty] | Y | [11 empty] | Study still in setup there is an issue with the supply of the IMP (retuximab) and the sponsor currently has a UK wide hold on the study we have no date for site activation as yet. | Sponsor
46523 | 926 | 1469 | 28 | 11/LO/1570 | CHEMO-T | 2014-08-01 | 2014-08-13 | No |  | 12 | [8 empty] | Y | [9 empty] | No eligible patients seen small potential population | Neither
46524 | 926 | 1469 | 28 | 13/LO/1473 | TIG3 | 2014-07-01 | 2014-07-01 | Yes | 2014-07-04 | 0 | 3 | 3 | Yes | [16 empty] | Please Select...
46525 | 926 | 1469 | 28 | 13/NE/0299 | EuroHYP1: European multicentre, randomised, phase III clinical trial of therapeutic hypothermia plus best medical treatment versus best medical treatment alone for acute ischaemic stroke | 2014-09-05 | 2014-09-05 | No |  | 0 | [9 empty] | Y | [8 empty] | Several patients screened but were screen failures site continues to look for participants | Neither
46526 | 926 | 1469 | 28 | 11/EM/0398 | A Phase III, Multi-center, Double-Blind, Randomized, Placebo Controlled Clinical Trial to Evaluate the Safety and Efficacy of MK0431A (A Fixed-Dose Combination Tablet of Sitagliptin and Metformin) in Pediatric Patients with Type 2 Diabetes Mellitus) | 2014-07-02 | 2014-09-02 | No |  | 62 | [6 empty] | Y | [11 empty] | Study suffered from extensive sponsor delays the VRA to NHS permission was 60 days. The sponsor delayed site activation and the site was only fully activated by the sponsor on 16/12/2014. The target is only one participant and the team are now actively looking for participants which will clearly be now outside of the 70 day benchmark | Sponsor
46527 | 926 | 1469 | 28 | 14/ES/0001 | Randomised, Double-Blind, Placebo-Controlled, Parallel-Group Study to Assess Cardiovascular Outcomes Following Treatment with Ertugliflozin (MK-8835/PF-04971729) in Participants with Type 2 Diabetes | 2014-09-09 | 2014-09-10 | Yes | 2014-11-04 | 1 | 55 | 56 | Yes | [16 empty] | Please Select...
46528 | 926 | 1469 | 28 | 14/YH/0088 | Phase I study of KHK2823 in AML or MDS | 2014-06-02 | 2014-06-06 | Yes | 2014-08-21 | 4 | 76 | 80 | No | [5 empty] | Y | [9 empty] | No eligible patients seen | Neither
46529 | 926 | 1469 | 28 | 13/NE/0126 | ASSIGN NEO.1.C/F | 2014-06-16 | 2014-06-20 | Yes | 2014-07-07 | 4 | 17 | 21 | Yes | [16 empty] | Please Select...
46530 | 926 | 1469 | 28 | 13/WA/0413 | EORTC 40085 | 2014-04-22 | 2014-05-07 | No |  | 15 | [5 empty] | Y | [12 empty] | The study has now been closed globally by the sponsor before the site was activated. | Sponsor
46531 | 926 | 1469 | 28 | 14/LO/0667 | MK5172/MK8742 in Subjects with HCV/HIV Co-Infection | 2014-05-19 | 2014-06-10 | Yes | 2014-06-12 | 22 | 2 | 24 | Yes | [16 empty] | Please Select...
46532 | 926 | 1469 | 28 | 13/EM/0154 | SWIFFT | 2014-06-19 | 2014-06-19 | Yes | 2014-07-10 | 0 | 21 | 21 | Yes | [16 empty] | Please Select...
46533 | 926 | 1469 | 28 | 14/WM/0135 | Daratumumab+Rd vs Rd in Relapsed or Refractory Multiple Myeloma | 2014-08-06 | 2014-08-14 | Yes | 2014-10-13 | 8 | 60 | 68 | Yes | [16 empty] | Please Select...
46534 | 926 | 1469 | 28 | 14/LO/0602 | An OpenLabel, Multicenter Evaluation of the Safety and Efficacy of Recombinant Coagulation Factor IX Fc Fusion Protein (rFIXFc; BIIB029) in the Prevention and Treatment of Bleeding in Previously Untreated Patients With Severe Hemophilia B | 2014-08-06 | 2014-09-16 | No |  | 41 | [11 empty] | Y | [6 empty] | Rare condition no patients seen | Neither
46535 | 926 | 1469 | 28 | 14/YH/1057 | A phase 3, multicenter, randomized, open-label study to compare the efficasy and safety of sofosbuvir/ GS-5816 fixed dose combination for 12 weeks with sofosbuvir and ribavirin for 24 weeks in subjects with chronic genotype 3 HCV Infection | 2014-09-09 | 2014-09-10 | Yes | 2014-09-15 | 1 | 5 | 6 | Yes | [16 empty] | Please Select...
46536 | 926 | 1469 | 28 | 14/WM/1056 | A Phase 3, Multicenter, Randomized, DoubleBlind, Placebo Controlled Study to Investigate the Efficacy and Safety of Sofosbuvir/GS5816 Fixed Dose Combination for 12 Weeks in Subjects with Chronic HCV | 2014-09-15 | 2014-09-26 | Yes | 2014-09-30 | 11 | 4 | 15 | Yes | [16 empty] | Please Select...
46537 | 926 | 1469 | 28 | 13/SC/0111 | FOCUS4: Molecular selection of therapy in colorectal cancer | 2014-01-22 | 2014-02-12 | No |  | 21 | [12 empty] | Y | [5 empty] | Site has not been fully activated by the sponsor. The study is on hold due to internal pathology delays. | Both
46538 | 926 | 1469 | 28 | 12/LO/1889 | FTY720 in Primary Progressive Multiple Sclerosis Open Label Extension | 2014-05-28 | 2014-06-17 | Yes | 2014-06-26 | 20 | 9 | 29 | Yes | [16 empty] | Please Select...
46539 | 926 | 1469 | 28 | 14/SC/0170 | Phase 3 study to test the effects of SA237 in patients with NMO&NMOSD SA-307JG | 2014-07-15 | 2014-07-31 | No |  | 16 | [9 empty] | Y | [8 empty] | No eligible patients seen 2 were screened but were screen failures | Neither
46540 | 926 | 1469 | 28 | 14/YH/0090 | Study to test ADIPEG20 in patients with mesothelioma and NSCLC V 02 | 2014-05-02 | 2014-07-11 | Yes | 2014-07-11 | 70 | 0 | 70 | Yes | [16 empty] | Please Select...
46541 | 926 | 1469 | 28 | 14/LO/0680 | MEDI4736 in NSCLC (D4191C00003, ATLANTIC Study) | 2014-07-15 | 2014-07-21 | Yes | 2014-09-05 | 6 | 46 | 52 | Yes | [16 empty] | Please Select...
46542 | 926 | 1469 | 28 | 14/LO/1042 | GO29293 AntiPDL1 | 2014-07-08 | 2014-07-28 | Yes | 2014-08-12 | 20 | 15 | 35 | Yes | [16 empty] | Please Select...
46543 | 926 | 1469 | 28 | 13/LO/1682 | Study of Maintenance Rucaparib in Relapsed Highgrade | 2014-04-01 | 2014-08-06 | No |  | 127 | [10 empty] | Y | [7 empty] | VRA to NHS permission delay caused through contracting delays with sponsor. Finalised costs and contract sent to sponsor on 13/06/2014 signed off by sponsor 05/08/2014 VRA submitted 01/04/2014 but study could not be signed off until contracts were signed on the 05/08 NHS permission issued 06/08/14. Study has yet to recruit as the patient population is small and inclusion criteria are very strict. | Sponsor
46544 | 926 | 1469 | 28 | 13/LO/1595 | CBT vs Standardised Medical Care to treat Dissociative Seizures | 2014-08-25 | 2014-09-30 | No |  | 36 | [8 empty] | Y | [9 empty] | The NHS permission was technically delayed by six days which caused this to go over the 30 day limit. Following NHS permission the study has not recruited anyone yet due to the strict inclusion criteria. | Neither
46974 | 926 | 1469 | 28 | 14/WM/0159 | SNIFFLE 2 Study | 2014-10-09 | 2014-10-10 | Yes | 2014-11-24 | 1 | 45 | 46 | Yes | [16 empty] | Please Select...
46975 | 926 | 1469 | 28 | 14/LO/0565 | Lubiprostone for the treatment of paediatric functional constipation | 2014-10-16 | 2014-11-24 | No |  | 39 | [6 empty] | Y | [11 empty] | Contracting delays held up NHS permission and exceeded the 30 day target. In addition the site has yet to be activated by the sponsor the is SIV planned for 23/01/2015 so any recruitment will be outside of the 70 day target | Sponsor
46976 | 926 | 1469 | 28 | 14/EM/1071 | D5136C00007 Ticagrelor for sickle cell disease in paediatric patients | 2014-11-05 | 2014-11-27 | No |  | 22 | [19 empty] | Please Select...
46977 | 926 | 1469 | 28 | 06/Q0703/40 | NV25361 | 2014-10-29 | 2014-10-29 | No |  | 0 | [19 empty] | Please Select...
46978 | 926 | 1469 | 28 | 06/Q0201/66 | ACST-2 version 3.2 | 2014-11-06 | 2014-11-06 | No |  | 0 | [19 empty] | Please Select...
46979 | 926 | 1469 | 28 | 14/EE/1120 | MK5172/MK8742 in HCV G1, 4, 6 with Inherited Blood Disorders | 2014-11-03 | 2014-11-12 | Yes | 2014-12-10 | 9 | 28 | 37 | Yes | [16 empty] | Please Select...
46980 | 926 | 1469 | 28 | 14/SC/1030 | G-TOG - Gentamicin in the Treatment of Gonorrhoea | 2014-09-26 | 2014-10-30 | No |  | 34 | [6 empty] | Y | [11 empty] | NHS permission was slightly delayed from the 30 day target. Site activation was delayed by the sponsor due to the availability of sponsor and site staff for training and availability of the IMP shipment to pharmacy. | Sponsor
46981 | 926 | 1469 | 28 | 14/LO/0185 | CSF neurofilaments - a Novel phase 2a neuroprotective trial in early SPMS (PROXIMUS) | 2014-04-23 | 2014-10-31 | No |  | 191 | [9 empty] | Y | [8 empty] | 3 patients screened, first one screened 12/NOV/14 all screen failures | Neither
46982 | 926 | 1469 | 28 | 13/LO/1579 | SPOT | 2014-08-26 | 2014-10-22 | Yes | 2014-12-10 | 57 | 49 | 106 | No |  |  |  | Y | [11 empty] | Site was not formally activated by the sponsor until 01/12/2014 which was outside of the 70 day target. The first recruit was 10 days later. | Sponsor
46983 | 926 | 1469 | 28 | 14/LO/0521 | Switching to, then stopping treatment with nilotinib for CML patients. | 2014-10-20 | 2014-11-11 | No |  | 22 | [12 empty] | Y | [5 empty] | The study has recruited 2 patients in the UK in one year and is 300 patients behind globally. Site has approached one patient who has declined the study and have three more patients who are considering the trial. | Neither
46987 | 926 | 1469 | 28 | 14/NW/1144 | MLN0264 in Pancreatic Adenocarcinoma | 2014-12-02 | 2014-12-02 | No |  | 0 | [19 empty] | Please Select...
46988 | 926 | 1469 | 28 | 14/LO/0673 | MLN9708 in Multiple Myeloma after Autologous Stem Cell Transplant | 2014-07-07 | 2014-11-14 | No |  | 130 | [8 empty] | Y | [9 empty] | No patients have been seen who fit the eligibility criteria | Neither
46989 | 926 | 1469 | 28 | 14/SC/1014 | The JANUS 1 Study Incyte INCB 18424362 | 2014-11-24 | 2014-11-27 | No |  | 3 | [19 empty] | Please Select...
46990 | 926 | 1469 | 28 | 14/NW/1143 | MLN0264 in Adenocarcinoma of the Stomach or Gastroesophageal Junction | 2014-11-26 | 2014-12-03 | No |  | 7 | [19 empty] | Please Select...
46991 | 926 | 1469 | 28 | 13/SC/0332 | Takeda TOMM40_301 Alzheimer's Disease study | 2014-11-10 | 2014-11-20 | No |  | 10 | [19 empty] | Please Select...
46995 | 926 | 1469 | 28 | 14/LO/1444 | 520-215 AfFIRM A Phase 2 Trial of Filanesib in Relapsed/Refractory MM | 2014-11-14 | 2014-12-03 | No |  | 19 | [19 empty] | Please Select...
46996 | 926 | 1469 | 28 | 14/EE/0102 | DU176b-F-E308 | 2014-11-25 | 2014-12-09 | No |  | 14 | [19 empty] | Please Select...
46997 | 926 | 1469 | 28 | 14/EM/0160 | AEGIS-I, Phase II, dose ranging study of CSL112 in Acute (MICSLCTHDL1277) | 2014-10-15 | 2014-10-21 | No |  | 6 | [6 empty] | Y | [11 empty] | Sponsor delayed activation until their previous safety feasibility study had been completed. Site was finally activated by the sponsor 19/01/2015 therefore all recruitment will be outside of the 70 day window. | Sponsor
46998 | 926 | 1469 | 28 | 10/H1010/31 | HPV-062 EXT:015 | 2014-09-19 | 2014-10-01 | Yes | 2014-11-26 | 12 | 56 | 68 | Yes | [16 empty] | Please Select...
46999 | 926 | 1469 | 28 | 14/LO/0392 | Randomised study of ABT-494 in subjects with Rheumatoid Arthritis | 2014-10-15 | 2014-10-16 | Yes | 2014-11-25 | 1 | 40 | 41 | Yes | [16 empty] | Please Select...
47002 | 926 | 1469 | 28 | 14/YH/1025 | Prodigy-I | 2014-11-24 | 2014-12-10 | No |  | 16 | [19 empty] | Please Select...
47003 | 926 | 1469 | 28 | 14/NW/1239 | Guselkumab in Psoriasis following inadequate Ustekinumab response | 2014-12-03 | 2014-12-15 | No |  | 12 | [19 empty] | Please Select...
47004 | 926 | 1469 | 28 | 14/NI/0043 | Study Reference KIT-302-03-01 | 2014-09-18 | 2014-10-09 | Yes | 2014-11-18 | 21 | 40 | 61 | Yes | [16 empty] | Please Select...
47005 | 926 | 1469 | 28 | 14/SC/1252 | NEXUS - 24 week Study to investigate new medicine Namilumab in patients | 2014-12-16 | 2014-12-16 | No |  | 0 | [19 empty] | Please Select...
47006 | 926 | 1469 | 28 | 14/NS/0089 | Hip 'Op | 2014-11-03 | 2014-11-06 | No |  | 3 | [19 empty] | Please Select...
47007 | 926 | 1469 | 28 | 14/LO/1195 | 997HA306 | 2014-11-18 | 2014-11-20 | No |  | 2 | [19 empty] | Please Select...
47008 | 926 | 1469 | 28 | 14/NE/1001 | ReActiv8 | 2014-12-19 | 2014-12-19 | No |  | 0 | [19 empty] | Please Select...
47009 | 926 | 1469 | 28 | 14/EM/1035 | Prospective Outcomes of Secondline Therapy in Acute GraftversusHost Study including ECP (POSTAGE) | 2014-12-18 | 2014-12-18 | No |  | 0 | [19 empty] | Please Select...
47010 | 926 | 1469 | 28 | 13/LO/1886 | IPI-145 in subjects with refractory iNHL | 2014-10-24 | 2014-11-10 | No |  | 17 | [19 empty] | Please Select...
47011 | 926 | 1469 | 28 | 14/LO/0171 | British Childhood Cancer Survivor Study - Case-Control Studies - v1.0 | 2014-05-22 | 2014-10-03 | No |  | 134 | [12 empty] | Y | [5 empty] | Delays in issuing honorary access for researchers delayed NHS permission and so the 70 day benchmark cannot be met | NHS Provider
47013 | 926 | 1469 | 28 | 14/EM/1059 | 047 FIT (Fostamatinib for Immune Thrombocytopenia) Study | 2014-10-02 | 2014-12-19 | No |  | 78 | [12 empty] | Y | [5 empty] | Study still in set up | Neither
47014 | 926 | 1469 | 28 | 14/LO/0566 | Olaparib therapy in high risk HER2 negative BRCA mutated breast cancer | 2014-09-05 | 2014-12-03 | No |  | 89 | [6 empty] | Y | [11 empty] | Sponsor delays in contracting, sponsor set up activities at site were slow, this delayed NHS permission which was issued after the 70 day benchmark. Site was finally activated by sponsor 19/12/2014 | Sponsor