## Sheet1
ID | Trust ID | Submission ID | Meta Submission ID | Research Ethics Committee Reference Number | Name of Trial | Date of Receipt of Valid Research Application | Date of NHS Permission | First Patient Recruited? | Date of First Patient Recruited | Duration between VRA and NHS Permission | Duration between NHS Permission and First Patient | Duration between VRA and First Patient | Benchmark Met | Added By User ID | Amended By User Id | Date Added | Date Amended | A - Permissions delayed/ denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | K - Not Used | L - Not Used | M - Not Used | N - Not Used | O - Not Used | Comments | Reasons for delay correspond to:
33889 | 926 | 687 | 22 | 11/YH/0006 | MERIDIAN | 2013-03-12 | 2013-04-02 | No |  | 21 |  |  |  | Unknown | Unknown | 2013-08-07 | 2014-04-30 |  |  | Y | [12 empty] | Staff delays | Sponsor
33890 | 926 | 687 | 22 | 2013-08-07 | EnligHTN II | 2013-04-02 | 2013-04-03 | Yes | 2013-04-05 | 1 | 2 | 3 | Yes | Unknown | Unknown | 2013-08-07 | 41759 | [16 empty] | Please Select...
33891 | 926 | 687 | 22 | 12/LO/1823 | WAVES | 2013-03-11 | 2013-04-03 | Yes | 2013-05-14 | 23 | 41 | 64 | Yes | Unknown | Unknown | 2013-08-07 | 41759 | [16 empty] | Please Select...
33892 | 926 | 687 | 22 | 11/LO/1333 | MiPEP | 2013-01-08 | 2013-04-04 | Yes | 2013-07-17 | 86 | 104 | 190 | No | Unknown | Unknown | 2013-08-07 | 41759 | Y | [14 empty] | Delays with approval - Pharmacy | NHS Provider
33893 | 926 | 687 | 22 | 12/EE/0435 | Phase 2 Preference Study of Tivozanib Hydrochloride vs Sunitinib | 2013-02-12 | 2013-04-08 | No |  | 55 |  |  |  | Unknown | Unknown | 2013-08-07 | 41759 |  |  |  |  | Y | [10 empty] | Staff issues | NHS Provider
33894 | 926 | 687 | 22 | 11/WM/0287 | Desktop III | 2013-04-09 | 2013-04-10 | Yes | 2013-07-18 | 1 | 99 | 100 | No | Unknown | Unknown | 2013-08-07 | 41759 | [9 empty] | Y | [5 empty] | Delays with recruitment | NHS Provider
33895 | 926 | 687 | 22 | 13/SC/0087 | Anal sensorimotor effects of neuromodulation | 2013-01-10 | 2013-04-11 | Yes | 2013-06-17 | 91 | 67 | 158 | No | Unknown | Unknown | 2013-08-07 | 41759 | Y | [14 empty] | Delays with approval and recruitment | NHS Provider
33896 | 926 | 687 | 22 | 12/LO/1876 | GO28141 PhIII Vemurafenib Vs Vemurafenib + GDC-0973 in Melanoma | 2013-02-20 | 2013-04-15 | No |  | 54 |  |  |  | Unknown | Unknown | 2013-08-07 | 41759 | Y | [14 empty] | Delays with approval | NHS Provider
33897 | 926 | 687 | 22 | 13/EM/0095 | CAIN457F2312 | 2013-04-09 | 2013-04-16 | Yes | 2013-05-02 | 7 | 16 | 23 | Yes | Unknown | Unknown | 2013-08-07 | 41759 | [16 empty] | Please Select...
33898 | 926 | 687 | 22 | 13/LO/0033 | PEGGY - A PHASE II, RANDOMIZED STUDY OF PACLITAXEL WITH GDC-0941 VERSUS PACLITAXEL WITH PLACEBO IN PATIENTS WITH LOCALLY RECURRENT OR METASTATIC BREAST CANCER | 2013-04-02 | 2013-04-16 | No |  | 14 |  |  |  | Unknown | Unknown | 2013-08-07 | 41759 | [9 empty] | Y | [5 empty] | Delays in recruitment | NHS Provider
33899 | 926 | 687 | 22 | 12/EE/0371 | Phase III Study Comparing Betrixiban with Enoxaparin in VTE | 2013-04-12 | 2013-04-18 | Yes | 2013-06-27 | 6 | 70 | 76 | No | Unknown | Unknown | 2013-08-07 | 41759 |  |  |  |  | Y | [10 empty] | Staff shortage | NHS Provider
33900 | 926 | 687 | 22 | 12/EE/0349 | BriTROC-1 | 2013-04-10 | 2013-04-18 | Yes | 2013-08-06 | 8 | 110 | 118 | No | Unknown | Unknown | 2013-08-07 | 41759 |  |  |  |  | Y |  |  |  |  | Y | [5 empty] | Staff delays | NHS Provider
33901 | 926 | 687 | 22 | 2013-08-06 | Serum creatinine changes after critical illness and implications for diagnosis of chronic kidney | 2013-03-13 | 2013-04-19 | Yes | 2013-05-01 | 37 | 12 | 49 | Yes | Unknown | Unknown | 2013-08-07 | 41759 | [16 empty] | Please Select...
33902 | 926 | 687 | 22 | 11/LO/2026 | EBNA1 IgG predicts SPMS | 2013-04-05 | 2013-04-26 | No |  | 21 |  |  |  | Unknown | Unknown | 2013-08-07 | 41759 | [9 empty] | Y | [5 empty] | Staff delays | NHS Provider
33903 | 926 | 687 | 22 | 11/LO/1540 | GWAS | 2013-04-26 | 2013-04-26 | Yes | 2013-05-19 | 0 | 23 | 23 | Yes | Unknown | Unknown | 2013-08-07 | 41759 | [16 empty] | Please Select...
33904 | 926 | 687 | 22 | 12/NE/0367 | GSK SHIELD | 2013-04-25 | 2013-04-30 | No |  | 5 |  |  |  | Unknown | Unknown | 2013-08-07 | 41759 |  |  | Y | [12 empty] | The study has been closed by the sponsor. No patients recruited as it was closed within a few weeks of being initiated | Sponsor
33905 | 926 | 687 | 22 | 12/EE/0544 | INSPIRE | 2012-11-26 | 2013-05-01 | Yes | 2013-05-07 | 156 | 6 | 162 | No | Unknown | Unknown | 2013-08-07 | 41759 | [9 empty] | Y | [5 empty] | Delay due to ethics hold up | Sponsor
33906 | 926 | 687 | 22 | 12/LO/1653 | NEPTUNE | 2013-05-01 | 2013-05-02 | Yes | 2013-06-05 | 1 | 34 | 35 | Yes | Unknown | Unknown | 2013-08-07 | 41759 | [16 empty] | Please Select...
33907 | 926 | 687 | 22 | 13/LO/0257 | Genetic Factors Affecting the Timing of Puberty | 2013-01-22 | 2013-05-02 | Yes | 2013-06-28 | 100 | 57 | 157 | No | Unknown | Unknown | 2013-08-07 | 41759 | Y | [14 empty] | Delays with permissions | NHS Provider
33908 | 926 | 687 | 22 | 12/SC/0570 | PASSAGE | 2013-05-03 | 2013-05-03 | Yes | 2013-07-10 | 0 | 68 | 68 | Yes | Unknown | Unknown | 2013-08-07 | 41759 | [16 empty] | Please Select...
33909 | 926 | 687 | 22 | 13/SC/0092 | Siponimod BAF312 | 2013-04-22 | 2013-05-07 | Yes | 2013-09-10 | 15 | 126 | 141 | No | Unknown | Unknown | 2013-08-07 | 41759 | [9 empty] | Y | [5 empty] | due to placebo control and patients needing to stop their current MS therapy in order to be deemed eligible. | Neither
33910 | 926 | 687 | 22 | 13/LO/0472 | Ultrasound Vasculature | 2013-02-26 | 2013-05-09 | Yes | 2013-06-17 | 72 | 39 | 111 | No | Unknown | Unknown | 2013-08-07 | 41759 | Y | [14 empty] | Delays with risk assesment & ethics | NHS Provider
33911 | 926 | 687 | 22 | 12/WA/0308 | Lilly RHAP PsA study | 2013-04-29 | 2013-05-09 | Yes | 2013-06-19 | 10 | 41 | 51 | Yes | Unknown | Unknown | 2013-08-07 | 41759 | [16 empty] | Please Select...
33912 | 926 | 687 | 22 | 11/LO/1543 | Signalling networks in IBD - version 1.0 | 2013-05-08 | 2013-05-09 | Yes | 2013-05-13 | 1 | 4 | 5 | Yes | Unknown | Unknown | 2013-08-07 | 41759 | [16 empty] | Please Select...
33913 | 926 | 687 | 22 | 10/MRE09/10 | StAmP | 2013-05-08 | 2013-05-13 | Yes | 2013-06-01 | 5 | 19 | 24 | Yes | Unknown | Unknown | 2013-08-07 | 41759 | [15 empty] | Delayed Site initiation | Sponsor
33914 | 926 | 687 | 22 | 13/LO/0094 | HAPPY London | 2013-05-13 | 2013-05-15 | Yes | 2013-06-18 | 2 | 34 | 36 | Yes | Unknown | Unknown | 2013-08-07 | 41759 | [16 empty] | Please Select...
33915 | 926 | 687 | 22 | 12/WA/0250 | BI 695500 versus rituximab in patients with moderately to severely active rheumatoid arthritis: a randomized, doubleblind, parallel arm, multiple dose, active comparator trial. | 2013-05-15 | 2013-05-20 | Yes | 2013-06-27 | 5 | 38 | 43 | Yes | Unknown | Unknown | 2013-08-07 | 41759 | [16 empty] | Please Select...
33916 | 926 | 687 | 22 | ND | Multiple Myeloma Patient Pathway | 2013-05-22 | 2013-05-22 | No |  | 0 |  |  |  | Unknown | Unknown | 2013-08-07 | 41759 | [9 empty] | Y | [5 empty] | Delayed site initiation | Sponsor
33917 | 926 | 687 | 22 | 13/LO/0077 | The HALT Hepatitis Study | 2013-06-05 | 2013-06-05 | Yes | 2013-08-15 | 0 | 71 | 71 | No | Unknown | Unknown | 2013-08-07 | 41759 | [9 empty] | Y | [5 empty] | Weekly clinic moved 2 days back so missed by 1 day | NHS Provider
33918 | 926 | 687 | 22 | 13/LO/0097 | Evaluating the Safety and Efficacy of GS-6624, a Monoclonal Antibody Against Lysyl Oxidase-Like 2 (LOXL2), in Subjects with Advanced Liver Fibrosis but not Cirrhosis Secondary to | 2013-06-10 | 2013-06-10 | No |  | 0 |  |  |  | Unknown | Unknown | 2013-08-07 | 41759 | [8 empty] | Y | [7 empty] | NHS Provider
33919 | 926 | 687 | 22 | 12/LO/1378 | PBS Study | 2013-06-04 | 2013-06-11 | Yes | 2013-12-06 | 7 | 178 | 185 | No | Unknown | Unknown | 2013-08-07 | 41759 | [9 empty] | Y | [5 empty] | Delays with staff | NHS Provider
33920 | 926 | 687 | 22 | 11/SC/0282 | RADVAN | 2013-06-06 | 2013-06-11 | No |  | 5 |  |  |  | Unknown | Unknown | 2013-08-07 | 41759 | [9 empty] | Y | [5 empty] | no patients were eligible | NHS Provider
33921 | 926 | 687 | 22 | 11/L0/1904 | QBX | 2013-06-13 | 2013-06-14 | No |  | 1 |  |  |  | Unknown | Unknown | 2013-08-07 | 41759 | [9 empty] | Y | [5 empty] | Delays with Staff | NHS Provider
33922 | 926 | 687 | 22 | 13/SS/0072 | PROOF study: Patient reported outcomes of Brimonidine Tartrate 0.5% gel for treatment of severe facial erythema of rosacea | 2013-06-06 | 2013-06-14 | Yes | 2013-06-18 | 8 | 4 | 12 | Yes | Unknown | Unknown | 2013-08-07 | 41759 | [16 empty] | Please Select...
33923 | 926 | 687 | 22 | 13/EM/0244 | Technical Evaluation of the Xpert(r) HPV Assay in General Screening Population | 2013-05-31 | 2013-06-20 | Yes | 2013-08-06 | 20 | 47 | 67 | Yes | Unknown | Unknown | 2013-08-07 | 41759 | [16 empty] | Please Select...
33924 | 926 | 687 | 22 | 13/LO/0363 | Patterns of cytokine gene expression in bacteraemic patients (V1) | 2013-02-13 | 2013-06-21 | Yes | 2013-07-05 | 128 | 14 | 142 | No | Unknown | Unknown | 2013-08-07 | 41759 | Y | [14 empty] | Delays with Ethics & CI paperwork | NHS Provider
33925 | 926 | 687 | 22 | 13/SC/0073 | COSMIC-HF A dose escalation study in patients with heart failure | 2013-06-13 | 2013-06-24 | Yes | 2014-04-15 | 11 | 295 | 306 | No | Unknown | Unknown | 2013-08-07 | 41759 |  |  |  |  | Y | [11 empty] | NHS Provider
33926 | 926 | 687 | 22 | 12/LO/1973 | Lilly JADZ RA Study | 2013-05-21 | 2013-06-25 | Yes | 2013-07-11 | 35 | 16 | 51 | Yes | Unknown | Unknown | 2013-08-07 | 41759 | [16 empty] | Please Select...
33927 | 926 | 687 | 22 | 13/LO/0130 | Lilly JADW A Study | 2013-05-21 | 2013-06-25 | Yes | 2013-07-25 | 35 | 30 | 65 | Yes | Unknown | Unknown | 2013-08-07 | 41759 | [6 empty] | Y | [9 empty] | NHS Provider
33928 | 926 | 687 | 22 | 13/SC/0021 | 14V-MC-JADV | 2013-06-24 | 2013-06-27 | No |  | 3 |  |  |  | Unknown | Unknown | 2013-08-07 | 41759 | [8 empty] | Y | [7 empty] | NHS Provider
33929 | 926 | 687 | 22 | 12/YH/0318 | GS-US-312-0115 | 2013-06-18 | 2013-07-01 | Yes | 2013-12-01 | 13 | 153 | 166 | No | Unknown | Unknown | 2013-10-28 | 41759 | [7 empty] | Y | [8 empty] | NHS Provider
33930 | 926 | 687 | 22 | 13/EE/0038 | HALT IT | 2013-06-26 | 2013-07-09 | Yes | 2013-07-26 | 13 | 17 | 30 | Yes | Unknown | Unknown | 2013-10-28 | 41759 | [16 empty] | Please Select...
33931 | 926 | 687 | 22 | 12/SC/0014 | VANISH | 2013-05-22 | 2013-07-16 | Yes | 2013-08-14 | 55 | 29 | 84 | No | Unknown | Unknown | 2013-10-28 | 41759 | [5 empty] | Y | [10 empty] | NHS Provider
33932 | 926 | 687 | 22 | 13/LO/0135 | METS | 2013-07-15 | 2013-07-17 | Yes | 2013-07-17 | 2 | 0 | 2 | Yes | Unknown | Unknown | 2013-10-28 | 41759 | [16 empty] | Please Select...
33933 | 926 | 687 | 22 | 13/LO/0530 | Characterising Metastatic Penile Cancer Using Molecular Imaging - Hybrid MRI PET (MRI-PET) | 2013-07-16 | 2013-07-22 | Yes | 2013-10-19 | 6 | 89 | 95 | No | Unknown | Unknown | 2013-10-28 | 41759 |  |  |  |  | Y |  |  |  |  | Y | [5 empty] | Contractual delays in obtaining the necessary SLAs | NHS Provider
33934 | 926 | 687 | 22 | GTAC185 | BNIT PRV 301 | 2013-07-25 | 2013-07-26 | No |  | 1 |  |  |  | Unknown | Unknown | 2013-10-28 | 41759 | [16 empty] | NHS Provider
33935 | 926 | 687 | 22 | 12/WS/0300 | ODYSSEY | 2013-07-10 | 2013-07-30 | Yes | 2013-10-15 | 20 | 77 | 97 | No | Unknown | Unknown | 2013-10-28 | 41759 | [9 empty] | Y | [5 empty] | Late site initiation | Sponsor
33936 | 926 | 687 | 22 | 12/LO/1923 | Cough in TB | 2013-07-23 | 2013-08-08 | Yes | 2013-08-28 | 16 | 20 | 36 | Yes | Unknown | Unknown | 2013-10-28 | 41759 | [16 empty] | Please Select...
33937 | 926 | 687 | 22 | 12/NW/0361 | SANAD-II | 2013-08-12 | 2013-08-13 | Yes | 2013-08-27 | 1 | 14 | 15 | Yes | Unknown | Unknown | 2013-10-28 | 41759 | [16 empty] | Please Select...
33938 | 926 | 687 | 22 | 13/LO/0975 | International Ovarian Tumour Analysis (IOTA) Phase 5 | 2013-08-14 | 2013-08-14 | Yes | 2013-09-10 | 0 | 27 | 27 | Yes | Unknown | Unknown | 2013-10-28 | 41759 | [16 empty] | Please Select...
33939 | 926 | 687 | 22 | 13/LO/0528 | PIONEER | 2013-08-14 | 2013-08-14 | Yes | 2013-11-28 | 0 | 106 | 106 | No | Unknown | Unknown | 2013-10-28 | 41759 | [6 empty] | Y | [9 empty] | NHS Provider
33940 | 926 | 687 | 22 | 13/LO/0315 | BAMI | 2013-08-22 | 2013-08-22 | Yes | 2013-10-03 | 0 | 42 | 42 | Yes | Unknown | Unknown | 2013-10-28 | 41759 | [16 empty] | Please Select...
33941 | 926 | 687 | 22 | 13/LO/0322 | Predicting lung function decline in adolescents with CF | 2013-08-16 | 2013-08-22 | No |  | 6 |  |  |  | Unknown | Unknown | 2013-10-28 | 41759 | [5 empty] | Y | [10 empty] | NHS Provider
33942 | 926 | 687 | 22 | 09/H0707/88 | NEON | 2013-09-04 | 2013-09-11 | No |  | 7 |  |  |  | Unknown | Unknown | 2013-10-28 | 41759 | [9 empty] | Y | [5 empty] | only site to help with the study | NHS Provider
33943 | 926 | 687 | 22 | 13/EE/0202 | CAM-3001-1107 | 2013-09-11 | 2013-09-12 | No |  | 1 |  |  |  | Unknown | Unknown | 2013-10-28 | 41759 | [5 empty] | Y | [10 empty] | NHS Provider
33944 | 926 | 687 | 22 | 13/LO/0891 | Probiotic and assesement of gut function 12.05 NRC | 2013-09-13 | 2013-09-13 | Yes | 2014-01-06 | 0 | 115 | 115 | No | Unknown | Unknown | 2013-10-28 | 41759 | [6 empty] | Y | [9 empty] | NHS Provider
33945 | 926 | 687 | 22 | 12/LO/0918 | Early Assessment of Circulating Volume in Trauma | 2013-09-30 | 2013-09-30 | Yes | 2013-10-19 | 0 | 19 | 19 | Yes | Unknown | Unknown | 2013-10-28 | 41759 | [16 empty] | Please Select...
33946 | 926 | 687 | 22 | 13/LO/0501 | Maribavir v Valganciclovir in CMV | 2013-07-09 | 2013-07-19 | Yes | 2013-08-12 | 10 | 24 | 34 | Yes | Unknown | Unknown | 2013-10-30 | 41759 |  |  |  |  | Y | [11 empty] | Neither
33947 | 926 | 687 | 22 | 13/ES/0013 | UK use of aqueous zanamivir during the 2009 A-H1N1 influenza pandemic | 2013-07-23 | 2013-07-23 | No |  | 0 |  |  |  | Unknown | Unknown | 2013-10-30 | 41759 | [6 empty] | Y | [8 empty] | study is in conjunction with other sutyd | Neither
33948 | 926 | 687 | 22 | 12/WS/0145 | ATTAIN | 2013-07-26 | 2013-07-26 | Yes | 2013-08-05 | 0 | 10 | 10 | Yes | Unknown | Unknown | 2013-10-30 | 41759 | [16 empty] | Please Select...
33949 | 926 | 687 | 22 | 13/LO/0098 | GS-US-321-0105 | 2013-07-09 | 2013-08-06 | No |  | 28 |  |  |  | Unknown | Unknown | 2013-10-30 | 41759 | [6 empty] | Y | [9 empty] | Neither
33950 | 926 | 687 | 22 | n/a | Does image-localisation of breast tumours affect the rate of reoperation following breast-conserving | 2013-08-08 | 2013-08-08 | No |  | 0 |  |  |  | Unknown | Unknown | 2013-10-30 | 41759 |  |  |  |  | Y | [11 empty] | NHS Provider
33951 | 926 | 687 | 22 | 11/EM/0442 | ENCEPH UK/ UK CHIMES | 2013-08-09 | 2013-08-13 | Yes | 2013-10-11 | 4 | 59 | 63 | Yes | Unknown | Unknown | 2013-10-30 | 41759 | [16 empty] | Please Select...
33952 | 926 | 687 | 22 | 09/H0718/45 | SASS Study | 2013-08-14 | 2013-08-14 | No |  | 0 |  |  |  | Unknown | Unknown | 2013-10-30 | 41759 | [6 empty] | Y | [9 empty] | NHS Provider
33953 | 926 | 687 | 22 | 13/LO/0560 | Symbicort Turbohaler | 2013-08-15 | 2013-08-21 | Yes | 2013-12-28 | 6 | 129 | 135 | No | Unknown | Unknown | 2013-10-30 | 41759 | [7 empty] | Y | [8 empty] | Neither
33954 | 926 | 687 | 22 | 13/LO/0284 | Enhancing the detection of MRD in patients with B-cell malignancies | 2013-08-29 | 2013-08-29 | Yes | 2013-10-23 | 0 | 55 | 55 | Yes | Unknown | Unknown | 2013-10-30 | 41759 | [16 empty] | Please Select...
33955 | 926 | 687 | 22 | 13/LO/0215 | Screening for Viral Hepatitis in migrants in East London | 2013-09-20 | 2013-09-24 | No |  | 4 |  |  |  | Unknown | Unknown | 2013-10-30 | 41759 | [7 empty] | Y | [8 empty] | NHS Provider
33956 | 926 | 687 | 22 | 13/LO/0807 | JNJ-38518168 | 2013-09-24 | 2013-10-03 | Yes | 2014-01-01 | 9 | 90 | 99 | No | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [6 empty] | Y | [9 empty] | NHS Provider
33957 | 926 | 687 | 22 | 13/LO/0855 | A Phase 3, Randomized, Double-Blind, Placebo-Controlled Study Evaluating the Efficacy and Safety of Idelalisib (GS-1101) in Combination with Rituximab for Previously Treated Indolent Non-Hodgkin Lymphomas | 2013-08-02 | 2013-10-07 | Yes | 2014-04-01 | 66 | 176 | 242 | No | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [6 empty] | Y | [9 empty] | NHS Provider
33958 | 926 | 687 | 22 | 12/NE/0228 | TiLTs-CC | 2013-10-10 | 2013-10-11 | No |  | 1 |  |  |  | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [9 empty] | Y | [5 empty] | None – the project was at risk as CCG North were deliberating whether patients should receive funding for this procedure. The principal investigator – Prof Knowles in collaboration with the Chief investigator decided to postpone recruitment and enrollment until a decision was taken by CCG North (impacted on continuation of this protocol). | Sponsor
33959 | 926 | 687 | 22 | 13/WM/0365 | CAIN457F2306E1 | 2013-10-11 | 2013-10-11 | Yes | 2013-10-16 | 0 | 5 | 5 | Yes | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [16 empty] | Please Select...
33960 | 926 | 687 | 22 | 13/SC/0279 | GS-US-292-0109 | 2013-07-31 | 2013-10-14 | Yes | 2013-10-15 | 75 | 1 | 76 | No | CTP Submission Platform | Unknown | 2014-01-28 | 41759 |  |  |  |  | Y | [11 empty] | NHS Provider
33961 | 926 | 687 | 22 | 13/EM/0230 | A Phase II Randomized, DoubleBlind, PlaceboControlled, Multicenter Study of VS 6063 in Subjects with Malignant Pleural Mesothelioma | 2013-07-26 | 2013-10-15 | No |  | 81 |  |  |  | CTP Submission Platform | Unknown | 2014-01-28 | 41759 |  |  |  |  | Y | [11 empty] | NHS Provider
33962 | 926 | 687 | 22 | 13/EE/0276 | GS-US-334-0153 | 2013-10-01 | 2013-10-17 | Yes | 2013-10-21 | 16 | 4 | 20 | Yes | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [16 empty] | Please Select...
33963 | 926 | 687 | 22 | 005-02-13 | STEP hep | 2013-10-22 | 2013-10-23 | No |  | 1 |  |  |  | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [6 empty] | Y | [9 empty] | Neither
33964 | 926 | 687 | 22 | 12/YH/0446 | JNJ 207047 | 2013-10-21 | 2013-10-25 | Yes | 2014-01-02 | 4 | 69 | 73 | No | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [9 empty] | Y | [5 empty] | Christmas break | Neither
33965 | 926 | 687 | 22 | 13/YH/0118 | CQVA149A2318 | 2013-10-15 | 2013-10-30 | Yes | 2014-02-12 | 15 | 105 | 120 | No | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [6 empty] | Y | [9 empty] | NHS Provider
33966 | 926 | 687 | 22 | 13/LO/0784 | FDS-NBU-1034 - Elderly Volunteers Study | 2013-10-24 | 2013-10-30 | Yes | 2013-11-21 | 6 | 22 | 28 | Yes | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [16 empty] | Please Select...
33967 | 926 | 687 | 22 | 13/LO/0671 | 205MS303 | 2013-10-31 | 2013-10-31 | Yes | 2013-11-28 | 0 | 28 | 28 | Yes | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [16 empty] | Please Select...
33968 | 926 | 687 | 22 | 12/SC/0259 | GS-US-313-0125 | 2013-07-26 | 2013-10-31 | Yes | 2013-12-02 | 97 | 32 | 129 | No | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [6 empty] | Y | [9 empty] | Neither
33969 | 926 | 687 | 22 | 13/EM/0357 | CAIN457F2305 | 2013-10-30 | 2013-11-01 | Yes | 2013-11-19 | 2 | 18 | 20 | Yes | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [16 empty] | Please Select...
33970 | 926 | 687 | 22 | 13/LO/1097 | M13-102 | 2013-10-31 | 2013-11-05 | Yes | 2013-11-28 | 5 | 23 | 28 | Yes | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [16 empty] | Please Select...
33971 | 926 | 687 | 22 | 13/EM/1302 | A Phase IIIb randomised, openlabel study of the safety and efficacy of dolutegravir/abacavir/lamivudine once daily compared to atazanavir and ritonavir plus tenofovir/emtricitabine once daily in HIV1 infected antiretroviral therapy naive women. | 2013-11-01 | 2013-11-06 | Yes | 2014-02-11 | 5 | 97 | 102 | No | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [6 empty] | Y | [9 empty] | NHS Provider
33972 | 926 | 687 | 22 | 11/H1307/6 | SWITCH | 2013-11-11 | 2013-11-11 | No |  | 0 |  |  |  | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [6 empty] | Y | [9 empty] | NHS Provider
33974 | 926 | 687 | 22 | 12/EM/0003 | Induction of labour versus expectant management for nulliparous women over 35 years of age (35/39) | 2013-11-04 | 2013-11-12 | Yes | 2013-11-27 | 8 | 15 | 23 | Yes | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [16 empty] | Please Select...
33976 | 926 | 687 | 22 | 13/EE/0201 | COT1-13-01 Illiotibial Band in OA | 2013-11-14 | 2013-11-18 | Yes | 2014-01-09 | 4 | 52 | 56 | Yes | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [16 empty] | Please Select...
33977 | 926 | 687 | 22 | 13/SC/0463 | CDEB025A2222 | 2013-11-05 | 2013-11-21 | Yes | 2013-12-19 | 16 | 28 | 44 | Yes | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [16 empty] | Please Select...
33978 | 926 | 687 | 22 | 13/WS/0211 | TMC435HPC3014 | 2013-11-22 | 2013-11-25 | Yes | 2013-11-28 | 3 | 3 | 6 | Yes | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [16 empty] | Please Select...
33979 | 926 | 687 | 22 | 13/NW/0464 | A Placebo-Controlled, Multicenter, Double-Blind, Randomized, Pharmacokinetic and Pharmacodynamic Trial of IDN-6556 in Subjects with Acute-on-Chronic Liver Failure | 2013-11-18 | 2013-11-26 | No |  | 8 |  |  |  | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [6 empty] | Y | [9 empty] | NHS Provider
33980 | 926 | 687 | 22 | 13/EE/0241 | SIGNATURE | 2013-11-27 | 2013-11-28 | Yes | 2013-12-10 | 1 | 12 | 13 | Yes | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [16 empty] | Please Select...
33981 | 926 | 687 | 22 | 13/LO/1019 | 215MS201 | 2013-11-20 | 2013-11-28 | No |  | 8 |  |  |  | CTP Submission Platform | Unknown | 2014-01-28 | 41759 |  |  |  |  | Y | [11 empty] | NHS Provider
33982 | 926 | 687 | 22 | 13/LO/0936 | SUKCES | 2013-11-19 | 2013-11-29 | Yes | 2014-01-27 | 10 | 59 | 69 | Yes | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [16 empty] | Please Select...
33983 | 926 | 687 | 22 | 13/NW/0598 | RADICAL | 2013-11-20 | 2013-11-29 | Yes | 2013-12-03 | 9 | 4 | 13 | Yes | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [16 empty] | Please Select...
33984 | 926 | 687 | 22 | 12/YH/0475 | GP28331 - A PHASE Ib study - CHRONIC LYMPHOCYTIC LEUKAEMIA | 2013-12-06 | 2013-12-06 | No |  | 0 |  |  |  | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [6 empty] | Y | [8 empty] | No eligible patient | NHS Provider
33985 | 926 | 687 | 22 | 13/LO/1512 | RCT comparing twin block wear for varying durations | 2013-12-06 | 2013-12-06 | Yes | 2013-12-09 | 0 | 3 | 3 | Yes | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [16 empty] | Please Select...
33987 | 926 | 687 | 22 | 13/NW/0692 | CARMELINA | 2013-11-22 | 2013-12-12 | Yes | 2013-12-19 | 20 | 7 | 27 | Yes | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [16 empty] | Please Select...
33988 | 926 | 687 | 22 | 13/LO/1022 | 308: Phase 3 study of XL184 vs Everolimus in subjects with RCC | 2013-09-13 | 2013-12-12 | Yes | 2014-01-14 | 90 | 33 | 123 | No | CTP Submission Platform | Unknown | 2014-01-28 | 41759 |  |  |  |  | Y | [11 empty] | NHS Provider
33989 | 926 | 687 | 22 | 13/EM/0353 | Working after Brain Injury Final Version 1.0 | 2013-12-13 | 2013-12-13 | Yes | 2014-01-07 | 0 | 25 | 25 | Yes | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [16 empty] | Please Select...
33990 | 926 | 687 | 22 | 13/NE/0125 | PRESTO | 2013-12-15 | 2013-12-18 | Yes | 2014-02-26 | 3 | 70 | 73 | No | CTP Submission Platform | Unknown | 2014-01-28 | 41759 | [6 empty] | Y | [8 empty] | No eligible patient | NHS Provider
34327 | 926 | 687 | 22 | 12/LO/1950 | C25003 in NHL | 2013-04-19 | 2013-05-22 | No |  | 33 |  |  |  | Unknown | Unknown | 2014-04-30 | 41759 | [6 empty] | Y | [9 empty] | NHS Provider
34328 | 926 | 687 | 22 | 13/LO/0128 | Liily JADX RA study | 2013-05-21 | 2013-06-25 | No |  | 35 |  |  |  | Unknown | Unknown | 2014-04-30 | 41759 | [6 empty] | Y | [9 empty] | NHS Provider
34329 | 926 | 687 | 22 | 12/EE/0171 | A 2 Year mechanistic study of Belimumab in Idiopathic Membranous Glomerulonephropathy | 2013-06-27 | 2013-07-01 | Yes | 2013-09-09 | 4 | 70 | 74 | No | Unknown | Unknown | 2014-04-30 | 41759 | [6 empty] | Y | [9 empty] | NHS Provider
34330 | 926 | 687 | 22 | 13/LO/0572 | GSUS 292 0104 | 2013-07-10 | 2013-07-25 | Yes | 2013-07-25 | 15 | 0 | 15 | Yes | Unknown | Unknown | 2014-04-30 | 41759 | [16 empty] | Please Select...
34331 | 926 | 687 | 22 | 13/LO/0574 | GSUS2920111 | 2013-07-16 | 2013-07-26 | Yes | 2013-08-15 | 10 | 20 | 30 | Yes | Unknown | Unknown | 2014-04-30 | 41759 | [16 empty] | Please Select...
34332 | 926 | 687 | 22 | 12/NW/0802 | LAQ-MS-305 (CONCERTO) | 2013-05-14 | 2013-07-05 | Yes | 2013-12-19 | 52 | 167 | 219 | No | Unknown | Unknown | 2014-04-30 | 41759 | [9 empty] | Y | [5 empty] | Late site activation | Sponsor
34333 | 926 | 687 | 22 | 13/LO/002 | GS-US-312-0119 | 2013-07-24 | 2013-08-05 | No |  | 12 |  |  |  | Unknown | Unknown | 2014-04-30 | 41759 |  |  |  |  | Y | [11 empty] | NHS Provider
34334 | 926 | 687 | 22 | 13/LO/0736 | EGALITY GP2015 in Plaque Psoriasis | 2013-08-08 | 2013-08-08 | Yes | 2013-10-24 | 0 | 77 | 77 | No | Unknown | Unknown | 2014-04-30 | 41759 |  |  |  |  | Y | [11 empty] | NHS Provider
34335 | 926 | 687 | 22 | 12/WM/0341 | AMG145 Fourier in CVD | 2013-09-05 | 2013-09-05 | Yes | 2013-10-17 | 0 | 42 | 42 | Yes | Unknown | Unknown | 2014-04-30 | 41759 | [16 empty] | Please Select...
34336 | 926 | 687 | 22 | 13/EE/0201 | CAM-3001-1107 | 2013-09-11 | 2013-09-12 | Yes | 2014-03-10 | 1 | 179 | 180 | No | Unknown | Unknown | 2014-04-30 | 41759 | [6 empty] | Y | [9 empty] | NHS Provider
34337 | 926 | 687 | 22 | 13/LO/0499 | ASCERTAIN | 2013-07-30 | 2013-08-05 | Yes | 2014-01-10 | 6 | 158 | 164 | No | Unknown | Unknown | 2014-04-30 | 41759 | [6 empty] | Y | [9 empty] | NHS Provider
34338 | 926 | 687 | 22 | 13/LO/0665 | CAIN457A2312 | 2013-08-16 | 2013-09-17 | Yes | 2013-11-04 | 32 | 48 | 80 | No | Unknown | Unknown | 2014-04-30 | 41759 | [6 empty] | Y | [9 empty] | NHS Provider
34339 | 926 | 687 | 22 | 13/LO/0666 | CAIN457A2313 | 2013-09-16 | 2013-09-18 | Yes | 2013-11-28 | 2 | 71 | 73 | No | Unknown | Unknown | 2014-04-30 | 41759 | [6 empty] | Y | [9 empty] | NHS Provider
34340 | 926 | 687 | 22 | 13/LO/0983 | GO28625 FIR | 2013-09-25 | 2013-09-30 | Yes | 2013-12-02 | 5 | 63 | 68 | Yes | Unknown | Unknown | 2014-04-30 | 41759 | [16 empty] | Please Select...
34341 | 926 | 687 | 22 | 12/L0/1759 | OuTSMART | 2014-01-13 | 2014-01-24 | Yes | 2014-03-24 | 11 | 59 | 70 | Yes | Unknown | Unknown | 2014-04-30 | 41759 | [16 empty] | Please Select...
34342 | 926 | 687 | 22 | 12/LO/1319 | A Phase 2 study for older adults with Acute Lymphoblastic Leukaemia | 2013-12-03 | 2014-01-27 | No |  | 55 |  |  |  | Unknown | Unknown | 2014-04-30 | 41759 |  |  |  |  | Y | [11 empty] | NHS Provider
34343 | 926 | 687 | 22 | 11/H07228/8 | Rapid Identification via Interferon Gamma test for Active Tuberculosis | 2014-03-03 | 2014-03-13 | No |  | 10 |  |  |  | Unknown | Unknown | 2014-04-30 | 41759 | [16 empty] | Please Select...
34344 | 926 | 687 | 22 | 13/EM/0349 | MANTA | 2014-01-08 | 2014-01-08 | Yes | 2014-04-08 | 0 | 90 | 90 | No | Unknown | Unknown | 2014-04-30 | 41759 | [5 empty] | Y | [10 empty] | NHS Provider
34345 | 926 | 687 | 22 | 13/LO/1097 | LCZ696A2224 | 2014-01-20 | 2014-01-20 | No |  | 0 |  |  |  | Unknown | Unknown | 2014-04-30 | 41759 | [16 empty] | Please Select...
34346 | 926 | 687 | 22 | 13/SC/0558 | CAIN457A3301 | 2014-01-14 | 2014-01-21 | No |  | 7 |  |  |  | Unknown | Unknown | 2014-04-30 | 41759 | [6 empty] | Y | [9 empty] | NHS Provider
34347 | 926 | 687 | 22 | 13/SC/0486 | NOVAP | 2014-01-27 | 2014-01-27 | No |  | 0 |  |  |  | Unknown | Unknown | 2014-04-30 | 41759 | [6 empty] | Y | [9 empty] | NHS Provider
34348 | 926 | 687 | 22 | 04/MRE07/35 | STAMPEDE | 2014-01-09 | 2014-01-28 | No |  | 19 |  |  |  | Unknown | Unknown | 2014-04-30 | 41759 | [6 empty] | Y | [9 empty] | NHS Provider
34349 | 926 | 687 | 22 | 13/LO/1199 | JADY Extension | 2014-01-15 | 2014-01-29 | Yes | 2014-02-24 | 14 | 26 | 40 | Yes | Unknown | Unknown | 2014-04-30 | 41759 | [16 empty] | Please Select...
34350 | 926 | 687 | 22 | 08/H1102/112 | TARDIS | 2014-01-31 | 2014-01-31 | Yes | 2014-03-19 | 0 | 47 | 47 | Yes | Unknown | Unknown | 2014-04-30 | 41759 | [16 empty] | Please Select...
34351 | 926 | 687 | 22 | 13/LO/1115 | PIVOTAL | 2014-02-07 | 2014-02-14 | No |  | 7 |  |  |  | Unknown | Unknown | 2014-04-30 | 41759 | [16 empty] | Please Select...
34499 | 926 | 687 | 22 | 13/LO/0669 | MINIMISE STEMI trial version 1 | 2014-02-24 | 2014-03-20 | Yes | 2014-04-22 | 24 | 33 | 57 | Yes | Unknown | Unknown | 2014-04-30 | 41759 | [16 empty] | Please Select...
34500 | 926 | 687 | 22 | 13/LO/0576 | Evaluating an automated diabetic retinopathy screening tool | 2013-11-25 | 2014-01-22 | Yes | 2014-01-30 | 58 | 8 | 66 | Yes | Unknown | Unknown | 2014-04-30 | 41759 | [16 empty] | Please Select...
34501 | 926 | 687 | 22 | 10/H0302/51 | TB-REACH | 2014-01-13 | 2014-01-16 | No |  | 3 |  |  |  | Unknown | Unknown | 2014-04-30 | 41759 | [6 empty] | Y | [9 empty] | NHS Provider
34502 | 926 | 687 | 22 | 12/EM/0095 | TOTAL | 2014-01-29 | 2014-01-29 | Yes | 2014-03-17 | 0 | 47 | 47 | Yes | Unknown | Unknown | 2014-04-30 | 41759 | [16 empty] | Please Select...
34503 | 926 | 687 | 22 | 13/SW/0186 | EFFECT Efficacy of Fluticasone/Formoterol in COPD Treatment FLT3509 | 2014-01-08 | 2014-01-13 | No |  | 5 |  |  |  | Unknown | Unknown | 2014-04-30 | 41759 | Y | [15 empty] | NHS Provider
34504 | 926 | 687 | 22 | 12/NW/0509 | RELIEF | 2014-03-12 | 2014-03-13 | Yes | 2014-03-28 | 1 | 15 | 16 | Yes | Unknown | Unknown | 2014-04-30 | 41759 | [16 empty] | Please Select...
34505 | 926 | 687 | 22 | 13/LO/1284 | ROX Registry | 2014-01-08 | 2014-01-31 | No |  | 23 |  |  |  | Unknown | Unknown | 2014-04-30 | 41759 | [9 empty] | Y | [5 empty] | holding off recruitment until we get approval for an investigator-lead sub study which is being submitted to the REC presently. | NHS Provider
34506 | 926 | 687 | 22 | 13/LO/1881 | OPUS 1 (Biocryst) | 2014-02-04 | 2014-02-20 | Yes | 2014-02-24 | 16 | 4 | 20 | Yes | Unknown | Unknown | 2014-04-30 | 41759 | [16 empty] | Please Select...
34507 | 926 | 687 | 22 | 13/LO/1766 | EMR 100070-001: MSB0010718C in subjects with solid tumours | 2014-01-20 | 2014-02-18 | No |  | 29 |  |  |  | Unknown | Unknown | 2014-04-30 | 41759 | [16 empty] | Please Select...
34508 | 926 | 687 | 22 | 13/LO/1513 | CC-5013-NHL-007 Indolent lymphoma: Augment trial | 2013-12-20 | 2014-02-10 | No |  | 52 |  |  |  | Unknown | Unknown | 2014-04-30 | 41759 | Y | [15 empty] | NHS Provider
34509 | 926 | 687 | 22 | 13/YH/0174 | Adalimumab in Non-Radiographic Axial Spondyloarthritis | 2014-03-18 | 2014-03-18 | No |  | 0 |  |  |  | Unknown | Unknown | 2014-04-30 | 41759 | [16 empty] | Please Select...
34510 | 926 | 687 | 22 | 13/NW/0791 | GSK1278863 in CKD | 2014-03-20 | 2014-03-20 | No |  | 0 |  |  |  | Unknown | Unknown | 2014-04-30 | 41759 | [16 empty] | Please Select...
34511 | 926 | 687 | 22 | 13/NI/0148 | WB28182 | 2013-11-27 | 2014-02-11 | No |  | 76 |  |  |  | Unknown | Unknown | 2014-04-30 | 41759 | Y | [15 empty] | NHS Provider
34513 | 926 | 687 | 22 | 13/LO/1490 | GS-US-320-0110 | 2014-02-12 | 2014-03-25 | No |  | 41 |  |  |  | Unknown | Unknown | 2014-04-30 | 41759 | [16 empty] | Please Select...
34514 | 926 | 687 | 22 | 13/NE/0260 | OPTI-MIND 2 Protocol 07-12 | 2014-02-18 | 2014-02-20 | No |  | 2 |  |  |  | Unknown | Unknown | 2014-04-30 | 41759 | [16 empty] | Please Select...
34515 | 926 | 687 | 22 | 13/LO/1752 | Atopic Dermatitis CIM003JG | 2014-02-18 | 2014-02-24 | No |  | 6 |  |  |  | Unknown | Unknown | 2014-04-30 | 41759 | [16 empty] | Please Select...