## Sheet1
ID | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Date Site Ready To Start | A - Permissions delayed/ denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | Reasons for delay correspond to:
125273 | 17/LO/1451 | 229939 | Sotagliflozin vs. Placebo added to insulin +/- other OADs in T2DM | No |  | 55 |  |  | 2017-09-01 | 2017-12-13 | 2018-01-24 | 2018-01-29 | 2018-02-06 | 2018-03-05 | Y |  | Y | Y | Y | Y |  |  |  |  | Both
125274 | 17/LO/0925 | 223376 | M15-554- Comparing ABT-494 to Placebo in PsA subjects | Yes | 2018-05-03 | 18 | 94 | 112 | 2017-08-18 | 2018-01-11 | 2018-01-08 | 2018-01-23 | 2018-01-29 | 2018-02-15 |  | Y |  |  |  | Y |  |  |  |  | Sponsor
125275 | 17/LO/0926 | 222889 | Phase 3 PsA study subjects with inadeqate response to | Yes | 2018-02-19 | 18 | 21 | 39 | 2017-09-07 | 2018-01-11 | 2018-01-08 | 2018-01-29 | 2018-01-29 | 2018-02-15 | [10 empty] | NA
125276 | 17/EE/0038 | 217456 | RATRPstudy | No |  | 58 |  |  | 2017-02-09 | 2017-10-04 | 2017-04-13 | 2017-11-21 | 2017-12-01 | 2017-12-06 |  |  | Y | Y | Y | Y |  |  |  |  | Both
125277 | 16/EE/0370 | 198596 | MesoTRAP feasibility study | Yes | 2018-05-23 | 25 | 204 | 229 | 2017-07-31 | 2017-10-06 | 2017-01-11 | 2017-08-21 | 2017-10-31 | 2017-11-22 | [5 empty] | Y |  |  |  |  | Neither
125278 | 17/LO/1695 | 234684 | BMN 270-301: Gene Therapy Study in Severe Haemophilia A Patients | Yes | 2017-12-19 | 55 | 15 | 70 | 2017-10-10 | 2017-10-10 | 2017-11-24 | 2017-11-21 | 2017-12-04 | 2017-11-29 | [10 empty] | NA
125279 | 17/EE/0204 | 207238 | BCX7353 as a treatment for acute HAE attacks | Yes | 2018-01-02 | 49 | 34 | 83 | 2017-10-11 | 2017-10-11 | 2017-07-19 | 2017-11-09 | 2017-11-29 | 2017-12-05 |  |  |  | Y |  |  |  | Y |  |  | Sponsor
125280 | 16/LO/1024 | 195085 | BEAT LUPUS | No |  | 50 |  |  | 2016-11-28 | 2017-10-11 | 2016-09-20 | 2017-11-28 | 2017-11-30 | 2018-03-14 |  |  |  | Y |  | Y |  | Y |  |  | Sponsor
125281 | 17/LO/1101 | 227790 | CONVERGE | Yes | 2018-03-29 | 90 | 77 | 167 | 2017-10-13 | 2017-10-13 | 2017-08-30 | 2018-01-03 | 2018-01-11 | 2018-01-22 |  |  |  | Y |  |  |  | Y |  |  | Sponsor
125282 | 17/EE/0264 | 228153 | POSEIDON | Yes | 2017-11-07 | 0 | 25 | 25 | 2017-06-05 | 2017-10-13 | 2017-09-12 | 2017-10-13 | 2017-10-13 | 2017-10-13 | [10 empty] | NA
125283 | 17/LO/0960 | 223431 | Phase 1b/2a Study of ABI-H0731 in Patients With Chronic Hepatitis B | Yes | 2018-01-05 | 45 | 35 | 80 | 2017-07-07 | 2017-10-17 | 2017-09-20 | 2017-11-15 | 2017-12-01 | 2017-12-21 | [5 empty] | Y |  | Y |  |  | Both
125284 | 17/YH/0228 | 222492 | CALM II | No |  | 26 |  |  | 2017-09-15 | 2018-03-02 | 2017-10-05 | 2018-03-28 | 2018-03-28 | 2018-03-29 |  | Y |  | Y |  | Y |  |  |  |  | Sponsor
125285 | 16/LO/0831 | 196728 | CAP-IT | Yes | 2018-04-26 | 22 | 154 | 176 | 2017-09-22 | 2017-11-01 | 2016-11-11 | 2017-10-20 | 2017-11-23 | 2018-01-09 |  |  |  | Y |  | Y |  |  |  |  | Sponsor
125286 | 17/LO/1127 | 227441 | A Study of Dinutuximab and Irinotecan for Small Cell Lung Cancer | Yes | 2018-01-22 | 43 | 38 | 81 | 2017-08-31 | 2017-11-02 | 2017-08-31 | 2017-11-29 | 2017-12-15 | 2018-01-10 |  |  |  | Y | Y |  |  | Y |  |  | Both
125287 | 17/LO/1682 | 234268 | Roche Ph1 btripleneg BC | Yes | 2018-01-18 | 40 | 37 | 77 | 2017-11-01 | 2017-11-02 | 2017-11-20 | 2017-12-04 | 2017-12-12 | 2018-01-17 | Y |  |  | Y | [6 empty] | Sponsor
125288 | 17/LO/1758 | 230866 | ECLIPSE: Preoperative immunotherapy combinations in breast cancer | Yes | 2018-01-30 | 34 | 40 | 74 | 2017-10-13 | 2017-11-17 | 2017-11-21 | 2017-12-21 | 2017-12-21 | 2018-01-29 | Y |  |  | Y | [6 empty] | Sponsor
125289 | 16/SC/0324 | 197990 | StatinWISE | Yes | 2018-02-15 | 22 | 62 | 84 | 2017-10-05 | 2017-11-23 | 2016-09-28 | 2017-12-12 | 2017-12-15 | 2018-01-04 | [5 empty] | Y |  |  |  |  | Neither
125290 | 17/LO/1802 | 199038 | EQUIPTT | Yes | 2018-03-27 | 20 | 98 | 118 | 2017-11-29 | 2017-11-29 | 2017-11-23 | 2017-12-19 | 2017-12-19 | 2018-02-12 |  |  |  | Y | [6 empty] | Sponsor
125291 | 17/NW/0662 | 220156 | APPRAISE ATP | Yes | 2018-07-16 | 61 | 55 | 116 | 2017-12-01 | 2018-03-22 | 2018-03-22 | 2018-05-14 | 2018-05-22 | 2018-06-06 | Y |  |  | Y |  |  |  | Y |  |  | Sponsor
125292 | 17/NE/0377 | 233847 | A Phase 3b Study to Reduce the Incidence of Pre-dialysis Hyperkalaemia | Yes | 2018-05-21 | 32 | 31 | 63 | 2017-12-20 | 2018-03-19 | 2018-02-19 | 2018-04-12 | 2018-04-20 | 2018-04-24 | [10 empty] | NA
125293 | 18/NW/0075 | 229477 | Study of the safety & effectiveness of JNJ-56136379 in hepatitis B | Yes | 2018-06-07 | 92 | 13 | 105 | 2018-01-26 | 2018-02-22 | 2018-03-06 | 2018-05-16 | 2018-05-25 | 2018-06-01 |  |  |  | Y |  |  |  | Y |  |  | Sponsor
125294 | 17/SC/0650 | 235509 | SHP647 as induction therapy in moderate to severe Ulcerative Colitis | Yes | 2018-09-11 | 147 | 40 | 187 | 2018-01-10 | 2018-03-08 | 2018-03-07 | 2018-07-17 | 2018-08-02 | 2018-08-06 | [5 empty] | Y |  | Y |  |  | Sponsor
125295 | 17/LO/0948 | 222446 | FABULAS | Yes | 2018-02-21 | 31 | 20 | 51 | 2017-05-25 | 2018-01-01 | 2017-11-01 | 2018-02-01 | 2018-02-01 | 2018-02-12 | [10 empty] | NA
125296 | 17/LO/0334 | 214459 | FLO-ELA | Yes | 2018-03-31 | 35 | 52 | 87 | 2018-01-03 | 2018-01-03 | 2017-03-29 | 2018-01-25 | 2018-02-07 | 2018-03-14 |  |  |  | Y | [6 empty] | Sponsor
125297 | 17/SC/0216 | 223931 | ACE-LY-110 | Yes | 2018-03-21 | 16 | 56 | 72 | 2017-05-16 | 2018-01-08 | 2017-06-30 | 2017-09-11 | 2018-01-24 | 2018-03-19 | [10 empty] | NA
125298 | 17/WM/0299 | 209719 | T2NOW | Yes | 2018-03-16 | 45 | 21 | 66 | 2017-09-15 | 2018-01-09 | 2017-11-20 | 2018-02-26 | 2018-02-23 | 2018-03-06 | [10 empty] | NA
125299 | 17/NW/0511 | 226627 | ITI rFVIIIFc study in HaemophiliaA Pts who failed previous ITI therapy | No |  | 115 |  |  | 2018-01-09 | 2018-01-09 | 2017-11-06 | 2018-03-05 | 2018-05-04 | 2018-05-03 | [6 empty] | Y | Y |  |  | Both
125300 | 17/LO/1725 | 179050 | Pacemaker therapy for drug-refractory symptoms in mid-cavity HCM | Yes | 2018-02-13 | 8 | 35 | 43 | 2018-01-01 | 2018-01-01 | 2017-12-20 | 2018-01-09 | 2018-01-09 | 2018-02-08 | [10 empty] | NA
125301 | 17/NE/0061 | 215780 | CONVINCE - Protocol Version 2.1 29th November 2016 | No |  | 196 |  |  | 2017-12-22 | 2018-01-18 | 2017-07-25 | 2018-04-30 | 2018-08-02 | 2018-08-08 |  |  |  |  | Y | Y |  | Y |  |  | Both
125302 | 16/LO/1244 | 200385 | CANC 5642 | No |  | 141 |  |  | 2016-07-21 | 2018-02-01 | 2016-10-20 | 2017-02-22 | 2018-06-22 |  |  |  |  | Y | Y | [5 empty] | Both
125303 | 18/LO/0045 | 233362 | Study to test safety/efficacy of CIT treatment in NSCLC patients | Yes | 2018-08-07 | 160 | 28 | 188 | 2018-01-30 | 2018-01-31 | 2018-02-07 | 2018-06-26 | 2018-07-10 | 2018-07-27 |  | Y | [8 empty] | Sponsor
125304 | 17/EE/0040 | 222216 | ENCIRCLE Emergency Cerclage in Twins at Imminent Risk of preterm birth | No |  | 28 |  |  | 2018-02-08 | 2018-02-08 | 2017-03-02 | 2018-03-08 | 2018-03-08 | 2018-04-09 | [5 empty] | Y |  |  |  |  | Neither
125305 | 16/NW/0629 | 211995 | CF START | No |  | 102 |  |  | 2018-02-09 | 2018-02-09 | 2016-09-22 | 2018-05-10 | 2018-05-22 | 2018-06-19 |  |  |  |  | Y | Y | Y |  |  |  | NHS Provider
125306 | 17/SC/0526 | 227616 | CA209-9ER: Advanced or Metastatic Renal Cell Carcinoma | Yes | 2018-07-23 | 155 | 3 | 158 | 2018-02-15 | 2018-02-15 | 2017-11-20 | 2018-07-18 | 2018-07-20 | 2018-07-23 | [7 empty] | Y |  |  | Both
125307 | 17/EM/0032 | 209811 | Reclassifying constipation using MRI and high resolution manometry | No |  | 135 |  |  | 2018-02-13 | 2018-02-19 | 2017-03-02 | 2018-06-26 | 2018-07-04 | 2018-07-04 |  |  |  |  | Y | [5 empty] | NHS Provider
125308 | 17/SC/0638 | 236603 | BCX7353 long term safety study | Yes | 2018-04-25 | 37 | 28 | 65 | 2018-01-10 | 2018-02-19 | 2018-01-25 | 2018-03-20 | 2018-03-28 | 2018-03-30 | [10 empty] | NA
125309 | 17/LO/2064 | 232321 | Phase 2 study of BGB-3111 and Obinutuzumab in Follicular Lymphoma | No |  |  |  |  | 2018-01-30: 2018-01-17; 2018-01-31: 2018-08-10; 2018-02-07: 2018-06-12 |  |  |  | Y | [6 empty] | Sponsor
125310 | 17/EE/0382 | 220851 | PROFILE - personalised medicine in Crohn's disease | Yes | 2018-05-24 | 9 | 84 | 93 | 2018-01-08 | 2018-02-20 | 2017-11-02 | 2018-02-21 | 2018-03-01 | 2018-03-20 |  |  |  |  | Y | [5 empty] | NHS Provider
125311 | 17/EE/0480 | 235288 | Phase 3 Study of Pembro with/without Epacadostat in 1L Urothelial Carc | No |  |  |  |  | 2018-01-30: 2017-11-28; 2018-01-31: 2018-02-21; 2018-02-07: 2018-02-05 |  |  | Y | [7 empty] | Sponsor
125312 | 18/NE/0008 | 223912 | PRESTO (Treatment of stable thoracolumbar fractures: feasibility) | Yes | 2018-06-08 | 55 | 52 | 107 | 2017-11-03 | 2018-02-21 | 2018-03-20 | 2018-04-13 | 2018-04-17 | 2018-04-18 |  |  |  | Y |  | Y |  | Y |  |  | Sponsor
125314 | 17/SC/0023 | 220276 | The HarbOR study | No |  | 97 |  |  | 2018-03-02 | 2018-03-02 | 2017-02-08 | 2018-05-30 | 2018-06-07 | 2018-06-12 | [5 empty] | Y |  | Y |  |  | Sponsor
125315 | 17/YH/0436 | 234886 | BP40234: RO6874281 in combination with atezolizumab in solid tumours | Yes | 2018-06-26 | 32 | 28 | 60 | 2018-02-15 | 2018-04-27 | 2018-02-27 | 2018-05-17 | 2018-05-29 | 2018-06-05 | [10 empty] | NA
125316 | 17/SW/0010 | 197027 | Novel use of TXA to reduce the need for nasal packing in epistaxis | No |  | 46 |  |  | 2018-03-08 | 2018-03-08 | 2017-03-14 | 2018-04-13 | 2018-04-23 | 2018-05-24 |  |  |  |  | Y | Y |  |  |  |  | NHS Provider
125317 | 17/LO/1715 | 226230 | PHERGain | No |  | 159 |  |  | 2018-03-08 | 2018-03-08 | 2018-06-05 | 2018-08-13 | 2018-08-14 | 2018-08-21 | [5 empty] | Y |  | Y |  |  | Both
125318 | 17/NW/0193 | 216411 | IntAct- IFA to prevent anastomotic leak in rectal cancer surgery | No |  | 35 |  |  | 2017-11-09 | 2018-03-09 | 2017-04-20 | 2018-04-13 | 2018-04-13 | 2018-04-13 |  |  |  |  | Y | Y |  |  |  |  | NHS Provider
125319 | 18/YH/0014 | 224065 | The ACTIVE TRIAL | No |  | 115 |  |  | 2018-03-13 | 2018-03-20 | 2018-02-13 | 2018-07-11 | 2018-07-13 | 2018-07-23 | [5 empty] | Y |  | Y |  |  | Sponsor
125320 | 17/WS/0137 | 228128 | VNS-REHAB | No |  | 69 |  |  | 2018-03-08 | 2018-03-14 | 2017-09-27 | 2018-05-10 | 2018-05-22 | 2018-05-24 |  |  |  | Y | [6 empty] | Sponsor
125321 | 18/LO/0227 | 228539 | A feasibility study of ACT for people with MND (Phase 1) v1 | No |  | 42 |  |  | 2018-02-22 | 2018-08-09 | 2018-03-13 | 2018-09-07 | 2018-09-20 | 2018-09-27 | [7 empty] | Y |  |  | Sponsor
125322 | 17/NE/0124 | 216591 | TEMPO Study | No |  | 32 |  |  | 2017-04-12 | 2018-03-16 | 2017-07-10 | 2018-03-09 | 2018-04-17 | 2018-05-25 | [5 empty] | Y |  |  |  |  | Neither
125323 | 17/LO/1847 | 216867 | MUK Twelve | No |  |  |  |  | 2017-11-03: 2017-12-04; 2018-02-21: 2018-03-16; 2018-03-20: 2018-01-04 | [7 empty] | Y |  |  | Both
125324 | 16/EE/0546 | 210292 | Barrett?s oESophagus Trial 3 (BEST3) | No |  | 53 |  |  | 2017-05-26 | 2017-10-02 | 2017-02-15 | 2017-10-23 | 2017-11-24 | 2018-06-21 | [5 empty] | Y |  | Y |  |  | Neither
125325 | 17/LO/1690 | 220495 | ASTIClite | Yes | 2018-06-07 | 196 | 48 | 244 | 2017-10-06 | 2017-10-06 | 2017-11-15 | 2018-04-27 | 2018-04-20 | 2018-05-09 | Y |  |  |  | Y | Y |  |  |  |  | NHS Provider
125327 | 17/EM/1741 | 232904 | EMmY - Preventing Gestational Diabetes with myo-inositol supplement | Yes | 2018-02-14 | 106 | 14 | 120 | 2017-10-17 | 2017-10-17 | 2017-12-29 | 2018-01-31 | 2018-01-31 | 2018-02-14 | Y | [9 empty] | Neither
125328 | 16/SS/0137 | 199347 | ATTEST 2 | No |  | 181 |  |  | 2017-10-24 | 2017-10-24 | 2017-01-11 | 2018-02-09 | 2018-04-23 | 2018-02-24 |  |  |  | Y | Y | [5 empty] | Both
125329 | 17/SW/0221 | 232448 | (CAIN457K2340) Secukinumab compared with GP2017 in Active AS | Yes | 2017-12-18 | 47 | 5 | 52 | 2017-10-27 | 2017-10-27 | 2017-11-28 | 2017-12-08 | 2017-12-13 | 2017-12-16 | [10 empty] | NA
125330 | 17/EE/0402 | 224923 | M16-000 | No |  | 168 |  |  | 2017-10-12 | 2017-10-31 | 2017-11-28 | 2018-01-04 | 2018-04-17 | 2018-06-07 |  |  |  | Y | Y | [5 empty] | Both
125331 | 17/EE/0400 | 224645 | M16-006 | No |  | 168 |  |  | 2017-10-18 | 2017-10-31 | 2017-11-28 | 2018-01-04 | 2018-04-17 | 2018-05-18 |  |  |  |  | Y | Y |  |  |  |  | Both
125332 | 17/EM/0325 | 227113 | PCYC-1143-CA Phase 3 study of Ibrutinib in subjects with MCL | Yes | 2018-07-04 | 183 | 61 | 244 | 2017-08-08 | 2017-11-02 | 2017-10-10 | 2018-05-03 | 2018-05-04 | 2018-06-20 |  |  |  | Y |  | Y |  | Y |  |  | Sponsor
125333 | 17/SC/0294 | 224828 | WO39392 IMpassion 031 ATEZOLIZUMAB or PLACEBO + NAB-PACLITAXEL + CHEMO | Yes | 2018-02-27 | 25 | 91 | 116 | 2017-07-03 | 2017-11-03 | 2017-08-02 | 2017-11-15 | 2017-11-28 | 2018-01-24 |  |  |  |  | Y | Y |  |  |  |  | NHS Provider
125334 | 17/NE/0200 | 220486 | SMART Registry_Boston Scientific_(0393-0026) | No |  | 137 |  |  | 2017-11-03 | 2017-11-06 | 2017-08-24 | 2018-02-22 | 2018-03-23 | 2018-03-29 |  |  |  |  | Y |  |  | Y |  |  | Both
125335 | 17/LO/1592 | 225931 | BO39633 - Atezolizumab open label extension study | Yes | 2018-05-14 | 33 | 146 | 179 | 2017-10-02 | 2017-11-16 | 2017-11-07 | 2017-12-15 | 2017-12-19 | 2018-04-06 |  |  |  | Y | [6 empty] | Sponsor
125336 | 17/NE/0257 | 225434 | HUBBLE | Yes | 2018-05-08 | 30 | 139 | 169 | 2017-08-11 | 2017-11-20 | 2017-11-17 | 2017-10-17 | 2017-12-20 | 2018-01-24 |  |  |  |  | Y | [5 empty] | NHS Provider
125337 | 17/LO/0041 | 219676 | CardioMEMS HF System OUS Post Approval Study | Yes | 2018-04-20 | 122 | 28 | 150 | 2017-11-14 | 2017-11-21 | 2017-03-06 | 2018-03-14 | 2018-03-23 | 2018-01-26 |  |  |  | Y |  |  |  | Y |  |  | Sponsor
125338 | 17/WM/0106 | 201079 | MRI for early response prediction to anti-TNF therapy | Yes | 2018-06-01 | 84 | 107 | 191 | 2017-11-22 | 2017-11-22 | 2017-04-28 | 2018-04-19 | 2018-02-14 | 2018-01-08 |  |  |  | Y |  |  |  | Y |  |  | Sponsor
125339 | 17/WS/0081 | 225638 | QUIDS 2 | Yes | 2018-02-26 | 76 | 19 | 95 | 2017-11-23 | 2017-11-23 | 2017-08-15 | 2018-02-05 | 2018-02-07 | 2018-02-07 |  |  |  |  | Y |  |  | Y |  |  | Both
125341 | 17/EE/0481 | 226412 | PITHIA | No |  | 38 |  |  | 2017-08-29 | 2017-11-28 | 2018-01-18 | 2018-02-19 | 2018-01-05 |  |  |  |  | Y | [6 empty] | Sponsor
125342 | 17/LO/1478 | 226023 | SMART-C | Yes | 2018-02-12 | 37 | 38 | 75 | 2017-09-20 | 2017-11-29 | 2017-11-23 | 2017-12-14 | 2018-01-05 | 2018-01-29 | [10 empty] | NA
125343 | 17/YH/0345 | 233852 | COLUMBA | Yes | 2018-04-30 | 70 | 80 | 150 | 2017-08-22 | 2017-12-01 | 2018-01-17 | 2018-02-01 | 2018-02-09 | 2018-03-23 | [7 empty] | Y |  |  | Sponsor
125344 | 17/LO/1245 | 208149 | Metronidazole Versus lactic acId for Treating bacterial vAginosis?VITA | Yes | 2018-05-17 | 62 | 100 | 162 | 2017-10-19 | 2017-12-06 | 2017-09-12 | 2018-01-24 | 2018-02-06 | 2018-04-20 | [7 empty] | Y |  |  | Sponsor
125345 | 17/YH/0346 | 233641 | SHINE (BWI_2017_01) | Yes | 2018-02-28 | 48 | 14 | 62 | 2017-09-19 | 2017-12-28 | 2018-02-06 | 2018-02-21 | 2018-02-14 | 2018-02-21 | [10 empty] | NA
125346 | 17/EM/0361 | 234065 | 215MS202 Efficacy & Safety of BIIB033 as an Add-on Therapy in RMS | No |  | 157 |  |  | 2017-10-04 | 2018-01-12 | 2018-01-11 | 2018-03-28 | 2018-06-18 |  |  |  | Y |  | Y |  |  | Y |  |  | NHS Provider
125347 | 17/LO/1289 | 226881 | A Phase 2b Ublituximab, TGR-1202, Bendamustine in NHL patients | Yes | 2018-05-23 | 116 | 9 | 125 | 2017-10-27 | 2018-01-18 | 2017-10-17 | 2018-05-11 | 2018-05-14 | 2018-05-22 |  |  |  |  | Y |  |  | Y |  |  | NHS Provider
125348 | 17/SS/0052 | 196827 | Early valve surgery for severe asymptomatic aortic stenosis (EVoLVeD) | No |  | 34 |  |  | 2018-01-31 | 2018-03-16 | 2017-06-17 | 2018-04-05 | 2018-04-19 | 2018-04-27 | [5 empty] | Y |  |  |  |  | Sponsor
125349 | 18/LO/0079 | 232937 | LJPC-401 for iron overload in adults with TDT | Yes | 2018-06-12 | 39 | 29 | 68 | 2018-02-09 | 2018-04-05 | 2018-04-05 | 2018-04-26 | 2018-05-14 | 2018-05-15 |  |  |  |  | Y | [5 empty] | NHS Provider
125350 | 17/LO/1624 | 195099 | Effect of dietary nitrate ingestion in Heart Failure (DiNOmo-HF) | No |  | 45 |  |  | 2017-09-21 | 2018-04-10 | 2018-03-22 | 2018-05-21 | 2018-05-25 | 2018-05-25 | [5 empty] | Y |  |  |  |  | Neither
125351 | 18/LO/0099 | 240520 | Fitusiran in Patients With Hemophilia A or B Without Inhibitory Ab | No |  |  |  |  | 2017-08-22: 2017-08-01; 2017-12-01: 2018-08-08; 2018-01-17: 2018-03-22 | [7 empty] | Y |  |  | Sponsor
125352 | 17/SC/0039 | 220282 | MAGPIE | Yes | 2018-09-18 | 85 | 74 | 159 | 2018-04-05 | 2018-04-12 | 2017-04-18 | 2018-06-18 | 2018-07-06 | 2018-09-03 |  |  |  |  | Y |  |  | Y |  |  | Both
125353 | 17/EM/0281 | 229054 | 204862 Phase 3 switch study -TAF regimen to DTG + 3TC in HIV-1 adults | No |  | 17 |  |  | 2018-02-15 | 2018-04-13 | 2018-02-15 | 2018-04-26 | 2018-04-30 | 2018-05-08 |  |  | Y | [7 empty] | Sponsor
125354 | 18/LO/0235 | 240315 | An Open Label Extension Study of GBT440 Administered Orally to Patients with Sickle Cell Disease Who Have Participated in GBT440 Clinical Trials | No |  |  |  |  | 2017-08-22: 2018-02-09; 2017-12-01: 2018-04-17; 2018-01-17: 2018-04-17 |  |  |  | Y |  |  |  | Y |  |  | NHS Provider
125355 | 17/LO/0825 | 223457 | Filgotinib, GS-9876, GS-4059 in Adults with Active Sjogren?s Syndrome | No |  |  |  |  | 2017-08-22: 2018-03-26; 2017-12-01: 2018-04-18; 2018-01-17: 2017-06-30 | [7 empty] | Y |  |  | Sponsor
125356 | 17/SC/0639 | 236312 | BMN 270-302 Gene therapy study in severe Haemophilia A patients | No |  | 5 |  |  | 2018-01-08 | 2018-04-19 | 2018-02-26 | 2018-04-05 | 2018-04-24 | 2018-04-11 | [5 empty] | Y |  |  |  |  | Neither
125357 | 17/YH/0289 | 231276 | A phase 1/2 study with Acalabrutinib and AZD6738 in high risk CLL | No |  |  |  |  | 2017-08-22: 2018-01-11; 2017-12-01: 2018-04-23; 2018-01-17: 2017-10-18 |  |  |  | Y | Y | [5 empty] | Both
125358 | 18/EE/0079 | 237389 | APEX 2 BCX7353 in Prevention of HAE Attacks | Yes | 2018-07-10 | 23 | 55 | 78 | 2018-02-16 | 2018-04-23 | 2018-04-18 | 2018-04-11 | 2018-05-16 | 2018-05-21 | [10 empty] | NA
125359 | 17/SC/0090 | 215068 | c-TRAK TN | No |  |  |  |  | 2017-08-22: 2017-11-08; 2017-12-01: 2018-04-26; 2018-01-17: 2017-07-05 |  |  |  | Y | Y | [5 empty] | Both
125360 | 17/YH/0369 | 232340 | BGB-3111-304 | No |  | 25 |  |  | 2017-11-20 | 2018-08-30 | 2018-01-03 | 2018-08-16 | 2018-09-24 | 2018-09-28 |  |  |  |  | Y |  |  | Y |  |  | Both
125361 | 17/SC/0609 | 235575 | Daiichi Sankyo DS8201-A-U201 (DS-8201a) | Yes | 2018-07-02 | 18 | 49 | 67 | 2017-12-22 | 2018-04-26 | 2018-01-08 | 2018-04-04 | 2018-05-14 | 2018-06-27 | [5 empty] | Y |  |  |  |  | Neither
125362 | 18/LO/0364 | 237978 | Nalu Medical NAL-02-2016-FS SCS Feasibillity trial | Yes | 2018-06-13 | 48 | 0 | 48 | 2018-03-06 | 2018-04-26 | 2018-04-23 | 2018-06-05 | 2018-06-13 | 2018-06-13 | [7 empty] | Y |  |  | Both
125364 | 16/LO/2150 | 201093 | OCTOVA | No |  |  |  |  | 2017-08-22: 2018-04-20; 2017-12-01: 2018-05-02; 2018-01-17: 2017-01-26 | [7 empty] | Y |  |  | Sponsor
125365 | 18/LO/0149 | 236716 | MO39193 - Atezolizumab + Chemotherapy in early relapsing TNBC | Yes | 2018-08-16 | 95 | 10 | 105 | 2018-02-07 | 2018-05-03 | 2018-04-17 | 2018-06-13 | 2018-08-06 | 2018-08-15 |  |  |  |  | Y |  |  | Y |  |  | Both
125366 | 18/SC/0095 | 235876 | BREEZE-AD4 - Baricitinib in moderate to severe atopic dermatitis | No |  | 40 |  |  | 2018-02-15 | 2018-05-09 | 2018-04-05 | 2018-06-18 | 2018-06-18 |  |  |  |  | Y | Y | [5 empty] | Both
125367 | 18/LO/0333 | 216039 | A prospective study into the utility of qHBsAg in management of CHB v1 | Yes | 2018-07-04 | 43 | 12 | 55 | 2018-05-10 | 2018-05-10 | 2018-04-17 | 2018-06-22 | 2018-06-22 | 2018-06-22 | [10 empty] | NA
125368 | 18/LO/0052 | 228730 | A study to evaluate JNJ-64300535 DNA vaccine in chronic Hepatitis B | No |  |  |  |  | 2017-08-22: 2018-01-11; 2017-12-01: 2018-05-11; 2018-01-17: 2018-03-22 |  |  |  | Y | Y | [5 empty] | Both
125369 | 16/NS/0106 | 212541 | RAACENO | No |  | 37 |  |  | 2017-11-15 | 2018-05-16 | 2017-04-04 | 2018-06-01 | 2018-06-22 | [6 empty] | Y |  |  |  |  | Neither
125370 | 18/WA/0138 | 242665 | D5136C00009 - Hestia 3, Phase 3 study of Ticagrelor in Paediatric SCD | No |  | 48 |  |  | 2018-05-18 | 2018-07-31 | 2018-07-18 | 2018-08-23 | 2018-09-17 | 2018-09-18 | [10 empty] | NA
125371 | 18/LO/0779 | 235161 | B1371019 | No |  |  |  |  | 2017-08-22: 2018-04-23; 2017-12-01: 2018-08-10 | [10 empty] | NA
125372 | 17/YH/0386 | 233803 | Cryo AF Global Registry | Yes | 2018-07-27 | 17 | 49 | 66 | 2017-11-07 | 2018-05-22 | 2018-01-11 | 2018-06-08 | 2018-06-08 | 2018-07-04 | [5 empty] | Y |  |  |  |  | Neither
125373 | 16/WM/0472 | 211270 | CONFIRM | Yes | 2018-10-10 | 87 | 47 | 134 | 2017-05-05 | 2018-05-29 | 2017-03-14 | 2018-05-09 | 2018-08-24 | 2018-09-19 |  |  |  |  | Y |  |  | Y |  |  | Both
125374 | 17/YH/0262 | 219133 | TRITON Trial v1.0 | Yes | 2018-09-11 | 5 | 97 | 102 | 2017-10-09 | 2018-06-01 | 2017-11-07 | 2017-11-21 | 2018-06-06 | 2018-07-21 | [5 empty] | Y |  |  |  |  | Neither
125375 | 18/WS/0073 | 242354 | NEFECON IN PATIENTS WITH PRIMARY IGA-Nephropathy Caliditas | No |  | 100 |  |  | 2018-03-02 | 2018-06-04 | 2018-06-04 | 2018-09-04 | 2018-09-12 | 2018-09-20 |  |  |  | Y | [6 empty] | Sponsor
125377 | 18/NE/0125 | 238346 | PROFHER2 Trial - Version 1.0 | No |  | 62 |  |  | 2018-05-01 | 2018-06-05 | 2018-05-15 | 2018-07-05 | 2018-08-06 |  |  |  |  | Y | [6 empty] | Sponsor
125378 | 18/SC/0155 | 236211 | The EMPA-KIDNEY Study | No |  | 88 |  |  | 2018-04-20 | 2018-06-07 | 2018-04-26 | 2018-07-04 | 2018-09-03 |  |  |  |  | Y | [6 empty] | Sponsor
125379 | 17/EM/0406 | 235483 | PRTX-100 in ITP (PRTX-100-202) | No |  |  |  |  | 2017-08-22: 2018-06-05; 2017-12-01: 2018-06-07; 2018-01-17: 2018-01-15 |  |  |  | Y | Y | [5 empty] | Both
125380 | 17/LO/1596 | 228894 | REACH Pregnancy Circles Trial ; Version 1.0 | No |  |  |  |  | 2017-08-22: 2018-06-01; 2017-12-01: 2018-06-08; 2018-01-17: 2018-05-30 |  |  |  | Y | [6 empty] | Sponsor
125381 | 18/NE/0214 | 245998 | MN39158 - A Long Term Extension Study in Multiple Sclerosis | No |  | 84 |  |  | 2018-04-18 | 2018-06-18 | 2018-07-11 | 2018-07-19 | 2018-09-10 | [6 empty] | Y |  |  |  |  | Neither
128140 | 14/WS/0113 | 142409 | XILO-FIST | Yes | 2018-06-14 | 61 | 185 | 246 | 2017-06-12 | 2017-10-11 | 2016-06-15 | 2017-11-29 | 2017-12-11 | 2018-01-17 |  |  |  |  | Y | [5 empty] | NHS Provider
128141 | 17/ES/0051 | 223060 | Study of NUC-1031 in Patients with Platinum-Resistant Ovarian Cancer | Yes | 2018-03-15 | 63 | 70 | 133 | 2017-07-11 | 2017-11-02 | 2017-07-05 | 2017-12-12 | 2018-01-04 | 2018-03-12 |  |  |  |  | Y | [5 empty] | NHS Provider
128142 | 17/SC/0319 | 227637 | A phase II study of Cobimetnib + Atezolizmab in patients with tumours | Yes | 2017-12-21 | 43 | 6 | 49 | 2017-07-10 | 2017-11-02 | 2017-10-30 | 2017-12-08 | 2017-12-15 | 2017-12-20 | [10 empty] | NA
128143 | 17/LO/1519 | 230794 | The Leaflex? Performer Feasibility Study | Yes | 2018-05-01 | 77 | 90 | 167 | 2017-08-03 | 2017-11-15 | 2017-11-01 | 2018-01-18 | 2018-01-31 | 2018-04-26 | Y |  |  |  |  | Y |  |  |  |  | Both
128144 | 17/EE/0271 | 225013 | AceFIT ? Acetabular Fractures in older patients Intervention Trial. | Yes | 2018-05-11 | 121 | 37 | 158 | 2017-12-04 | 2017-12-04 | 2017-10-10 | 2018-03-01 | 2018-04-04 | 2018-04-06 | [5 empty] | Y |  |  |  |  | Neither
128145 | 17/EE/0422 | 230642 | M16-098 | Yes | 2018-04-09 | 24 | 45 | 69 | 2017-10-11 | 2018-01-30 | 2018-01-29 | 2018-02-16 | 2018-02-23 | 2018-03-06 | [5 empty] | Y | Y |  |  |  | Neither
128146 | 17/EE/0437 | 233853 | AQUILA (54767414SMM3001) | Yes | 2018-05-10 | 14 | 56 | 70 | 2017-10-27 | 2018-03-01 | 2018-01-10 | 2018-02-05 | 2018-03-15 | 2018-04-03 |  |  |  |  | Y | [5 empty] | NHS Provider
128147 | 17/SC/0652 | 235511 | SHP647 long term extension for moderate to severe Ulcerative Colitis | No |  | 135 |  |  | 2018-01-10 | 2018-03-20 | 2018-03-06 | 2018-07-17 | 2018-08-02 | 2018-08-06 | [5 empty] | Y |  |  |  |  | Neither
128148 | 18/EM/0086 | 236856 | A study of Mavenclad? in participants with multiple sclerosis | No |  | 111 |  |  | 2018-05-18 | 2018-05-23 | 2018-05-22 | 2018-08-28 | 2018-09-11 | 2018-09-12 |  |  |  | Y |  |  |  | Y |  |  | Sponsor
128149 | 18/LO/0448 | 241283 | CALDOSE - 1 | No |  | 86 |  |  | 2018-06-20 | 2018-06-20 | 2018-05-03 | 2018-06-26 | 2018-09-14 |  |  |  |  | Y |  | Y |  |  |  |  | Both
128150 | 17/LO/2043 | 236939 | Development Of a haemophiLia physiotherapy intervention - Version 1 | Yes | 2018-09-20 | 68 | 23 | 91 | 2018-06-21 | 2018-06-21 | 2018-05-25 | 2018-08-24 | 2018-08-28 | 2018-08-29 | [7 empty] | Y |  |  | Both
128151 | 17/SC/0164 | 210735 | Early cryoprecipitate in major trauma haemorrhage: CRYOSTAT-2 | Yes | 2018-07-16 | 17 | 5 | 22 | 2017-03-17 | 2018-06-24 | 2017-05-26 | 2018-07-11 | 2018-07-11 | 2018-07-11 | [10 empty] | NA
128152 | 18/NE/0102 | 240702 | CA40192:Etrolizumab in patients with moderate to severe UC or CD | No |  | 8 |  |  | 2018-03-19 | 2018-07-04 | 2018-05-15 | 2018-07-05 | 2018-07-12 | 2018-07-12 |  |  |  |  | Y | Y |  |  |  |  | NHS Provider
128153 | 17/NE/0113 | 210677 | The PIONEER Study | No |  | 4 |  |  | 2018-03-26 | 2018-09-17 | 2017-05-24 | 2018-09-11 | 2018-09-21 | 2018-09-28 | [5 empty] | Y |  |  |  |  | Neither
128154 | 17/NE/0082 | 217397 | Phase 3 study with subjects with Moderately to Severely Active RA with IR or Intolerance to bDMARDs | No |  | 53 |  |  | 2018-06-22 | 2018-07-09 | 2017-06-02 | 2018-08-23 | 2018-08-31 | 2018-09-04 |  |  |  |  | Y | Y |  |  |  |  | NHS Provider
128155 | 16/EE/0324 | 203951 | Prophylatic and Pre-emptive DLI for myeloid malignancies (PRO-DLI) | No |  |  |  |  | 2017-08-22: 2018-04-01; 2017-12-01: 2018-07-12; 2018-01-17: 2016-09-08 | [7 empty] | Y |  |  | Both
128156 | 18/NW/0037 | 234353 | REDUCE-RISKinCD-PIBD -TRIAL | No |  |  |  |  | 2017-08-22: 2018-07-16; 2017-12-01: 2018-07-16; 2018-01-17: 2018-07-12 | [7 empty] | Y |  |  | NHS Provider
128157 | 17/LO/1629 | 228288 | Phase 1b study in patients with advanced or solid tumours | Yes | 2018-09-05 | 23 | 27 | 50 | 2017-10-19 | 2018-07-17 | 2017-11-06 | 2018-06-27 | 2018-08-09 | 2018-08-28 | [10 empty] | NA
128158 | 18/LO/0378 | 234232 | PIONEER III | Yes | 2018-09-07 | 36 | 16 | 52 | 2018-04-23 | 2018-07-17 | 2018-06-22 | 2018-08-16 | 2018-08-22 | 2018-08-28 | [10 empty] | NA
128159 | 18/YH/0069 | 242258 | GLOW study | Yes | 2018-09-05 | 35 | 14 | 49 | 2018-02-06 | 2018-07-18 | 2018-06-04 | 2018-08-15 | 2018-08-22 | 2018-09-03 | [10 empty] | NA
128160 | 18/SC/0037 | 234222 | GO39942 / RO5541007 in lymphoma | No |  | 27 |  |  | 2018-02-27 | 2018-07-18 | 2018-04-16 | 2018-08-06 | 2018-08-14 | [11 empty] | NA
128161 | 18/LO/0397 | 237296 | MORPHEUS-TNBC | Yes | 2018-08-14 | 21 | 4 | 25 | 2018-03-15 | 2018-07-20 | 2018-06-08 | 2018-08-06 | 2018-08-10 | 2018-08-10 | [10 empty] | NA
128162 | 17/NE/0311 | 229481 | GO39733 | Yes | 2018-09-12 | 25 | 19 | 44 | 2017-09-08 | 2018-07-30 | 2017-11-22 | 2018-08-06 | 2018-08-24 | 2018-09-04 | [10 empty] | NA
128164 | 17/LO/0980 | 219505 | HALT - Stereotactic Body Radiotherapy for the treatment of OPD | No |  |  |  |  | 2017-08-22: 2018-02-23; 2017-12-01: 2018-08-10; 2018-01-17: 2017-07-10 |  |  |  |  | Y |  |  | Y |  |  | Both
128165 | 18/YH/0133 | 239570 | GO40241 - Phase III - Neoadjuvant Atezolizumab + Chemotherapy in NSCLC | No |  |  |  |  | 2017-08-22: 2018-04-11; 2017-12-01: 2018-08-10; 2018-01-17: 2018-05-17 | [7 empty] | Y |  |  | Both
128166 | 18/WA/0104 | 236930 | P3100:pevonedistat+azacitidine for HR MDS/CMML/low blast AML treatment | No |  |  |  |  | 2017-08-22: 2018-03-02; 2017-12-01: 2018-08-14; 2018-01-17: 2018-04-29 | [10 empty] | NA
128167 | 18/SW/0038 | 235662 | The LoDED Trial | Yes | 2018-10-11 | 49 | 7 | 56 | 2018-08-13 | 2018-08-16 | 2018-04-26 | 2018-10-02 | 2018-10-04 | 2018-10-08 | [10 empty] | NA
128168 | 18/LO/0555 | 237992 | PROTECTOR | No |  |  |  |  | 2017-08-22: 2018-08-17; 2017-12-01: 2018-08-17; 2018-01-17: 2018-04-19 | [10 empty] | NA
128169 | 18/LO/1398 | 247563 | Diabetic Gastroparesis Study with Randomized-withdrawal Period | No |  |  |  |  | 2017-08-22: 2018-08-22; 2017-12-01: 2018-08-22 | [10 empty] | NA
128170 | 18/NE/0142 | 242919 | The REVERSE study | No |  |  |  |  | 2018-07-13 | 2018-09-03 | 2018-07-13 |  |  | 2018-10-10 | [10 empty] | NA
128171 | 16/YH/0157 | 204585 | PLATO?-?PersonaLising?Anal?cancer?radioTherapy?dOse | No |  | 22 |  |  | 2017-05-17 | 2018-09-04 | 2016-07-20 | 2018-09-21 | 2018-09-26 | 2018-09-28 | [10 empty] | NA
128172 | 18/LO/1542 | 247189 | Phase 2 study to test the efficacy & safety of KPL 301 in GCA | No |  |  |  |  | 2017-08-22: 2018-07-24; 2017-12-01: 2018-09-04 | [10 empty] | NA
128173 | 18/SW/0135 | 232687 | TULIP: Surgical vs non-surgical treatment of LC1 pelvic injuries | No |  |  |  |  | 2017-08-22: 2018-07-27; 2017-12-01: 2018-09-05; 2018-01-17: 2018-07-04 | [10 empty] | NA
Note on A1: System generated field
Note on G1: System generated field. Please check your dates if value is negative.
Note on J1: Format dd/mm/yyyy.
Note on K1: Format dd/mm/yyyy.
Note on L1: Format dd/mm/yyyy.
Note on M1: Format dd/mm/yyyy.
Note on N1: Format dd/mm/yyyy.
Note on O1: Format dd/mm/yyyy.