## Sheet1
ID | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Date Site Ready To Start | A - Permissions delayed/ denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | Reasons for delay correspond to:
136509 | 17/LO/2064 | 232321 | Phase 2 study of BGB-3111 and Obinutuzumab in Follicular Lymphoma | Yes | 2018-12-10 | 122 | 0 | 122 | 2018-01-17 | 2018-08-10 | 2018-06-12 | 2018-11-30 | 2018-12-10 | 2018-12-10 |  |  |  | Y | Y | [5 empty] | Sponsor
136510 | 17/YH/0436 | 234886 | BP40234: RO6874281 in combination with atezolizumab in solid tumours | Yes | 2018-06-26 | 32 | 28 | 60 | 2018-02-15 | 2018-04-27 | 2018-02-27 | 2018-05-17 | 2018-05-29 | 2018-06-05 | [10 empty] | NA
136511 | 18/LO/0227 | 228539 | A feasibility study of ACT for people with MND (Phase 1) v1 | Yes | 2018-11-12 | 42 | 53 | 95 | 2018-02-22 | 2018-08-09 | 2018-03-13 | 2018-09-07 | 2018-09-20 | 2018-09-27 | [7 empty] | Y |  |  | Sponsor
136512 | 18/LO/0079 | 232937 | LJPC-401 for iron overload in adults with TDT | Yes | 2018-06-12 | 39 | 29 | 68 | 2018-02-09 | 2018-04-05 | 2018-04-05 | 2018-04-26 | 2018-05-14 | 2018-05-15 | [10 empty] | NA
136513 | 17/LO/1624 | 195099 | Effect of dietary nitrate ingestion in Heart Failure (DiNOmo-HF) | No |  | 45 |  |  | 2017-09-21 | 2018-04-10 | 2018-03-22 | 2018-05-21 | 2018-05-25 | 2018-05-25 | [5 empty] | Y |  |  |  |  | Sponsor
136514 | 18/LO/0099 | 240520 | Fitusiran in Patients With Hemophilia A or B Without Inhibitory Ab | No |  | 173 |  |  | 2017-08-01 | 2018-08-08 | 2018-03-22 | 2019-01-10 | 2019-01-28 | 2019-01-28 |  |  |  | Y | Y | [5 empty] | Sponsor
136515 | 17/SC/0039 | 220282 | MAGPIE | Yes | 2018-09-18 | 85 | 74 | 159 | 2018-04-05 | 2018-04-12 | 2017-04-18 | 2018-06-18 | 2018-07-06 | 2018-09-03 |  |  |  |  | Y |  |  | Y |  |  | Both
136516 | 17/EM/0281 | 229054 | 204862 Phase 3 switch study -TAF regimen to DTG + 3TC in HIV-1 adults | No |  | 17 |  |  | 2018-02-15 | 2018-04-13 | 2018-02-15 | 2018-04-26 | 2018-04-30 | 2018-05-08 |  |  | Y | [7 empty] | Sponsor
136517 | 18/LO/0235 | 240315 | An Open Label Extension Study of GBT440 Administered Orally to Patients with Sickle Cell Disease Who Have Participated in GBT440 Clinical Trials | Yes | 2019-02-06 | 245 | 50 | 295 | 2018-02-09 | 2018-04-17 | 2018-04-17 | 2018-05-30 | 2018-12-18 | 2019-01-29 |  |  |  | Y |  |  |  | Y |  |  | Sponsor
136518 | 17/LO/0825 | 223457 | Filgotinib, GS-9876, GS-4059 in Adults with Active Sjogren?s Syndrome | No |  |  |  |  | 2018-03-26 | 2018-04-18 | 2017-06-30 | [10 empty] | Y |  |  | Sponsor
136522 | 17/SC/0090 | 215068 | c-TRAK TN | No |  | 69 |  |  | 2017-11-08 | 2018-08-17 | 2017-07-05 | 2018-10-16 | 2018-10-25 | 2018-10-26 |  |  |  | Y | Y | [5 empty] | Sponsor
136523 | 17/YH/0369 | 232340 | BGB-3111-304 | No |  | 25 |  |  | 2017-11-20 | 2018-08-30 | 2018-01-03 | 2018-08-16 | 2018-09-24 | 2018-09-28 |  |  |  |  | Y | Y |  | Y |  |  | Sponsor
136524 | 17/SC/0609 | 235575 | Daiichi Sankyo DS8201-A-U201 (DS-8201a) | Yes | 2018-07-02 | 18 | 49 | 67 | 2017-12-22 | 2018-04-26 | 2018-01-08 | 2018-04-04 | 2018-05-14 | 2018-06-27 | [10 empty] | NA
136525 | 18/LO/0364 | 237978 | Nalu Medical NAL-02-2016-FS SCS Feasibillity trial | Yes | 2018-06-13 | 48 | 0 | 48 | 2018-03-06 | 2018-04-26 | 2018-04-23 | 2018-06-05 | 2018-06-13 | 2018-06-13 | [10 empty] | NA
136526 | 16/LO/2150 | 201093 | OCTOVA | No |  | 187 |  |  | 2018-04-20 | 2018-05-02 | 2017-01-26 | 2018-10-15 | 2018-11-05 | 2018-11-23 | [7 empty] | Y |  |  | Neither
136527 | 18/LO/0149 | 236716 | MO39193 - Atezolizumab + Chemotherapy in early relapsing TNBC | Yes | 2018-08-16 | 95 | 10 | 105 | 2018-02-07 | 2018-05-03 | 2018-04-17 | 2018-06-13 | 2018-08-06 | 2018-08-15 |  |  |  |  | Y |  |  | Y |  |  | Sponsor
136528 | 18/SC/0095 | 235876 | BREEZE-AD4 - Baricitinib in moderate to severe atopic dermatitis | No |  | 40 |  |  | 2018-02-15 | 2018-05-09 | 2018-04-05 | 2018-06-18 | 2018-06-18 |  |  |  |  | Y | Y | [5 empty] | Both
136530 | 18/LO/0052 | 228730 | A study to evaluate JNJ-64300535 DNA vaccine in chronic Hepatitis B | No |  |  |  |  | 2018-01-11 | 2018-05-11 | 2018-03-22 | [6 empty] | Y |  |  |  | Y |  |  | Sponsor
136531 | 16/NS/0106 | 212541 | RAACENO | Yes | 2018-10-18 | 37 | 118 | 155 | 2017-11-15 | 2018-05-16 | 2017-04-04 | 2018-06-01 | 2018-06-22 | 2018-06-25 | [5 empty] | Y |  |  |  |  | Sponsor
136532 | 18/WA/0138 | 242665 | D5136C00009 - Hestia 3, Phase 3 study of Ticagrelor in Paediatric SCD | Yes | 2018-11-13 | 48 | 57 | 105 | 2018-05-18 | 2018-07-31 | 2018-07-18 | 2018-08-23 | 2018-09-17 | [8 empty] | Y |  |  | Sponsor
136533 | 18/LO/0779 | 235161 | B1371019 | No |  | 181 |  |  | 2018-04-23 | 2018-08-10 | 2018-06-15 | 2019-02-04 | 2019-02-07 |  |  |  |  | Y |  |  |  | Y |  |  | Sponsor
136534 | 17/YH/0386 | 233803 | Cryo AF Global Registry | Yes | 2018-07-27 | 17 | 49 | 66 | 2017-11-07 | 2018-05-22 | 2018-01-11 | 2018-06-08 | 2018-06-08 | 2018-07-04 | [10 empty] | NA
136535 | 16/WM/0472 | 211270 | CONFIRM | Yes | 2018-10-10 | 87 | 47 | 134 | 2017-05-05 | 2018-05-29 | 2017-03-14 | 2018-05-09 | 2018-08-24 | 2018-09-19 |  |  |  |  | Y |  |  | Y |  |  | Both
136536 | 17/YH/0262 | 219133 | TRITON Trial v1.0 | Yes | 2018-09-18 | 5 | 104 | 109 | 2017-10-09 | 2018-06-01 | 2017-11-07 | 2017-11-21 | 2018-06-06 | 2018-07-21 | [5 empty] | Y |  |  |  |  | Neither
136537 | 18/WS/0073 | 242354 | NEFECON IN PATIENTS WITH PRIMARY IGA-Nephropathy Caliditas | Yes | 2018-10-31 | 100 | 49 | 149 | 2018-03-02 | 2018-06-04 | 2018-06-04 | 2018-09-04 | 2018-09-12 | 2018-09-20 |  |  |  | Y | [6 empty] | Sponsor
136538 | 18/NE/0125 | 238346 | PROFHER2 Trial - Version 1.0 | Yes | 2018-10-03 | 62 | 58 | 120 | 2018-05-01 | 2018-06-05 | 2018-05-15 | 2018-07-05 | 2018-08-06 | 2018-08-06 | [5 empty] | Y |  |  |  |  | NHS Provider
136539 | 18/SC/0155 | 236211 | The EMPA-KIDNEY Study | No |  | 88 |  |  | 2018-04-20 | 2018-06-07 | 2018-04-26 | 2018-07-04 | 2018-09-03 | 2018-09-03 |  |  |  | Y | [6 empty] | Sponsor
136540 | 17/EM/0406 | 235483 | PRTX-100 in ITP (PRTX-100-202) | No |  |  |  |  | 2018-06-05 | 2018-06-07 | 2018-01-15 | [5 empty] | Y | [7 empty] | Sponsor
136541 | 17/LO/1596 | 228894 | REACH Pregnancy Circles Trial ; Version 1.0 | Yes | 2019-02-05 | 41 | 5 | 46 | 2018-06-01 | 2018-12-21 | 2018-05-30 | 2019-01-31 | 2019-01-31 | 2019-01-31 | [10 empty] | NA
136542 | 18/NE/0214 | 245998 | MN39158 - A Long Term Extension Study in Multiple Sclerosis | Yes | 2018-11-14 | 84 | 65 | 149 | 2018-04-18 | 2018-06-18 | 2018-07-11 | 2018-07-19 | 2018-09-10 | 2018-09-10 | [5 empty] | Y |  |  |  |  | NHS Provider
136543 | 18/EM/0086 | 236856 | A study of Mavenclad? in participants with multiple sclerosis | No |  | 111 |  |  | 2018-05-18 | 2018-05-23 | 2018-05-22 | 2018-08-28 | 2018-09-11 | 2018-09-12 |  |  |  | Y |  | Y |  | Y |  |  | Sponsor
136544 | 18/LO/0448 | 241283 | CALDOSE - 1 | Yes | 2018-12-17 | 86 | 94 | 180 | 2018-06-20 | 2018-06-20 | 2018-05-03 | 2018-06-26 | 2018-09-14 | 2018-10-22 |  |  |  | Y |  | Y |  |  |  |  | Both
136545 | 17/LO/2043 | 236939 | Development Of a haemophiLia physiotherapy intervention - Version 1 | Yes | 2018-09-20 | 68 | 23 | 91 | 2018-06-21 | 2018-06-21 | 2018-05-25 | 2018-08-24 | 2018-08-28 | 2018-08-29 | [7 empty] | Y |  |  | Both
136546 | 17/SC/0164 | 210735 | Early cryoprecipitate in major trauma haemorrhage: CRYOSTAT-2 | Yes | 2018-07-16 | 17 | 5 | 22 | 2017-03-17 | 2018-06-24 | 2017-05-26 | 2018-07-11 | 2018-07-11 | 2018-07-11 | [10 empty] | NA
136547 | 18/NE/0102 | 240702 | CA40192:Etrolizumab in patients with moderate to severe UC or CD | No |  | 8 |  |  | 2018-03-19 | 2018-07-04 | 2018-05-15 | 2018-07-05 | 2018-07-12 | 2018-07-12 | [5 empty] | Y |  |  |  |  | Sponsor
136548 | 17/NE/0113 | 210677 | The PIONEER Study | No |  | 4 |  |  | 2018-03-26 | 2018-09-17 | 2017-05-24 | 2018-09-11 | 2018-09-21 | 2018-09-28 | [5 empty] | Y |  |  |  |  | Sponsor
136549 | 17/NE/0082 | 217397 | Phase 3 study with subjects with Moderately to Severely Active RA with IR or Intolerance to bDMARDs | No |  | 53 |  |  | 2018-06-22 | 2018-07-09 | 2017-06-02 | 2018-08-23 | 2018-08-31 | 2018-09-04 |  |  |  |  | Y | Y |  |  |  |  | NHS Provider
136550 | 16/EE/0324 | 203951 | Prophylatic and Pre-emptive DLI for myeloid malignancies (PRO-DLI) | No |  | 113 |  |  | 2018-04-01 | 2018-07-12 | 2016-09-08 | 2018-10-17 | 2018-11-02 | 2018-11-14 | [7 empty] | Y | Y |  | Both
136551 | 18/NW/0037 | 234353 | REDUCE-RISKinCD-PIBD -TRIAL | Yes | 2018-11-27 | 114 | 20 | 134 | 2018-07-16 | 2018-07-16 | 2018-07-12 | 2018-10-29 | 2018-11-07 | 2018-11-07 | [7 empty] | Y |  |  | NHS Provider
136552 | 17/LO/1629 | 228288 | Phase 1b study in patients with advanced or solid tumours | Yes | 2018-09-05 | 23 | 27 | 50 | 2017-10-19 | 2018-07-17 | 2017-11-06 | 2018-06-27 | 2018-08-09 | 2018-08-28 | [10 empty] | NA
136553 | 18/LO/0378 | 234232 | PIONEER III | Yes | 2018-09-07 | 36 | 16 | 52 | 2018-04-23 | 2018-07-17 | 2018-06-22 | 2018-08-16 | 2018-08-22 | 2018-08-28 | [10 empty] | NA
136554 | 18/YH/0069 | 242258 | GLOW study | Yes | 2018-09-05 | 35 | 14 | 49 | 2018-02-06 | 2018-07-18 | 2018-06-04 | 2018-08-15 | 2018-08-22 | 2018-09-03 | [10 empty] | NA
136555 | 18/SC/0037 | 234222 | GO39942 / RO5541007 in lymphoma | No |  | 27 |  |  | 2018-02-27 | 2018-07-18 | 2018-04-16 | 2018-08-06 | 2018-08-14 | 2018-10-24 | [7 empty] | Y |  |  | Sponsor
136556 | 18/LO/0397 | 237296 | MORPHEUS-TNBC | Yes | 2018-08-14 | 21 | 4 | 25 | 2018-03-15 | 2018-07-20 | 2018-06-08 | 2018-08-06 | 2018-08-10 | 2018-08-10 | [10 empty] | NA
136557 | 17/NE/0311 | 229481 | GO39733 | Yes | 2018-09-12 | 25 | 19 | 44 | 2017-09-08 | 2018-07-30 | 2017-11-22 | 2018-08-06 | 2018-08-24 | 2018-09-04 | [10 empty] | NA
136558 | 17/LO/0980 | 219505 | HALT - Stereotactic Body Radiotherapy for the treatment of OPD | No |  | 76 |  |  | 2018-02-23 | 2018-08-10 | 2017-07-10 | 2018-10-16 | 2018-10-25 | 2018-10-29 |  |  |  | Y |  | Y |  |  |  |  | Sponsor
136559 | 18/YH/0133 | 239570 | GO40241 - Phase III - Neoadjuvant Atezolizumab + Chemotherapy in NSCLC | Yes | 2019-03-11 | 112 | 101 | 213 | 2018-04-11 | 2018-08-10 | 2018-05-17 | 2018-11-07 | 2018-11-30 | 2018-12-07 | [7 empty] | Y |  |  | NHS Provider
136560 | 18/WA/0104 | 236930 | P3100:pevonedistat+azacitidine for HR MDS/CMML/low blast AML treatment | No |  | 64 |  |  | 2018-03-02 | 2018-08-14 | 2018-04-29 | 2018-10-08 | 2018-10-17 | 2018-11-06 |  |  |  |  | Y | Y |  |  |  |  | NHS Provider
136561 | 18/SW/0038 | 235662 | The LoDED Trial | Yes | 2018-10-11 | 49 | 7 | 56 | 2018-08-13 | 2018-08-16 | 2018-04-26 | 2018-10-02 | 2018-10-04 | 2018-10-08 | [10 empty] | NA
136562 | 18/LO/0555 | 237992 | PROTECTOR | Yes | 2018-11-01 | 61 | 15 | 76 | 2018-08-17 | 2018-08-17 | 2018-04-19 | 2018-10-17 | 2018-10-17 | 2018-11-01 | [9 empty] | Y | NHS Provider
136563 | 18/LO/1398 | 247563 | Diabetic Gastroparesis Study with Randomized-withdrawal Period | No |  |  |  |  | 2018-08-22 | 2018-08-22 | 2018-11-06 | [13 empty] | NA
136564 | 18/NE/0142 | 242919 | The REVERSE study | Yes | 2018-11-05 | 45 | 18 | 63 | 2018-07-13 | 2018-09-03 | 2018-07-13 | 2018-10-05 | 2018-10-18 | 2018-10-10 | [10 empty] | NA
136565 | 16/YH/0157 | 204585 | PLATO?-?PersonaLising?Anal?cancer?radioTherapy?dOse | No |  | 22 |  |  | 2017-05-17 | 2018-09-04 | 2016-07-20 | 2018-09-21 | 2018-09-26 | 2018-09-28 | [5 empty] | Y |  |  |  |  | NHS Provider
136566 | 18/LO/1542 | 247189 | Phase 2 study to test the efficacy & safety of KPL 301 in GCA | No |  | 135 |  |  | 2018-07-24 | 2018-09-04 | 2018-12-06 | 2019-01-07 | 2019-01-17 |  |  |  |  | Y | [6 empty] | Sponsor
136567 | 18/SW/0135 | 232687 | TULIP: Surgical vs non-surgical treatment of LC1 pelvic injuries | Yes | 2018-12-24 | 90 | 20 | 110 | 2018-07-27 | 2018-09-05 | 2018-07-04 | 2018-11-16 | 2018-12-04 | 2018-12-04 | [5 empty] | Y |  |  |  |  | Neither
136568 | 17/SC/0394 | 229032 | A Phase 2 Dose-Finding Study of Pacritinib in Myelofibrosis Patients | Yes | 2018-11-23 | 91 | 53 | 144 | 2018-05-30 | 2018-07-02 | 2017-10-23 | 2018-08-09 | 2018-10-01 | 2018-10-30 |  |  |  |  | Y | [5 empty] | NHS Provider
136569 | 17/LO/0038 | 182633 | UK P3BEP Trial | Yes | 2018-11-15 | 14 | 42 | 56 | 2017-05-22 | 2018-09-20 | 2017-04-06 | 2018-06-02 | 2018-10-04 | 2018-10-15 | [10 empty] | NA
136570 | 18/SC/0342 | 247085 | Phase III Trial of AMT-061 in adults with haemophilia B | Yes | 2019-01-22 | 23 | 109 | 132 | 2018-06-11 | 2018-09-12 | 2018-09-06 | 2018-09-26 | 2018-10-05 | 2018-11-22 | [5 empty] | Y |  |  |  |  | NHS Provider
136571 | 16/LO/1099 | 181655 | TIGER: A RANDOMIZED PHASE III TRIAL COMPARING CONVENTIONAL-DOSE CHEMOTHERAPY | Yes | 2018-11-15 | 26 | 37 | 63 | 2017-10-03 | 2018-09-13 | 2016-11-01 | 2018-10-02 | 2018-10-09 | 2018-11-06 | [10 empty] | NA
136572 | 16/EE/0315 | 197289 | Metformin SGA study version 1.2 | No |  | 193 |  |  | 2018-03-20 | 2018-04-12 | 2016-11-21 | 2018-09-05 | 2018-10-22 | 2018-10-22 |  |  |  | Y | [6 empty] | Sponsor
136573 | 18/NI/0060 | 242168 | Lenabasum in Cystic Fibrosis | Yes | 2019-01-10 | 2 | 77 | 79 | 2018-07-16 | 2018-10-23 | 2018-06-29 | 2018-10-04 | 2018-10-25 | 2018-12-03 | [5 empty] | Y |  |  |  |  | Sponsor
136574 | 18/EM/0193 | 243749 | 021FSG16010 - DUPLEX, Patients with FSGS | Yes | 2018-12-18 | 35 | 50 | 85 | 2018-08-14 | 2018-09-24 | 2018-09-18 | 2018-10-24 | 2018-10-29 | 2018-11-20 | [5 empty] | Y |  |  |  |  | Neither
136575 | 18/EM/0148 | 236593 | Durvalumab + BCG in NMIBC | No |  | 29 |  |  | 2018-05-24 | 2018-10-02 | 2018-07-16 | 2018-10-24 | 2018-10-31 | 2018-11-08 | [5 empty] | Y |  |  |  |  | Sponsor
136576 | 18/LO/1120 | 246006 | Enfortumab Vedotin vs. chemotherapy in advanced or metatstatic urothel | Yes | 2018-11-08 | 23 | 7 | 30 | 2018-06-06 | 2018-10-09 | 2018-09-18 | 2018-10-24 | 2018-11-01 | 2018-11-07 | [10 empty] | NA
136577 | 17/NW/0698 | 233163 | IMMU-132 in Breast Cancer | Yes | 2018-11-26 | 35 | 20 | 55 | 2018-05-23 | 2018-10-02 | 2018-05-02 | 2018-11-01 | 2018-11-06 | 2018-11-19 | [10 empty] | NA
136578 | 18/LO/1583 | 239032 | BYPASS-CTCA | Yes | 2018-11-15 | 11 | 9 | 20 | 2018-10-26 | 2018-10-26 | 2018-10-19 | 2018-11-05 | 2018-11-06 | 2018-11-14 | [10 empty] | NA
136579 | 18/LO/0864 | 245423 | Safety & efficacy of Venetoclax + Fulvestrant in ER+ MBC patients | Yes | 2018-11-23 | 38 | 14 | 52 | 2018-03-28 | 2018-10-02 | 2018-07-12 | 2018-11-01 | 2018-11-09 | 2018-11-22 | [10 empty] | NA
136580 | 18/EM/0112 | 236871 | ALL-RIC | No |  | 21 |  |  | 2018-04-23 | 2018-10-19 | 2018-06-12 | 2018-10-26 | 2018-11-09 | 2018-11-23 | [5 empty] | Y |  |  |  |  | NHS Provider
136581 | 18/ES/0102 | 236940 | Bio-T-App | Yes | 2018-12-11 | 7 | 27 | 34 | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-14 | 2018-11-14 | 2018-12-17 | [10 empty] | NA
136582 | 18/SC/0502 | 246134 | ACI-24-1801 | Yes | 2019-01-14 | 43 | 53 | 96 | 2018-10-05 | 2018-10-10 | 2018-10-15 | 2018-11-19 | 2018-11-22 | 2019-01-15 | [5 empty] | Y |  |  |  |  | Sponsor
136583 | 18/LO/1276 | 233887 | PINBALL | Yes | 2018-12-03 | 57 | 5 | 62 | 2018-07-16 | 2018-10-02 | 2018-10-02 | 2018-11-28 | 2018-11-28 | 2018-11-29 | [10 empty] | NA
136584 | 18/NE/0078 | 235552 | SETS aHUS: Stopping Eculizumab Treatment Safely in aHUS | No |  | 54 |  |  | 2018-08-03 | 2018-10-05 | 2018-04-13 | 2018-10-22 | 2018-11-28 | 2018-11-28 | [5 empty] | Y |  |  |  |  | NHS Provider
136585 | 18/EM/0113 | 236887 | MOR106-CL-201_Phase II_Atopic Dermatitis_IV MOR106 | Yes | 2018-12-11 | 28 | 11 | 39 | 2018-04-30 | 2018-11-02 | 2018-05-09 | 2018-11-07 | 2018-11-30 | 2018-12-06 | [10 empty] | NA
136586 | 17/NW/0678 | 233267 | INS1007-201 - The Willow Study | No |  | 55 |  |  | 2018-10-24 | 2018-10-24 | 2018-07-26 | 2018-12-18 | 2018-12-18 | 2018-12-18 |  |  | Y | [7 empty] | Sponsor
136587 | 18/LO/1111 | 248674 | SOAR | No |  |  |  |  | 2018-06-15 | 2018-06-15 | [6 empty] | Y | [7 empty] | Sponsor
136588 | 18/EE/0136 | 243704 | Efficacy and Safety of Bimekizumab in Chronic Plaque Psoriasis | No |  |  |  |  | 2018-03-27 | 2018-07-16 | [6 empty] | Y | [7 empty] | Sponsor
136589 | 18/LO/0722 | 238635 | A Phase 3 study of Ozanimod as induction therapy for Crohn?s Disease | No |  | 180 |  |  | 2018-05-01 | 2018-08-16 | 2018-07-30 | 2019-12-20 | 2019-02-12 |  |  |  |  | Y | [6 empty] | Sponsor
136590 | 18/LO/0996 | 244434 | LV Only MPP with SyncAV | No |  | 87 |  |  | 2018-09-14 | 2018-09-17 | 2018-09-04 | 2018-11-26 | 2018-12-13 | 2018-12-19 |  |  |  | Y | [6 empty] | Sponsor
136591 | 18/LO/1038 | 228625 | Remote monitoring & gaming technology for children with CF | Yes | 2019-01-03 | 81 | 24 | 105 | 2018-08-03 | 2018-09-20 | 2018-08-23 | 2018-12-10 | 2018-12-10 | 2018-12-10 |  |  |  |  | Y | [5 empty] | NHS Provider
136592 | 18/LO/2062 | 237959 | Administering Cryoprecipitate in Obstetric Bleeding at an Earlier Time | Yes | 2019-03-12 | 8 | 13 | 21 | 2018-09-21 | 2019-02-19 | 2019-01-22 | 2019-02-27 | 2019-02-27 | [11 empty] | NA
136593 | 18/NE/0139 | 240364 | TAK954-2002 | No |  |  |  |  | 2018-05-14 | 2018-09-26 | 2018-06-12 | [5 empty] | Y | [7 empty] | Sponsor
136594 | 18/LO/1172 | 245733 | Phase 2 Study Comparing CB839 & Cabo vs. Placebo & Cabo in Adv RCC | No |  | 71 |  |  | 2018-08-17 | 2018-10-02 | 2018-08-10 | 2018-12-04 | 2018-12-12 | 2019-01-04 |  |  |  |  | Y |  |  | Y |  |  | Both
136595 | 17/WS/0187 | 220456 | RESHAPE-HF2 | No |  | 100 |  |  | 2018-01-05 | 2018-10-17 | 2018-03-20 | 2019-01-21 | 2019-01-25 |  |  |  |  | Y |  |  |  | Y |  |  | Sponsor
136596 | 18/LO/1791 | 246700 | Study of effectiveness and safety of a treatment for children with RSV | No |  |  |  |  | 2018-10-05 | 2018-12-06 | 2018-12-05 | [6 empty] | Y | [5 empty] | Y | Both
136597 | 18/LO/0995 | 244737 | Lenvatinib plus Pembrolizumab to Treat Advanced Endometrial Cancer | Yes | 2019-01-10 | 55 | 20 | 75 | 2017-12-14 | 2018-10-27 | 2018-09-20 | 2018-12-13 | 2018-12-21 | 2019-01-04 | [10 empty] | NA
136598 | 18/SC/0243 | 240684 | ORION-4 | No |  | 104 |  |  | 2018-05-23 | 2018-11-02 | 2018-10-01 | 2019-02-01 | 2019-02-14 | [6 empty] | Y |  |  |  |  | NHS Provider
136599 | 18/SC/0614 | 251365 | PTG-300 in NTD and TD ?-Thalassaemia patients with Chronic Anaemia | No |  |  |  |  | 2018-09-26 | 2018-11-06 | [13 empty] | Y | Neither
136600 | 18/LO/1805 | 246414 | JAVELIN BRCA/ATM | No |  | 7 |  |  | 2018-08-08 | 2019-03-05 | 2019-02-19 | 2019-03-07 | 2019-03-12 | [11 empty] | NA
136601 | 17/LO/0568 | 215024 | Motivating Structured walking Activity in Intermittent Claudication (MOSAIC) | Yes | 2019-02-04 | 42 | 45 | 87 | 2018-08-28 | 2018-11-09 | 2017-04-27 | 2018-12-21 | 2018-12-21 | 2018-12-21 |  |  |  | Y | [6 empty] | Sponsor
136602 | 17/NI/0096 | 225743 | HOPE-1 | Yes | 2019-02-19 | 60 | 42 | 102 | 2018-10-25 | 2018-11-09 | 2017-07-14 | 2018-12-20 | 2019-01-08 | 2019-01-11 | [10 empty] | NA
136603 | 18/LO/1922 | 251251 | Study to Evaluate the Effect of GBT440 in Pediatrics with Sickle Cell | No |  | 85 |  |  | 2018-08-14 | 2018-11-13 | 2019-01-09 | 2019-02-06 | 2019-02-06 |  |  |  |  | Y |  | Y |  |  |  |  | NHS Provider
136604 | 18/LO/1492 | 248861 | PRAETORIAN-DFT | No |  |  |  |  | 2018-11-12 | 2018-11-14 | 2018-11-12 | [10 empty] | Y |  |  | NHS Provider
136605 | 18/WA/0161 | 238902 | WISARD: DTG+RPV FDC in patients with HIV-1 and the K103N mutation | No |  | 89 |  |  | 2018-11-15 | 2018-11-15 | 2018-10-04 | 2019-02-06 | 2019-02-12 | [11 empty] | NA
136606 | 18/EM/0307 | 241127 | PROMOTE food in inflammatory bowel disease | Yes | 2019-02-06 | 71 | 12 | 83 | 2018-10-18 | 2018-11-15 | 2018-11-09 | 2019-01-25 | 2019-01-25 | 2019-01-25 | [10 empty] | NA
136607 | 18/SC/0242 | 238151 | BLING III study | No |  |  |  |  | 2018-11-14 | 2018-11-19 | 2018-08-24 | [10 empty] | Y |  |  | NHS Provider
136608 | 18/SC/0428 | 239952 | GO39932 | No |  | 72 |  |  | 2018-09-28 | 2018-11-21 | 2018-11-16 | 2019-01-25 | 2019-02-01 | 2019-02-21 | [10 empty] | NA
136609 | 18/SW/0047 | 232201 | DIPLOMA trial version 1.0 | No |  |  |  |  | 2018-11-23 | 2018-11-23 | 2018-03-15 | [13 empty] | NA
136610 | 18/LO/0071 | 229507 | A-BRAVE Trial | No |  | 8 |  |  | 2017-10-10 | 2018-11-26 | 2018-04-03 | 2018-11-27 | 2018-12-04 | 2018-12-07 |  |  |  | Y | [6 empty] | Sponsor
136611 | 18/WA/0092 | 230113 | Ustekinumab in adolescents with recent-onset type 1 diabetes (USTEKID) | No |  |  |  |  | 2018-11-26 | 2018-11-26 | 2018-09-21 | [13 empty] | NA
136612 | 18/LO/1453 | 246119 | BARBICAN | Yes | 2019-01-15 | 22 | 27 | 49 | 2018-08-13 | 2018-11-27 | 2018-11-15 | 2018-12-14 | 2018-12-19 | 2018-12-21 | [10 empty] | NA
139482 | 17/WS/0137 | 228128 | VNS-REHAB | No |  | 33 |  |  | 2018-03-08 | 2018-04-19 | 2017-09-27 | 2018-05-10 | 2018-05-22 | 2018-05-24 |  |  | Y | [7 empty] | Sponsor
139483 | 17/SC/0526 | 227616 | CA209-9ER: Advanced or Metastatic Renal Cell Carcinoma | Yes | 2018-07-24 | 85 | 4 | 89 | 2018-02-15 | 2018-04-26 | 2017-11-20 | 2018-07-18 | 2018-07-20 | 2018-07-23 |  |  |  | Y |  |  |  | Y |  |  | Sponsor
139484 | 17/LO/1715 | 226230 | PHERGain | Yes | 2018-10-22 | 96 | 69 | 165 | 2018-03-08 | 2018-05-10 | 2018-06-05 | 2018-08-13 | 2018-08-14 | 2018-08-21 |  |  |  | Y |  |  |  | Y |  |  | Sponsor
139485 | 18/YH/0014 | 224065 | ACTIVE | Yes | 2019-01-11 | 60 | 182 | 242 | 2018-03-13 | 2018-05-14 | 2018-02-13 | 2018-07-11 | 2018-07-13 | 2018-07-23 |  |  |  | Y |  |  |  | Y |  |  | Sponsor
139486 | 18/LO/0330 | 236942 | Time Lapse Imaging Trial (TILT) | No |  | 261 |  |  | 2018-02-28 | 2018-05-30 | 2018-05-25 | 2019-02-15 | 2019-02-15 |  |  |  |  | Y | Y | [5 empty] | Both
139487 | 15/SC/0691 | 179484 | RePHILL (Resuscitation with Pre?HospItaL bLood products) | Yes | 2019-02-13 | 38 | 195 | 233 | 2017-12-06 | 2018-06-25 | 2016-06-10 | 2018-07-27 | 2018-08-02 | 2018-09-24 | [5 empty] | Y |  |  |  |  | NHS Provider
139488 | 17/NE/0061 | 215780 | CONVINCE - Protocol Version 2.1 29th November 2016 | No |  | 16 |  |  | 2017-12-22 | 2018-07-17 | 2017-07-25 | 2018-04-30 | 2018-08-02 | 2018-08-08 |  |  |  | Y |  | Y |  | Y |  |  | Sponsor
139489 | 18/LO/0773 | 245000 | LUSTRUM Accelerated Partner Therapy (APT) Chlamydia Trial V1.0 | No |  | 49 |  |  | 2018-07-20 | 2018-08-31 | 2018-07-23 | 2018-10-16 | 2018-10-19 |  |  |  |  | Y | [6 empty] | Sponsor
139490 | 17/LO/1847 | 216867 | MUK Twelve | Yes | 2019-01-15 | 49 | 70 | 119 | 2017-12-04 | 2018-09-18 | 2018-01-04 | 2018-11-02 | 2018-11-06 | 2018-11-23 |  |  |  | Y |  | Y |  |  |  |  | Sponsor
139491 | 18/EM/0281 | 251974 | Tralokinumab in moderate-severe AD extension trial 1337 | No |  | 67 |  |  | 2018-10-02 | 2018-10-05 | 2018-11-14 | 2018-11-30 | 2018-12-11 | [5 empty] | Y | Y |  | Y |  |  | NHS Provider
139492 | 18/EM/0229 | 250101 | PROTECT | No |  | 76 |  |  | 2018-08-23 | 2018-10-05 | 2018-10-04 | 2018-12-19 | 2018-12-20 |  |  |  |  | Y |  |  |  | Y |  |  | Sponsor
139493 | 15/LO/1132 | 232468 | NITRATE-CIN | Yes | 2018-11-29 | 0 | 50 | 50 | 2018-10-10 | 2018-10-10 | 2018-08-21 | 2018-10-10 | 2018-10-10 | 2018-11-27 | [10 empty] | NA
139494 | 18/SC/0427 | 220853 | The Bronchiolitis Endotracheal Surfactant Study (BESS) | No |  | 58 |  |  | 2018-10-16 | 2018-10-16 | 2018-10-15 | 2018-12-11 | 2018-12-13 | 2018-12-20 |  |  |  |  | Y | Y |  |  |  |  | NHS Provider
139495 | 17/LO/1273 | 216265 | CheckMate 648 | No |  | 76 |  |  | 2018-08-20 | 2018-10-23 | 2017-08-30 | 2019-01-02 | 2019-01-07 | [5 empty] | Y | Y |  |  |  |  | NHS Provider
139496 | 18/NE/0295 | 251374 | Tralokinumab in adolescents with moderate-severe AD -1334 | Yes | 2019-02-20 | 84 | 15 | 99 | 2018-10-08 | 2018-11-13 | 2018-11-23 | 2019-01-15 | 2019-02-05 | 2019-02-20 |  |  |  | Y |  | Y |  | Y |  |  | Sponsor
139497 | 18/YH/0127 | 239022 | iMODERN | Yes | 2018-12-24 | 28 | 11 | 39 | 2018-10-05 | 2018-11-15 | 2018-05-21 | 2018-11-26 | 2018-12-13 | 2018-12-17 | [10 empty] | NA
139498 | 18/WM/0324 | 246654 | FORCE - Forearm fracture Recovery in Children Evaluation | Yes | 2019-02-13 | 29 | 55 | 84 | 2018-10-11 | 2018-11-21 | 2018-11-16 | 2018-12-12 | 2018-12-20 | 2019-01-16 |  |  |  | Y |  |  |  | Y |  |  | Both
139499 | 18/EM/0310 | 239782 | C-STICH2 Randomised controlled trial of emergency cerclage | No |  |  |  |  | 2018-11-28 | 2018-11-28 | 2018-11-16 | [6 empty] | Y |  |  |  | Y |  |  | Sponsor
139500 | 17/LO/1372 | 203851 | RAPID-1DFU | No |  | 59 |  |  | 2017-07-27 | 2018-12-03 | 2018-11-30 | 2019-01-03 | 2019-01-31 |  |  |  |  | Y |  | Y |  |  |  |  | Sponsor
139501 | 18/LO/2070 | 246179 | TAPS2: Transfusions Antenatally in Pregnant women with SCD | No |  |  |  |  | 2018-12-03 | 2018-12-04 | [7 empty] | Y | [6 empty] | Sponsor
139502 | 18/LO/1993 | 254340 | ACROBAT EDGE | No |  | 69 |  |  | 2018-10-18 | 2018-12-04 | 2019-01-24 | 2019-02-07 | 2019-02-11 | 2019-02-21 |  |  |  | Y |  | Y |  |  |  |  | Sponsor
139503 | 18/WS/0165 | 247486 | OCTARAY FIM (BWI_2017_05) | Yes | 2019-01-18 | 7 | 35 | 42 | 2018-08-14 | 2018-12-07 | 2018-11-20 | 2018-12-12 | 2018-12-14 | 2018-12-14 | [10 empty] | NA
139504 | 18/NW/0644 | 248582 | HUPK | No |  |  |  |  | 2018-05-22 | 2018-12-07 | 2018-11-30 | [7 empty] | Y | Y |  |  |  |  | NHS Provider
139505 | 18/LO/0723 | 244615 | RPC01-3203:study of Ozanimod as Maintenance therapy for Crohns Disease | No |  | 63 |  |  | 2018-05-01 | 2018-12-11 | 2018-09-18 | 2018-12-20 | 2019-02-12 |  |  |  |  | Y |  | Y |  | Y |  |  | Sponsor
139506 | 18/LO/1223 | 244752 | RPC01-3204: Open Label Extension study of Ozanimod for Crohn?s Disease | No |  | 63 |  |  | 2018-05-01 | 2018-12-11 | 2018-09-18 | 2018-12-20 | 2019-02-12 |  |  |  |  | Y |  | Y |  | Y |  |  | Sponsor
139507 | 18/LO/1348 | 233373 | EXPLORER-HCM | No |  | 8 |  |  | 2018-05-29 | 2018-12-12 | 2018-10-22 | 2018-10-09 | 2018-12-20 | 2019-01-31 |  |  |  | Y |  | Y |  |  |  |  | NHS Provider
139508 | 18/LO/1351 | 243522 | M16-047 Ph3 JAK+TCS subjects with moderate to severe AD | No |  | 5 |  |  | 2018-08-14 | 2019-01-03 | 2018-10-26 | 2018-12-07 | 2019-01-08 |  |  |  |  | Y |  | Y |  | Y |  |  | Sponsor
139509 | 18/SC/0421 | 247127 | M18-891 Phase 3 JAK monotherapy atopic dermatitis adolescents&adults | No |  | 1 |  |  | 2018-09-10 | 2019-01-03 | 2018-10-17 | 2018-12-07 | 2019-01-04 |  |  |  |  | Y | Y | Y |  |  |  |  | Sponsor
139510 | 18/LO/0438 | 228704 | ALN-AT3SC-009 | No |  | 24 |  |  | 2017-08-14 | 2019-01-04 | 2018-05-17 | 2019-01-17 | 2019-01-28 | 2019-02-07 |  |  |  | Y |  | Y |  |  |  |  | Sponsor
139511 | 18/LO/1559 | 238899 | Pruritus and Systemic Disease-2048/0007 CARA | No |  | 17 |  |  | 2018-10-18 | 2019-01-04 | 2018-11-02 | 2018-12-19 | 2019-01-21 |  |  |  |  | Y | Y | [5 empty] | Sponsor
139512 | 18/NW0517 | 244505 | I6T-MC-AMAN, Ulcerative Colitis (LUCENT 1) | Yes | 2019-03-14 | 10 | 56 | 66 | 2018-04-03 | 2019-01-07 | 2018-11-14 | 2018-12-03 | 2019-01-17 | 2019-02-09 | [10 empty] | NA
139513 | 18/NW0518 | 244506 | I6T-MC-AMBG, Ulcerative Colitis (LUCENT 2) | No |  | 10 |  |  | 2018-04-03 | 2019-01-07 | 2018-11-14 | 2018-11-28 | 2019-01-17 | [10 empty] | Y | Neither
139514 | 17/LO/0998 | 228693 | MAVMET | No |  |  |  |  | 2019-01-08 | 2019-01-09 | 2017-10-16 | [7 empty] | Y | [5 empty] | NHS Provider
139515 | 18/LO/1726 | 250632 | PROPHESY | Yes | 2019-02-28 | 35 | 13 | 48 | 2018-11-09 | 2019-01-11 | 2018-11-16 | 2019-02-12 | 2019-02-15 | 2019-02-26 | [10 empty] | NA
139516 | 18/WS/0137 | 247036 | VISION Study of 177Lu-PSMA-617 in the treatment of PSMA-Positive mCRPC | No |  | 71 |  |  | 2018-11-29 | 2019-01-15 | 2018-09-10 | 2019-03-06 | 2019-03-27 | [11 empty] | NA
139517 | 19/LO/0156 | 257577 | PSR(Product Surveillance Registry) Platform Base - Sacral Neuromodulation (SNM) | No |  |  |  |  | 2019-01-15 | 2019-01-15 | 2019-01-31 | [13 empty] | NA
139518 | 18/LO/1359 | 231542 | IMPACT | No |  |  |  |  | 2019-01-17 | 2019-01-17 | 2019-01-07 |  |  | 2019-03-22 | [10 empty] | NA
139519 | 18/LO/0124 | 228319 | ALN-AT3SC-003 | No |  | 7 |  |  | 2017-08-01 | 2019-01-21 | 2018-04-23 | 2019-01-15 | 2019-01-28 | [11 empty] | NA
139520 | 18/WS/0201 | 251717 | ENHANCE: A Study of Primary Biliary Cholangitis | No |  |  |  |  | 2018-10-25 | 2019-01-21 | 2019-02-21 | [13 empty] | NA
139521 | 18/SW/0247 | 248334 | BEGONIA - Phase II study of oncology combinations in 1L Stage IV TNBC. | Yes | 2019-02-04 | 9 | 4 | 13 | 2018-09-12 | 2019-01-22 | 2018-11-29 | 2019-01-29 | 2019-01-31 | 2019-01-31 | [10 empty] | NA
139522 | 18/LO/0965 | 236530 | REVERSE-AKI | No |  |  |  |  | 2019-01-23 | 2019-01-23 | 2018-10-22 | [13 empty] | NA
139523 | 18/NW/0813 | 256738 | CAIN457M2302 (SUNRISE): Secukinumab in hidradenitis suppurativa | No |  |  |  |  | 2018-11-19 | 2019-01-23 | 2019-01-22 | [13 empty] | NA
139524 | 18/LO/1808 | 253366 | Phase II paediatric study of ostilodrostat in Cushing's patients | No |  |  |  |  | 2018-10-09 | 2019-01-24 | 2019-03-19 | [13 empty] | NA
139525 | 17/LO/2060 | 230779 | ZUMA-7 | No |  | 2 |  |  | 2018-08-08 | 2019-01-29 | 2018-09-18 | 2018-12-17 | 2019-01-31 | 2019-02-11 | [10 empty] | NA
139526 | 18/WM/0352 | 241385 | LAPTOP - Late Presenter Treatment Optimisation Study | No |  |  |  |  | 2019-01-02 | 2019-01-29 | [14 empty] | NA
139527 | 18/SC/0682 | 254018 | Study of Tezepelumab in Moderate-to-Severe Atopic Dermatitis | No |  |  |  |  | 2018-12-13 | 2019-02-06 | 2018-12-11 | [13 empty] | NA
139528 | 18/SC/0454 | 249509 | POISE-3 | No |  |  |  |  | 2018-11-30 | 2019-02-06 | [14 empty] | NA
139529 | 16/EM/0322 | 202096 | Tenecteplase in Wake-up Ischaemic Stroke Trial (TWIST) | No |  |  |  |  | 2019-02-07 | 2019-02-07 | 2017-08-18 | [13 empty] | NA
139530 | 18/NE/0296 | 248487 | CALIBRE Study | No |  |  |  |  | 2019-02-07 | 2019-02-07 | 2018-10-19 | [13 empty] | NA
139531 | 18/LO/0430 | 241907 | PRN1008 ? an Oral BTK Inhibitor in Patients with Relapsed ITP | No |  |  |  |  | 2018-11-05 | 2019-02-08 | 2018-06-11 | [13 empty] | NA
139532 | 19/LO/0227 | 259669 | OLE-Patients with Hemophilia A or B or without Inhibitory FVIII or FIX | No |  |  |  |  | 2019-02-05 | 2019-02-08 | [14 empty] | NA
139533 | 18/YH/0475 | 254218 | Study of KY1005 in Patients with Moderate to Severe Atopic Dermatitis | No |  |  |  |  | 2019-01-09 | 2019-02-11 | [14 empty] | NA
139534 | 18/LO/1184 | 239603 | M16-067 (INSPIRE) | No |  |  |  |  | 2018-09-26 | 2019-02-15 | 2019-12-20 | [13 empty] | NA
139535 | 18/LO/1185 | 239614 | M16-066 (COMMAND) | No |  |  |  |  | 2018-09-26 | 2019-02-15 | 2019-01-04 | [13 empty] | NA
139536 | 17/WA/0191 | 228332 | Targeted Temperature Management After Cardiac Arrest 2 (TTM 2) | No |  |  |  |  | 2019-02-25 | 2019-02-25 | 2018-06-21 | [13 empty] | NA
139537 | 18/EE/0373 | 249396 | Breast Cancer Her 2 | No |  |  |  |  | 2018-06-08 | 2019-02-26 | [14 empty] | NA
139538 | 18/LO/1861 | 252394 | A Phase 3 Study of Durvalumab in Muscle Invasive Bladder Cancer | No |  |  |  |  | 2018-09-18 | 2019-02-26 | [14 empty] | NA
139539 | 18/LO/1187 | 240011 | ATHENA | No |  | 14 |  |  | 2018-07-13 | 2019-02-26 | 2018-09-11 | 2019-03-05 | 2019-03-12 | [11 empty] | NA
139540 | 18/LO/1995 | 253000 | A Phase 3 trial of BCG +/- MK-3475 for HR NMIBC (KEYNOTE-676) | No |  |  |  |  | 2018-09-07 | 2019-02-28 | 2019-01-08 | [13 empty] | NA
139541 | 18/EE/0300 | 236285 | PROMPT | No |  |  |  |  | 2018-10-01 | 2019-03-01 | 2018-10-19 | [13 empty] | NA
139542 | 17/WA/0383 | 233958 | WHiTE Five - Main Study | No |  |  |  |  | 2019-02-27 | 2019-03-04 | 2018-02-12 | [13 empty] | NA
139543 | 18/WM/0383 | 252607 | Ecztra 7 (ECZema TRAlokinumab trial no. 7) | No |  |  |  |  | 2018-10-03 | 2019-03-04 | 2019-02-06 | [13 empty] | NA
139544 | 19/SC/0122 | 259342 | DESTINY PWS - A Study of DCCR in Patients with Prader-Willi Syndrome | No |  |  |  |  | 2019-02-26 | 2019-03-05 | [14 empty] | NA
139545 | 19/LO/0128 | 234820 | Iron and Muscle | No |  |  |  |  | 2019-01-15 | 2019-03-08 | 2019-03-07 | [13 empty] | NA
139546 | 18/LO/2045 | 252053 | Radiance II study | No |  |  |  |  | 2018-10-25 | 2019-03-08 | [14 empty] | NA
139547 | 17/NW/0634 | 209375 | COMICE | No |  |  |  |  | 2018-08-03 | 2019-03-12 | 2019-01-16 | [13 empty] | NA
139548 | 18/SC/0195 | 224790 | PHASE II STUDY ASSESSING THE COMBINED USE OF AUTOLOGOUS BONE MARROW DERIVED MONONUCLEAR CELLS AND G-CSF WITH PERCUTANEOUS CIRCULATORY ASSISTANCE IN THE TREATMENT OF DILATED CARDIOMYOPATHY | No |  | 28 |  |  | 2018-10-16 | 2018-11-09 | 2018-06-14 | 2018-12-07 | 2018-12-07 | 2018-12-07 | [5 empty] | Y |  |  |  |  | Neither
139549 | 18/LO/0365 | 233381 | Boston Virgin Back Study | Yes | 2018-10-18 | 7 | 36 | 43 | 2017-07-21 | 2018-09-05 | 2018-09-05 | 2018-08-29 | 2018-09-12 | 2018-10-05 | [10 empty] | NA
139550 | 18/LO/1693 | 230030 | Electrical VAgal StimulatION in Ulcerative Colitis ? EVASION-UC | Yes | 2018-11-08 | 4 | 37 | 41 | 2018-05-30 | 2018-09-28 | 2018-09-26 | 2018-10-02 | 2018-10-02 | [11 empty] | NA
139551 | 18/LO/0958 | 203080 | The POWERED Study: Prophylaxis with metformin to prevent PTDM | Yes | 2019-01-23 | 165 | 16 | 181 | 2017-11-20 | 2018-07-26 | 2018-07-26 | 2019-01-07 | 2019-01-07 | 2019-01-07 |  |  |  | Y |  |  |  | Y |  |  | Sponsor
139552 | 18/LO/1698 | 249064 | Active over alcohol (AOA) | Yes | 2019-01-21 | 10 | 42 | 52 | 2018-09-04 | 2018-11-30 | 2018-11-28 | 2018-12-10 | 2018-12-10 | 2019-01-10 | [10 empty] | NA
139553 | 18/NW/0689 | 249543 | Clinical and radiographic changes in intrabony defects following non-surgical vs. surgical minimally-invasive periodontal therapy. A parallel group, single centre, examiner-blind, non-inferiority randomised controlled trial. | Yes | 2019-03-20 | 9 | 91 | 100 | 2018-08-30 | 2018-12-10 | 2018-11-29 | 2018-12-19 | 2018-12-19 | 2019-03-04 | [9 empty] | Y | Neither
139554 | 19/HRA/0634 | 258886 | Mobile learning to improve clinicians ability to break bad news | No |  | 38 |  |  | 2019-01-09 | 2019-01-09 | 2019-01-28 | 2019-02-16 | 2019-02-16 | 2019-02-14 | [9 empty] | Y | Neither
Note on A1: System generated field
Note on G1: System generated field. Please check your dates if value is negative.
Note on J1: Format dd/mm/yyyy.
Note on K1: Format dd/mm/yyyy.
Note on L1: Format dd/mm/yyyy.
Note on M1: Format dd/mm/yyyy.
Note on N1: Format dd/mm/yyyy.
Note on O1: Format dd/mm/yyyy.