## Sheet1
ID | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Date Site Ready To Start | A - Permissions delayed/ denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | Reasons for delay correspond to:
146836 | 17/LO/1596 | 228894 | REACH Pregnancy Circles Trial; Version 1.0 | Yes | 2019-02-05 | 41 | 5 | 46 | 2018-06-01 | 2018-12-21 | 2018-05-30 | 2019-01-31 | 2019-01-31 | 2019-02-01 | [10 empty] | NA
146837 | 18/NI/0060 | 242168 | Lenabasum in Cystic Fibrosis | Yes | 2019-01-10 | 2 | 77 | 79 | 2018-07-16 | 2018-10-23 | 2018-06-29 | 2018-10-04 | 2018-10-25 | 2018-11-30 |  |  |  | Y | [6 empty] | Sponsor
146838 | 18/EM/0148 | 236593 | Durvalumab + BCG in NMIBC | Yes | 2019-03-28 | 29 | 148 | 177 | 2018-05-24 | 2018-10-02 | 2018-07-16 | 2018-10-24 | 2018-10-31 | 2018-11-08 | [5 empty] | Y |  |  | Y |  | Neither
146839 | 18/LO/1120 | 246006 | Enfortumab Vedotin vs. chemotherapy in advanced or metatstatic urothel | Yes | 2018-11-08 | 23 | 7 | 30 | 2018-06-06 | 2018-10-09 | 2018-09-18 | 2018-10-24 | 2018-11-01 | 2018-11-07 | [10 empty] | NA
146840 | 17/NW/0698 | 233163 | IMMU-132 in Breast Cancer | Yes | 2018-11-26 | 35 | 20 | 55 | 2018-05-23 | 2018-10-02 | 2018-05-02 | 2018-11-01 | 2018-11-06 | 2018-11-19 | [10 empty] | NA
146841 | 18/LO/1583 | 239032 | BYPASS-CTCA | Yes | 2018-11-15 | 11 | 9 | 20 | 2018-10-26 | 2018-10-26 | 2018-10-19 | 2018-11-05 | 2018-11-06 | 2018-11-14 | [10 empty] | NA
146842 | 18/LO/0864 | 245423 | Safety & efficacy of Venetoclax + Fulvestrant in ER+ MBC patients | Yes | 2018-11-23 | 38 | 14 | 52 | 2018-03-28 | 2018-10-02 | 2018-07-12 | 2018-11-01 | 2018-11-09 | 2018-11-22 | [10 empty] | NA
146843 | 18/EM/0112 | 236871 | ALL-RIC | No |  | 21 |  |  | 2018-04-23 | 2018-10-19 | 2018-06-12 | 2018-10-26 | 2018-11-09 | 2018-11-23 |  |  |  |  | Y | Y |  |  |  |  | NHS Provider
146844 | 18/ES/0102 | 236940 | Bio-T-App | Yes | 2018-12-11 | 7 | 27 | 34 | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-14 | 2018-11-14 | 2018-12-17 | [10 empty] | NA
146845 | 18/SC/0502 | 246134 | ACI-24-1801 | Yes | 2019-01-14 | 43 | 53 | 96 | 2018-10-05 | 2018-10-10 | 2018-10-15 | 2018-11-19 | 2018-11-22 | 2019-01-15 |  |  |  |  | Y | Y |  | Y |  |  | Sponsor
146846 | 18/LO/1276 | 233887 | PINBALL | Yes | 2018-12-03 | 57 | 5 | 62 | 2018-07-16 | 2018-10-02 | 2018-10-02 | 2018-11-28 | 2018-11-28 | 2018-11-29 | [10 empty] | NA
146847 | 18/NE/0078 | 235552 | SETS aHUS: Stopping Eculizumab Treatment Safely in aHUS | Yes | 2019-01-03 | 54 | 36 | 90 | 2018-08-03 | 2018-10-05 | 2018-04-13 | 2018-10-22 | 2018-11-28 | 2018-11-28 | [5 empty] | Y |  |  |  |  | Neither
146848 | 18/EM/0113 | 236887 | MOR106-CL-201_Phase II_Atopic Dermatitis_IV MOR106 | Yes | 2018-12-11 | 28 | 11 | 39 | 2018-04-30 | 2018-11-02 | 2018-05-09 | 2018-11-07 | 2018-11-30 | 2018-12-06 | [10 empty] | NA
146849 | 17/NW/0678 | 233267 | INS1007-201 - The Willow Study | No |  | 55 |  |  | 2018-10-24 | 2018-10-24 | 2018-07-26 | 2018-12-18 | 2018-12-18 | 2018-12-18 |  | Y | [8 empty] | Sponsor
146850 | 18/LO/2062 | 237959 | Administering Cryoprecipitate in Obstetric Bleeding at an Earlier Time | Yes | 2019-03-12 | 8 | 13 | 21 | 2018-09-21 | 2019-02-19 | 2019-01-22 | 2019-02-27 | 2019-02-27 | 2019-03-04 | [10 empty] | NA
146851 | 18/LO/1172 | 245733 | Phase 2 Study Comparing CB839 & Cabo vs. Placebo & Cabo in Adv RCC | Yes | 2019-01-03 | 71 | 22 | 93 | 2018-08-17 | 2018-10-02 | 2018-08-10 | 2018-12-04 | 2018-12-12 | 2019-01-04 |  |  |  |  | Y |  |  | Y |  |  | Both
146852 | 17/WS/0187 | 220456 | RESHAPE-HF2 | No |  | 100 |  |  | 2018-01-05 | 2018-10-17 | 2018-03-20 | 2019-01-21 | 2019-01-25 |  |  |  |  | Y |  | Y |  |  |  |  | Sponsor
146853 | 18/LO/1791 | 246700 | Study of effectiveness and safety of a treatment for children with RSV | No |  | 265 |  |  | 2018-10-05 | 2018-12-06 | 2018-12-05 | 2019-03-13 | 2019-08-28 | [6 empty] | Y |  |  |  |  | Neither
146854 | 18/LO/0995 | 244737 | Lenvatinib plus Pembrolizumab to Treat Advanced Endometrial Cancer | Yes | 2019-01-10 | 55 | 20 | 75 | 2017-12-14 | 2018-10-27 | 2018-09-20 | 2018-12-13 | 2018-12-21 | 2019-01-04 | [10 empty] | NA
146855 | 18/SC/0243 | 240684 | ORION-4 | Yes | 2019-09-06 | 104 | 204 | 308 | 2018-05-23 | 2018-11-02 | 2018-10-01 | 2019-02-01 | 2019-02-14 | 2019-08-19 |  |  |  | Y | Y | [5 empty] | Both
146856 | 18/SC/0614 | 251365 | PTG-300 in NTD and TD β-Thalassaemia patients with Chronic Anaemia | Yes | 2019-03-28 | 70 | 72 | 142 | 2018-09-26 | 2018-11-06 | 2018-11-06 | 2019-01-09 | 2019-01-15 | 2019-03-05 |  |  |  |  | Y | [5 empty] | NHS Provider
146857 | 18/LO/1805 | 246414 | JAVELIN BRCA/ATM | Yes | 2019-05-15 | 7 | 64 | 71 | 2018-08-08 | 2019-03-05 | 2019-02-19 | 2019-03-07 | 2019-03-12 | 2019-05-10 | [10 empty] | NA
146858 | 17/LO/0568 | 215024 | Motivating Structured walking Activity in Intermittent Claudication (MOSAIC) | Yes | 2019-02-04 | 42 | 45 | 87 | 2018-08-28 | 2018-11-09 | 2017-04-27 | 2018-12-21 | 2018-12-21 | 2018-12-21 |  |  |  | Y | [6 empty] | Sponsor
146859 | 17/NI/0096 | 225743 | HOPE-1 | Yes | 2019-02-19 | 60 | 42 | 102 | 2018-10-25 | 2018-11-09 | 2017-07-14 | 2018-12-20 | 2019-01-08 | 2019-01-11 |  |  |  | Y |  |  |  | Y |  |  | Sponsor
146860 | 18/LO/1922 | 251251 | Study to Evaluate the Effect of GBT440 in Pediatrics with Sickle Cell | Yes | 2019-03-06 | 85 | 28 | 113 | 2018-08-14 | 2018-11-13 | 2019-01-09 | 2019-02-06 | 2019-02-06 | 2019-03-05 |  |  |  |  | Y | [5 empty] | NHS Provider
146861 | 18/LO/1492 | 248861 | PRAETORIAN-DFT | Yes | 2019-04-12 | 135 | 14 | 149 | 2018-11-12 | 2018-11-14 | 2018-11-12 | 2019-03-14 | 2019-03-29 | 2019-03-29 | [7 empty] | Y |  |  | Sponsor
146862 | 18/WA/0161 | 238902 | WISARD: DTG+RPV FDC in patients with HIV-1 and the K103N mutation | Yes | 2019-03-19 | 89 | 35 | 124 | 2018-11-15 | 2018-11-15 | 2018-10-04 | 2019-02-06 | 2019-02-12 | [5 empty] | Y | [5 empty] | NHS Provider
146863 | 18/EM/0307 | 241127 | PROMOTE food in inflammatory bowel disease | Yes | 2019-02-06 | 71 | 12 | 83 | 2018-10-18 | 2018-11-15 | 2018-11-09 | 2019-01-25 | 2019-01-25 | 2019-01-25 | [10 empty] | NA
146864 | 18/SC/0242 | 238151 | BLING III study | Yes | 2019-05-24 | 163 | 23 | 186 | 2018-11-14 | 2018-11-19 | 2018-08-24 | 2019-04-29 | 2019-05-01 | 2019-05-02 |  |  |  | Y |  |  |  | Y |  |  | Sponsor
146865 | 18/SC/0428 | 239952 | GO39932 | Yes | 2019-05-09 | 72 | 97 | 169 | 2018-09-28 | 2018-11-21 | 2018-11-16 | 2019-01-25 | 2019-02-01 | 2019-02-21 |  |  |  | Y |  | Y |  | Y | Y |  | Sponsor
146866 | 18/SW/0047 | 232201 | DIPLOMA trial version 1.0 | Yes | 2019-04-26 | 152 | 2 | 154 | 2018-11-23 | 2018-11-23 | 2018-03-15 | 2019-04-15 | 2019-04-24 |  |  |  |  | Y | [6 empty] | Sponsor
146867 | 18/LO/0071 | 229507 | A-BRAVE Trial | No |  | 8 |  |  | 2017-10-10 | 2018-11-26 | 2018-04-03 | 2018-11-27 | 2018-12-04 | 2018-12-07 | [5 empty] | Y |  |  |  |  | Sponsor
146868 | 18/WA/0092 | 230113 | Ustekinumab in adolescents with recent-onset type 1 diabetes (USTEKID) | No |  | 151 |  |  | 2018-11-26 | 2018-11-26 | 2018-09-21 | 2019-02-13 | 2019-04-26 | 2019-04-26 |  |  |  |  | Y | Y |  |  |  |  | NHS Provider
146869 | 18/LO/1453 | 246119 | BARBICAN | Yes | 2019-01-15 | 22 | 27 | 49 | 2018-08-13 | 2018-11-27 | 2018-11-15 | 2018-12-14 | 2018-12-19 | 2018-12-21 | [10 empty] | NA
146870 | 18/EM/0281 | 251974 | Tralokinumab in moderate-severe AD extension trial 1337 | Yes | 2019-02-20 | 67 | 71 | 138 | 2018-10-02 | 2018-10-05 | 2018-11-14 | 2018-11-30 | 2018-12-11 | 2018-12-11 |  |  |  | Y |  | Y |  | Y |  |  | Sponsor
146871 | 18/EM/0229 | 250101 | PROTECT | No |  | 76 |  |  | 2018-08-23 | 2018-10-05 | 2018-10-04 | 2018-12-19 | 2018-12-20 | 2019-04-03 |  |  |  | Y |  | Y |  | Y |  |  | Sponsor
146872 | 18/LO/1132 | 232468 | NITRATE-CIN | Yes | 2018-11-29 | 0 | 50 | 50 | 2018-10-10 | 2018-10-10 | 2018-08-21 | 2018-10-10 | 2018-10-10 | 2018-11-27 | [10 empty] | NA
146873 | 18/SC/0427 | 220853 | The Bronchiolitis Endotracheal Surfactant Study (BESS) | Yes | 2019-01-02 | 58 | 20 | 78 | 2018-10-16 | 2018-10-16 | 2018-10-15 | 2018-12-11 | 2018-12-13 | 2018-12-20 | [10 empty] | NA
146874 | 17/LO/1273 | 216265 | CheckMate 648 | Yes | 2019-04-09 | 76 | 92 | 168 | 2018-08-20 | 2018-10-23 | 2017-08-30 | 2019-01-02 | 2019-01-07 | 2019-03-27 |  |  |  |  | Y | Y |  | Y |  |  | Both
146875 | 18/EE/0301 | 251374 | Tralokinumab in adolescents with moderate-severe AD -1334 | Yes | 2019-02-20 | 84 | 15 | 99 | 2018-10-08 | 2018-11-13 | 2018-11-23 | 2019-01-15 | 2019-02-05 | 2019-02-20 |  |  |  | Y |  |  |  | Y |  |  | Sponsor
146876 | 18/YH/0127 | 239022 | iMODERN | Yes | 2018-12-24 | 28 | 11 | 39 | 2018-10-05 | 2018-11-15 | 2018-05-21 | 2018-11-26 | 2018-12-13 | 2018-12-17 | [10 empty] | NA
146877 | 18/WM/0324 | 246654 | FORCE - Forearm fracture Recovery in Children Evaluation | Yes | 2019-02-13 | 29 | 55 | 84 | 2018-10-11 | 2018-11-21 | 2018-11-16 | 2018-12-12 | 2018-12-20 | 2019-01-16 | [5 empty] | Y |  |  |  |  | Neither
146878 | 18/EM/0310 | 239782 | C-STICH2 Randomised controlled trial of emergency cerclage | No |  | 168 |  |  | 2018-11-28 | 2018-11-28 | 2018-11-16 | 2019-04-09 | 2019-05-15 |  |  |  |  | Y |  | Y |  | Y | Y |  | Sponsor
146879 | 17/LO/1372 | 203851 | RAPID-1DFU | Yes | 2019-07-03 | 59 | 153 | 212 | 2017-07-27 | 2018-12-03 | 2018-11-30 | 2019-01-03 | 2019-01-31 | 2019-02-28 |  |  |  | Y |  | Y |  |  |  | Y | Neither
146881 | 18/LO/1993 | 254340 | ACROBAT EDGE | No |  | 69 |  |  | 2018-10-18 | 2018-12-04 | 2019-01-24 | 2019-02-07 | 2019-02-11 | 2019-02-21 |  |  |  | Y |  | Y |  | Y |  |  | Sponsor
146882 | 18/WS/0165 | 247486 | OCTARAY FIM (BWI_2017_05) | Yes | 2019-01-18 | 7 | 35 | 42 | 2018-08-14 | 2018-12-07 | 2018-11-20 | 2018-12-12 | 2018-12-14 | 2018-12-14 | [10 empty] | NA
146883 | 18/NW/0644 | 248582 | HUPK | Yes | 2019-06-12 | 152 | 35 | 187 | 2018-05-22 | 2018-12-07 | 2018-11-30 | 2019-03-20 | 2019-05-08 | 2019-05-29 |  |  |  |  | Y | [5 empty] | NHS Provider
146884 | 18/LO/0723 | 244615 | RPC01-3203:study of Ozanimod as Maintenance therapy for Crohn's Disease | No |  | 63 |  |  | 2018-05-01 | 2018-12-11 | 2018-09-18 | 2018-12-20 | 2019-02-12 |  |  |  |  | Y |  | Y |  |  |  |  | Sponsor
146885 | 18/LO/1223 | 244752 | RPC01-3204: Open Label Extension study of Ozanimod for Crohn's Disease | No |  | 63 |  |  | 2018-05-01 | 2018-12-11 | 2018-09-18 | 2018-12-20 | 2019-02-12 |  |  |  |  | Y |  | Y |  |  |  |  | Sponsor
146886 | 18/LO/1348 | 233373 | EXPLORER-HCM | Yes | 2019-04-17 | 8 | 118 | 126 | 2018-05-29 | 2018-12-12 | 2018-10-22 | 2018-10-09 | 2018-12-20 | 2019-01-31 | [5 empty] | Y |  |  |  |  | Neither
146887 | 18/LO/1351 | 243522 | M16-047 Ph3 JAK+TCS subjects with moderate to severe AD | Yes | 2019-04-03 | 5 | 85 | 90 | 2018-08-14 | 2019-01-03 | 2018-10-26 | 2018-12-07 | 2019-01-08 | 2019-01-14 | [5 empty] | Y |  |  |  |  | Neither
146888 | 18/SC/0421 | 247127 | M18-891 Phase 3 JAK monotherapy atopic dermatitis adolescents & adults | No |  | 1 |  |  | 2018-09-10 | 2019-01-03 | 2018-10-17 | 2018-12-07 | 2019-01-04 | [6 empty] | Y |  |  |  |  | Neither
146889 | 18/LO/0438 | 228704 | ALN-AT3SC-009 | No |  | 24 |  |  | 2017-08-14 | 2019-01-04 | 2018-05-17 | 2019-01-17 | 2019-01-28 | 2019-02-07 | [5 empty] | Y |  |  |  |  | Neither
146890 | 18/LO/1559 | 238899 | Pruritus and Systemic Disease-2048/0007 CARA | Yes | 2019-04-17 | 17 | 86 | 103 | 2018-10-18 | 2019-01-04 | 2018-11-02 | 2018-12-19 | 2019-01-21 | 2019-04-03 |  |  |  | Y | [6 empty] | Sponsor
146891 | 18/NW/0517 | 244505 | I6T-MC-AMAN, Ulcerative Colitis (LUCENT 1) | Yes | 2019-03-14 | 10 | 56 | 66 | 2018-04-03 | 2019-01-07 | 2018-11-14 | 2018-12-03 | 2019-01-17 | 2019-02-09 | [10 empty] | NA
146892 | 18/NW/0518 | 244506 | I6T-MC-AMBG, Ulcerative Colitis (LUCENT 2) | No |  | 10 |  |  | 2018-04-03 | 2019-01-07 | 2018-11-14 | 2018-11-28 | 2019-01-17 | 2019-02-09 | [5 empty] | Y |  |  |  |  | Sponsor
146893 | 17/LO/0998 | 228693 | MAVMET | No |  | 174 |  |  | 2019-01-08 | 2019-01-09 | 2017-10-16 | 2019-02-13 | 2019-07-02 | [5 empty] | Y | Y |  |  |  |  | NHS Provider
146894 | 18/LO/1726 | 250632 | PROPHESY | Yes | 2019-02-28 | 35 | 13 | 48 | 2018-11-09 | 2019-01-11 | 2018-11-16 | 2019-02-12 | 2019-02-15 | 2019-02-26 | [10 empty] | NA
146895 | 18/WS/0137 | 247036 | VISION Study of 177Lu-PSMA-617 in the treatment of PSMA-Positive mCRPC | Yes | 2019-04-09 | 71 | 13 | 84 | 2018-11-29 | 2019-01-15 | 2018-09-10 | 2019-03-06 | 2019-03-27 | 2019-03-29 | [10 empty] | NA
146896 | 19/LO/0156 | 257577 | PSR(Product Surveillance Registry) Platform Base - Sacral Neuromodulation (SNM) | No |  | 197 |  |  | 2019-01-15 | 2019-01-15 | 2019-01-31 | 2019-07-25 | 2019-07-31 | [6 empty] | Y |  | Y |  |  | NHS Provider
146897 | 18/LO/1359 | 231542 | IMPACT | Yes | 2019-06-11 | 64 | 81 | 145 | 2019-01-17 | 2019-01-17 | 2019-01-07 | 2019-03-22 | 2019-03-22 | 2019-03-22 | [5 empty] | Y |  |  |  |  | Neither
146898 | 18/LO/0124 | 228319 | ALN-AT3SC-003 | No |  | 7 |  |  | 2017-08-01 | 2019-01-21 | 2018-04-23 | 2019-01-15 | 2019-01-28 | 2019-02-07 | [5 empty] | Y | Y |  |  |  | Neither
146899 | 18/WS/0201 | 251717 | ENHANCE: A Study of Primary Biliary Cholangitis | No |  | 122 |  |  | 2018-10-25 | 2019-01-21 | 2019-02-21 | 2019-04-23 | 2019-05-23 | 2019-05-29 |  |  |  | Y |  | Y |  | Y |  |  | Sponsor
146900 | 18/SW/0247 | 248334 | BEGONIA - Phase II study of oncology combinations in 1L Stage IV TNBC. | Yes | 2019-02-04 | 9 | 4 | 13 | 2018-09-12 | 2019-01-22 | 2018-11-29 | 2019-01-29 | 2019-01-31 | 2019-01-31 | [10 empty] | NA
146901 | 18/LO/0965 | 236530 | REVERSE-AKI | Yes | 2019-07-19 | 133 | 44 | 177 | 2019-01-23 | 2019-01-23 | 2018-10-22 | 2019-06-05 | 2019-06-05 | 2019-06-05 |  |  |  | Y | [6 empty] | Sponsor
146902 | 18/NW/0813 | 256738 | CAIN457M2302 (SUNRISE): Secukinumab in hidradenitis suppurativa | No |  | 169 |  |  | 2018-11-19 | 2019-01-23 | 2019-01-22 | 2019-07-02 | 2019-07-11 | [6 empty] | Y |  | Y |  |  | Sponsor
146903 | 18/LO/1808 | 253366 | Phase II paediatric study of ostilodrostat in Cushing's patients | No |  | 202 |  |  | 2018-10-09 | 2019-01-24 | 2019-03-19 | 2019-08-08 | 2019-08-14 | [6 empty] | Y |  | Y | Y |  | Sponsor
146904 | 17/LO/2060 | 230779 | ZUMA-7 | Yes | 2019-03-21 | 2 | 49 | 51 | 2018-08-08 | 2019-01-29 | 2018-09-18 | 2018-12-17 | 2019-01-31 | 2019-02-11 | [10 empty] | NA
146905 | 18/WM/0352 | 241385 | LAPTOP - Late Presenter Treatment Optimisation Study | No |  | 76 |  |  | 2019-01-02 | 2019-01-29 | 2019-01-15 | 2019-01-25 | 2019-04-15 | [5 empty] | Y | Y |  |  |  |  | NHS Provider
146906 | 18/SC/0682 | 254018 | Study of Tezepelumab in Moderate-to-Severe Atopic Dermatitis | Yes | 2019-05-20 | 85 | 18 | 103 | 2018-12-13 | 2019-02-06 | 2018-12-11 | 2019-03-14 | 2019-05-02 | 2019-05-08 | [7 empty] | Y |  |  | Sponsor
146907 | 18/SC/0454 | 249509 | POISE-3 | No |  |  |  |  | 2018-11-30 | 2019-02-06 | 2019-01-16 | [12 empty] | Y | NHS Provider
146908 | 16/EM/0322 | 202096 | Tenecteplase in Wake-up Ischaemic Stroke Trial (TWIST) | No |  | 107 |  |  | 2019-02-07 | 2019-05-15 | 2017-08-18 | 2019-07-05 | 2019-08-30 |  |  |  |  | Y |  | Y |  | Y |  |  | Sponsor
146909 | 18/NE/0296 | 248487 | CALIBRE Study | No |  | 140 |  |  | 2019-02-07 | 2019-02-07 | 2018-10-19 | 2019-03-18 | 2019-06-27 | 2019-07-15 |  |  |  | Y | Y | Y |  |  |  |  | Both
146910 | 18/LO/0430 | 241907 | PRN1008 - an Oral BTK Inhibitor in Patients with Relapsed ITP | Yes | 2019-04-26 | 48 | 29 | 77 | 2018-11-05 | 2019-02-08 | 2018-06-11 | 2019-03-25 | 2019-03-28 | 2019-04-01 | [10 empty] | NA
146911 | 19/LO/0227 | 259669 | OLE-Patients with Hemophilia A or B or without Inhibitory FVIII or FIX | No |  | 98 |  |  | 2019-02-05 | 2019-06-25 | 2019-05-24 | 2019-09-24 | 2019-10-01 | [6 empty] | Y |  |  |  |  | Neither
146912 | 18/EM/0407 | 254218 | Study of KY1005 in Patients with Moderate to Severe Atopic Dermatitis | No |  |  |  |  | 2019-01-09 | 2019-02-11 | 2019-01-24 | [12 empty] | Y | NHS Provider
146913 | 18/LO/1184 | 239603 | M16-067 (INSPIRE) | Yes | 2019-08-06 | 145 | 27 | 172 | 2018-09-26 | 2019-02-15 | 2019-12-20 | 2019-07-08 | 2019-07-10 | 2019-07-29 |  |  |  | Y | [6 empty] | Sponsor
146914 | 18/LO/1185 | 239614 | M16-066 (COMMAND) | No |  | 171 |  |  | 2018-09-26 | 2019-02-15 | 2019-01-04 | 2019-07-30 | 2019-08-05 |  |  |  |  | Y |  |  |  | Y |  |  | Sponsor
146916 | 18/EE/0373 | 249396 | Breast Cancer Her 2 | No |  | 91 |  |  | 2018-06-08 | 2019-02-26 | 2019-01-19 | 2019-03-27 | 2019-05-28 | 2019-06-03 |  |  |  | Y |  | Y |  |  |  |  | Sponsor
146917 | 18/LO/1861 | 252394 | A Phase 3 Study of Durvalumab in Muscle Invasive Bladder Cancer | No |  | 121 |  |  | 2018-09-18 | 2019-02-26 | 2019-05-30 | 2019-06-27 | 2019-06-27 | 2019-07-04 | Y |  |  | Y |  | Y |  | Y |  |  | Sponsor
146918 | 18/LO/1187 | 240011 | ATHENA | Yes | 2019-04-03 | 14 | 22 | 36 | 2018-07-13 | 2019-02-26 | 2018-09-11 | 2019-03-05 | 2019-03-12 | 2019-03-29 | [10 empty] | NA
146919 | 18/EM/0383 | 253000 | A Phase 3 trial of BCG +/- MK-3475 for HR NMIBC (KEYNOTE-676) | No |  | 144 |  |  | 2018-09-07 | 2019-02-28 | 2019-01-08 | 2019-07-22 | 2019-07-22 | 2019-07-22 |  |  |  | Y | Y | Y |  | Y |  |  | Both
146920 | 18/EE/0300 | 236285 | PROMPT | No |  | 53 |  |  | 2018-10-01 | 2019-03-01 | 2018-10-19 | 2019-02-11 | 2019-04-23 | 2019-08-13 |  |  |  | Y |  | Y |  |  |  |  | Sponsor
146921 | 17/WA/0383 | 233958 | WHiTE Five - Main Study | Yes | 2019-07-30 | 129 | 19 | 148 | 2019-02-27 | 2019-03-04 | 2018-02-12 | 2019-07-05 | 2019-07-11 | 2019-07-22 | [9 empty] | Y | Neither
146922 | 18/WM/0383 | 252607 | Ecztra 7 (ECZema TRAlokinumab trial no. 7) | No |  | 59 |  |  | 2018-10-03 | 2019-03-04 | 2019-02-06 | 2019-04-12 | 2019-05-02 | 2019-05-16 | [5 empty] | Y |  | Y |  |  | Sponsor
146923 | 19/SC/0122 | 259342 | DESTINY PWS - A Study of DCCR in Patients with Prader-Willi Syndrome | Yes | 2019-08-22 | 105 | 65 | 170 | 2019-02-26 | 2019-03-05 | 2019-05-07 | 2019-05-23 | 2019-06-18 | 2019-06-26 |  |  |  |  | Y | Y |  |  |  |  | NHS Provider
146924 | 19/LO/0128 | 234820 | Iron and Muscle | No |  | 70 |  |  | 2019-01-15 | 2019-03-08 | 2019-03-07 | 2019-03-19 | 2019-05-17 | [5 empty] | Y | Y |  |  |  |  | NHS Provider
146925 | 18/LO/2045 | 252053 | Radiance II study | Yes | 2019-04-16 | 31 | 8 | 39 | 2018-10-25 | 2019-03-08 | 2019-01-25 | 2019-03-18 | 2019-04-08 | 2019-04-12 | [10 empty] | NA
146926 | 17/NW/0634 | 209375 | COMICE | No |  | 162 |  |  | 2018-08-03 | 2019-03-12 | 2019-01-16 | 2019-08-14 | 2019-08-21 | 2019-09-03 |  |  |  |  | Y | Y |  | Y |  |  | Both
146927 | 18/SC/0195 | 224790 | PHASE II STUDY ASSESSING THE COMBINED USE OF AUTOLOGOUS BONE MARROW DERIVED MONONUCLEAR CELLS AND G-CSF WITH PERCUTANEOUS CIRCULATORY ASSISTANCE IN THE TREATMENT OF DILATED CARDIOMYOPATHY | Yes | 2019-01-29 | 28 | 53 | 81 | 2018-10-16 | 2018-11-09 | 2018-06-14 | 2018-12-07 | 2018-12-07 | 2018-12-07 | [5 empty] | Y |  |  |  |  | Neither
146928 | 18/LO/1698 | 249064 | Active over alcohol (AOA) | Yes | 2019-01-21 | 10 | 42 | 52 | 2018-09-04 | 2018-11-30 | 2018-11-28 | 2018-12-10 | 2018-12-10 | 2019-01-10 | [10 empty] | NA
146929 | 18/LO/1956 | 249543 | Clinical and radiographic changes in intrabony defects following non-surgical vs. surgical minimally-invasive periodontal therapy. A parallel group, single centre, examiner-blind, non-inferiority randomised controlled trial. | Yes | 2019-03-20 | 9 | 91 | 100 | 2018-08-30 | 2018-12-10 | 2018-11-29 | 2018-12-19 | 2018-12-19 | 2019-03-04 |  |  |  | Y | [6 empty] | Sponsor
146930 | 19/HRA/0634 | 258886 | Mobile learning to improve clinicians ability to break bad news | No |  | 38 |  |  | 2019-01-09 | 2019-01-09 | 2019-01-28 | 2019-02-16 | 2019-02-16 | 2019-02-14 | [5 empty] | Y |  |  |  |  | Neither
146931 | 18/LO/0235 | 240315 | GBT440-034 - OLE GBT440 in Patients with Sickle Cell Disease | Yes | 2019-02-06 | 41 | 50 | 91 | 2018-02-09 | 2018-11-07 | 2018-04-17 | 2018-05-30 | 2018-12-18 | 2019-01-29 | [5 empty] | Y |  |  | Y |  | Neither
146932 | 19/LO/0385 | 256511 | A Phase 2a Study to Assess EYP001a in Patients with NASH | No |  | 31 |  |  | 2019-03-11 | 2019-08-13 | 2019-08-12 | 2019-07-10 | 2019-09-13 | [11 empty] | NA
146933 | 18/LO/2006 | 250980 | The TARGET BP OFF-MED Trial | Yes | 2019-05-14 | 21 | 33 | 54 | 2018-11-28 | 2019-03-21 | 2019-02-14 | 2019-03-28 | 2019-04-11 | 2019-04-24 | [10 empty] | NA
146934 | 18/SS/0010 | 238051 | Erdafitinib compared with Vinflunine or Docetaxel or Pembrolizumab | Yes | 2019-04-11 | 7 | 7 | 14 | 2018-12-13 | 2019-03-28 | 2018-03-21 | 2019-03-26 | 2019-04-04 | 2019-04-05 | [10 empty] | NA
146935 | 19/WA/0104 | 262263 | Protocol 0169 - TD-9855 for Treating snOH | No |  | 128 |  |  | 2019-03-22 | 2019-04-23 | 2019-05-22 | 2019-08-29 | 2019-08-29 |  |  |  |  | Y |  |  |  | Y |  |  | Sponsor
146936 | 19/LO/0341 | 259731 | Pre-operative GDC-9545 for women with stage 1-3 operable breast cancer | No |  | 27 |  |  | 2019-02-20 | 2019-05-08 | 2019-03-19 | 2019-06-04 | 2019-06-04 | 2019-06-18 | [5 empty] | Y |  |  |  |  | Neither
146937 | 19/EM/0142 | 260307 | Efficacy & Safety of Bimekizumab in PsA | No |  |  |  |  | 2019-04-18 | 2019-05-16 | 2019-08-01 |  |  |  |  | Y | [8 empty] | Sponsor
146938 | 19/EM/0141 | 260308 | BE COMPLETE | No |  |  |  |  | 2019-04-18 | 2019-05-16 | 2019-07-31 |  |  |  |  | Y | [8 empty] | Sponsor
146939 | 19/SC/0021 | 249552 | OPTIMAS Trial | No |  | 125 |  |  | 2019-01-21 | 2019-05-16 | 2019-04-04 | 2019-06-19 | 2019-09-18 |  |  |  |  | Y |  |  |  | Y |  |  | Sponsor
146940 | 19/NW/0158 | 259931 | Surgery or Cast for Injuries of the EpicoNdyle in Children's Elbows | No |  | 54 |  |  | 2019-03-12 | 2019-05-17 | 2019-03-25 | 2019-06-07 | 2019-07-10 | [11 empty] | NA
146942 | 19/LO/0433 | 255914 | EIG-LNF-011 lonafirnib+ritonavir with/without PEG INF-alfa-2a in HDV | Yes | 2019-08-29 | 37 | 63 | 100 | 2019-01-15 | 2019-05-21 | 2019-05-22 | 2019-06-21 | 2019-06-27 | 2019-08-04 | [5 empty] | Y |  |  |  |  | Neither
146944 | 17/LO/1875 | 219487 | Renal Adjuvant MultiPle Arm Randomised Trial (RAMPART) | Yes | 2019-07-30 | 16 | 46 | 62 | 2018-06-05 | 2019-05-29 | 2018-01-08 | 2019-05-30 | 2019-06-14 | 2019-07-25 | [10 empty] | NA
146945 | 19/LO/0802 | 264414 | Acceptability and tolerance study of high energy peptide based paediatric oral nutritional supplement for children | No |  | 121 |  |  | 2019-05-01 | 2019-05-29 | 2019-05-21 | 2019-09-26 | 2019-09-27 | [6 empty] | Y |  | Y |  |  | Sponsor
146946 | 18/EM/0323 | 251531 | Vedolizumab in Subjects Undergoing Stem Cell Transplantation | Yes | 2019-09-09 | 34 | 68 | 102 | 2018-10-30 | 2019-05-30 | 2019-03-28 | 2019-06-27 | 2019-07-03 | 2019-07-12 | [5 empty] | Y |  |  |  |  | Neither
146947 | 19/EM/0149 | 254032 | ALITHIOS- Open-label extension study of ofatumumab in relapsing MS | No |  | 62 |  |  | 2019-05-30 | 2019-05-30 | 2019-06-18 | 2019-07-31 | 2019-07-31 | [6 empty] | Y |  | Y |  |  | Neither
146948 | 18/LO/1397 | 247266 | Diabetic Gastroparesis Study 2 | No |  | 21 |  |  | 2018-07-04 | 2019-06-06 | 2018-11-06 | 2019-06-18 | 2019-06-27 | [6 empty] | Y |  |  |  |  | Neither
146949 | 19/SC/0064 | 255208 | MERIT - Mediterranean diet for prevention of type 2 diabetes | Yes | 2019-06-28 | 17 | 1 | 18 | 2019-01-16 | 2019-06-10 | 2019-05-07 | 2019-06-27 | 2019-06-27 | 2019-06-27 | [10 empty] | NA
146950 | 19/NW/0068 | 254093 | IMbrella B - Extension Study from Previous Atezolizumab Study | Yes | 2019-07-15 | 2 | 31 | 33 | 2019-02-07 | 2019-06-12 | 2019-04-04 | 2019-06-07 | 2019-06-14 | 2019-07-05 | [10 empty] | NA
146951 | 19/LO/0272 | 255069 | An RCT of ACT for people with MND | No |  | 80 |  |  | 2019-01-30 | 2019-06-17 | 2019-06-13 | 2019-09-04 | 2019-09-05 |  |  |  |  | Y |  | Y |  | Y |  |  | Sponsor
146952 | 18/LO/1399 | 247565 | Diabetic Gastroparesis Study 4 | No |  | 253 |  |  | 2018-08-22 | 2018-11-29 | 2018-11-06 | 2019-07-22 | 2019-08-09 |  |  |  |  | Y |  | Y |  | Y |  |  | Sponsor
146953 | 16/LO/1495 | 207629 | SPACE | Yes | 2019-03-26 | 68 | 6 | 74 | 2019-01-11 | 2019-01-11 | 2017-06-12 | 2019-03-20 | 2019-03-20 | 2019-03-20 | [10 empty] | NA
146954 | 17/NW/0247 | 222303 | AURORA | No |  | 122 |  |  | 2019-01-10 | 2019-02-11 | 2017-08-30 | 2019-06-07 | 2019-06-13 | [5 empty] | Y | Y |  |  |  |  | NHS Provider
146955 | 19/LO/0153 | 259690 | KVD900 | No |  | 58 |  |  | 2019-02-14 | 2019-04-01 | 2019-03-29 | 2019-05-21 | 2019-05-29 | [5 empty] | Y | Y |  |  |  |  | NHS Provider
146956 | 17/LO/2093 | 228763 | HEPMARC Study | No |  | 29 |  |  | 2019-02-13 | 2019-04-09 | 2018-02-26 | 2018-02-26 | 2019-05-08 | 2019-06-13 | [5 empty] | Y |  |  | Y |  | Sponsor
151067 | 16/LO/2150 | 201093 | OCTOVA | Yes | 2019-01-03 | 14 | 59 | 73 | 2018-04-20 | 2018-10-22 | 2017-01-26 | 2018-10-15 | 2018-11-05 | 2018-11-23 | [10 empty] | NA
151068 | 18/YH/0133 | 239570 | GO40241 - Phase III - Neoadjuvant Atezolizumab + Chemotherapy in NSCLC | Yes | 2019-03-11 | 21 | 102 | 123 | 2018-04-11 | 2018-11-08 | 2018-05-17 | 2018-11-22 | 2018-11-29 | 2018-12-07 |  |  |  |  | Y | Y |  |  |  |  | Both
151069 | 18/LO/1542 | 247189 | Phase 2 study to test the efficacy & safety of KPL 301 in GCA | Yes | 2019-07-31 | 66 | 195 | 261 | 2018-07-24 | 2018-11-12 | 2018-12-10 | 2019-01-07 | 2019-01-17 | 2019-01-17 | [5 empty] | Y |  |  |  |  | Neither
151070 | 18/LO/1398 | 247563 | Diabetic Gastroparesis Study with Randomized-withdrawal Period | No |  | 265 |  |  | 2018-08-22 | 2018-11-29 | 2018-11-06 | 2019-07-19 | 2019-08-21 |  |  |  |  | Y | Y | Y |  | Y |  |  | Both
151071 | 18/LO/0722 | 238635 | A Phase 3 study of Ozanimod as induction therapy for Crohn's Disease | No |  | 63 |  |  | 2018-05-01 | 2018-12-11 | 2018-07-30 | 2018-12-20 | 2019-02-12 | [6 empty] | Y |  |  |  |  | Neither
151072 | 17/SS/0082 | 222441 | SoSTART | No |  | 122 |  |  | 2018-09-11 | 2018-12-11 | 2017-10-05 | 2019-03-22 | 2019-04-12 |  |  |  |  | Y |  | Y |  | Y |  |  | Sponsor
151073 | 18/LO/0099 | 240520 | Fitusiran in Patients With Hemophilia A or B Without Inhibitory Ab | No |  | 14 |  |  | 2017-08-01 | 2019-01-14 | 2018-03-22 | 2019-01-10 | 2019-01-28 | 2019-02-07 | [5 empty] | Y |  |  | Y |  | Sponsor
151074 | 19/SC/0040 | 257213 | COSMOS: Guselkumab vs Placebo in Psoriatic Arthritis | Yes | 2019-07-01 | 95 | 27 | 122 | 2019-01-17 | 2019-03-01 | 2019-03-01 | 2019-05-30 | 2019-06-04 | 2019-06-06 | [7 empty] | Y |  |  | Sponsor
151075 | 18/YH/0236 | 230191 | PROTHOR | No |  |  |  |  | 2019-02-05 | 2019-04-04 | 2018-10-17 | [12 empty] | Y | NHS Provider
151076 | 19/LO/0106 | 257081 | Disrupt CAD III With the Shockwave Coronary IVL System | No |  | 59 |  |  | 2019-01-21 | 2019-04-09 | 2019-04-08 | 2019-05-21 | 2019-06-07 | 2019-06-07 | [5 empty] | Y | Y |  |  |  | Neither
151077 | 18/LO/0204 | 216147 | ANIMATE | Yes | 2019-09-25 | 39 | 124 | 163 | 2018-07-17 | 2019-04-15 | 2018-04-13 | 2019-05-24 | 2019-05-24 | 2019-06-21 |  |  |  | Y | [6 empty] | Sponsor
151078 | 19/LO/0344 | 257615 | RO7191863 in virologically supressed patients with chronic Hepatitis B | No |  | 69 |  |  | 2019-02-08 | 2019-04-16 | 2019-04-25 | 2019-06-10 | 2019-06-24 | 2019-06-24 |  |  |  |  | Y | Y |  |  |  |  | NHS Provider
151079 | 19/SC/0247 | 261133 | 4245 Somapacitan vs Norditropin in children with short stature (REAL5) | No |  | 129 |  |  | 2019-05-13 | 2019-05-13 | 2019-07-11 | 2019-09-06 | 2019-09-19 |  |  |  |  | Y |  |  |  | Y |  |  | Sponsor
151080 | 18/LO/1240 | 245093 | Open label trial of H3B-6545 in HER2 negative breast cancer | No |  | 25 |  |  | 2018-07-16 | 2019-05-17 | 2018-10-09 | 2019-05-10 | 2019-06-11 | 2019-08-13 | [5 empty] | Y |  |  |  |  | Sponsor
151081 | 18/LO/1946 | 249357 | Phase 3 study of Baricitinib in patients with SLE | Yes | 2019-07-11 | 25 | 27 | 52 | 2018-12-04 | 2019-05-20 | 2019-03-27 | 2019-06-11 | 2019-06-14 | 2019-06-30 | [10 empty] | NA
151082 | 19/SW/0070 | 259679 | CAPItello-290 | No |  | 29 |  |  | 2019-03-19 | 2019-05-29 | 2019-05-02 | 2019-06-13 | 2019-06-27 | 2019-07-05 | [5 empty] | Y |  |  |  |  | Sponsor
151083 | 19/EM/0020 | 252705 | TAPER | No |  | 102 |  |  | 2019-03-29 | 2019-05-31 | 2019-05-23 | 2019-09-06 | 2019-09-10 | [5 empty] | Y | Y |  |  |  |  | NHS Provider
151084 | 19/LO/0455 | 246792 | Pelle-926-301 | No |  | 81 |  |  | 2019-03-14 | 2019-06-27 | 2019-05-13 | 2019-08-19 | 2019-09-16 | [5 empty] | Y | Y |  |  |  |  | NHS Provider
151085 | 18/SC/0666 | 248460 | The Operative Rib Fixation (ORiF) Study | Yes | 2019-09-16 | 55 | 19 | 74 | 2019-06-05 | 2019-07-04 | 2019-07-09 | 2019-08-05 | 2019-08-28 | 2019-08-29 |  |  |  | Y | [6 empty] | NHS Provider
151086 | 18/LO/1798 | 254544 | ARRY-371797 (p38 MAP Kinase Inhibitor) | Yes | 2019-07-25 | 2 | 14 | 16 | 2018-03-15 | 2019-07-09 | 2018-12-14 | 2019-07-01 | 2019-07-11 | 2019-07-23 | [10 empty] | NA
151087 | 19/ES/0049 | 260196 | The ADDapt diet in reducing Crohn's disease inflammation - Version 1 | No |  | 27 |  |  | 2019-04-29 | 2019-07-09 | 2019-07-15 | 2019-08-05 | 2019-08-05 | [6 empty] | Y |  |  |  |  | Neither
151088 | 19/LO/0891 | 263922 | 2 different doses of crizanlizumab vs placebo in SCD patients | No |  | 77 |  |  | 2019-04-12 | 2019-07-15 | 2019-07-08 | 2019-09-24 | 2019-09-30 | [5 empty] | Y | [5 empty] | NHS Provider
151089 | 19/YH/0015 | 255446 | Beta-blockers or placebo for primary prophylaxis (BOPPP) Trial | No |  | 42 |  |  | 2019-04-18 | 2019-07-17 | 2019-04-24 | 2019-07-17 | 2019-08-28 | 2019-08-28 |  |  |  | Y | [6 empty] | Sponsor
151090 | 19/LO/0555 | 255609 | L1FE: Lateral compression type-1 fracture fixation in the elderly | Yes | 2019-08-30 | 16 | 28 | 44 | 2019-04-05 | 2019-07-17 | 2019-07-17 | 2019-08-02 | 2019-08-02 | 2019-08-02 | [10 empty] | NA
151091 | 19/LO/0905 | 257865 | PIBIK Study | No |  | 74 |  |  | 2019-07-03 | 2019-07-18 | 2019-07-17 | 2019-09-04 | 2019-09-30 |  |  |  |  | Y |  | Y |  | Y |  |  | Sponsor
151092 | 17/NW/0581 | 214739 | SC IL-1Ra in SAH - phase III trial | No |  |  |  |  | 2019-07-23 | 2019-07-23 | 2018-08-07 | [13 empty] | NA
151093 | 19/LO/0812 | 264281 | AXA1957-002 | Yes | 2019-08-28 | 6 | 30 | 36 | 2019-05-15 | 2019-07-23 | 2019-06-21 | 2019-07-24 | 2019-07-29 | 2019-07-31 | [10 empty] | NA
151094 | 19/YH/0072 | 257713 | B7451036 | No |  | 65 |  |  | 2019-01-29 | 2019-07-24 | 2019-07-11 | 2019-09-27 | 2019-09-27 |  |  |  |  | Y | [6 empty] | Sponsor
151095 | 18/SC/0423 | 245306 | The PEP-TALK Trial | No |  | 40 |  |  | 2019-07-19 | 2019-07-25 | 2018-11-23 | 2019-08-20 | 2019-09-03 | 2019-10-15 | [10 empty] | NA
151096 | 19/LO/1263 | 263485 | Cabozantinib with Nivolumab and Ipilimumab in Untreated Metastatic RCC | No |  |  |  |  | 2019-06-18 | 2019-07-25 | 2019-09-04 | [13 empty] | NA
151097 | 18/LO/1768 | 251935 | DS8201-A-U301, Phase 3, HER2-Positive Breast cancer | Yes | 2019-09-03 | 4 | 35 | 39 | 2018-08-01 | 2019-07-26 | 2019-02-06 | 2019-07-12 | 2019-07-30 | 2019-08-07 | [10 empty] | NA
151098 | 18/LO/1767 | 252328 | DS8201-A-U302, Phase 3, HER2-Positive breast cancer | No |  | 4 |  |  | 2018-10-11 | 2019-07-26 | 2019-02-06 | 2019-07-12 | 2019-07-30 | 2019-08-07 | [10 empty] | NA
151099 | 19/EE/0185 | 260536 | FIRST-line support for Assistance in Breathing in Children (FIRST-ABC) | Yes | 2019-10-01 | 14 | 50 | 64 | 2019-06-27 | 2019-07-29 | 2019-07-26 | 2019-08-08 | 2019-08-12 | 2019-09-12 | [10 empty] | NA
151100 | 19/LO/0581 | 249647 | Safety study of trifarotene cream in lamellar ichthyosis | No |  |  |  |  | 2019-04-16 | 2019-07-30 |  |  |  |  | Y | [9 empty] | Neither
151101 | 19/YH/0158 | 262107 | TRANSITION | Yes | 2019-09-04 | 14 | 22 | 36 | 2019-04-23 | 2019-07-30 | 2019-07-26 | 2019-08-06 | 2019-08-13 | 2019-08-16 | [10 empty] | NA
151102 | 19/NW/0510 | 269112 | A Study for Early Diagnosis of RSV in Paediatric Participants | No |  |  |  |  | 2019-07-31 | 2019-08-01 | 2019-09-25 | [13 empty] | NA
151103 | 19/SC/0248 | 262411 | Continuation study of PTG-300 in NTD and TD ?-Thalassaemia patients | No |  | 49 |  |  | 2019-04-12 | 2019-08-05 | 2019-07-09 | 2019-07-11 | 2019-09-23 | [11 empty] | NA
151104 | 18/SC/0680 | 241654 | Genentech GO29781 | No |  | 35 |  |  | 2018-12-12 | 2019-08-07 | 2019-03-01 | 2019-08-30 | 2019-09-11 | 2019-09-13 | [10 empty] | NA
151105 | 19/SW/0028 | 255759 | GRAVITAS-309: Initial Treatment for Chronic Graft-Versus-Host Disease | No |  | 8 |  |  | 2019-02-26 | 2019-08-07 | 2019-05-07 | 2019-08-01 | 2019-08-15 | 2019-09-24 | [10 empty] | NA
151106 | 19/NI/0110 | 260538 | EluNIR HBR study | Yes | 2019-09-23 | 39 | 7 | 46 | 2019-06-10 | 2019-08-08 | 2019-07-19 | 2019-08-26 | 2019-09-16 | 2019-09-18 | [10 empty] | NA
151107 | 19/LES/0026 | 258125 | DS8201-A-U303, HER 2 - Low Breast Cancer | Yes | 2019-09-11 | 13 | 21 | 34 | 2019-02-22 | 2019-08-08 | 2019-05-08 | 2019-08-05 | 2019-08-21 | 2019-09-03 | [10 empty] | NA
151108 | 19/LO/0855 | 260338 | NKTR-214 Phase II urothelial cancer with low PD-L1 expression Study | No |  |  |  |  | 2019-02-11 | 2019-08-09 | 2019-06-27 | [13 empty] | NA
151109 | 19/LO/0879 | 264047 | Perioperative MK-3475 for cisplatin-ineligible patients with MIBC | No |  | 8 |  |  | 2019-04-30 | 2019-08-13 | 2019-08-12 | 2019-07-30 | 2019-08-21 | 2019-09-06 | [10 empty] | NA
151110 | 18/SW/0268 | 251667 | Trial Net (TN22) | No |  |  |  |  | 2019-07-03 | 2019-08-13 | 2019-03-11 | [13 empty] | NA
151111 | 19/NE/0125 | 252601 | Xentuzumab, Everolimus and Exemestane in metastatic breast cancer. | No |  | 7 |  |  | 2019-03-23 | 2019-08-21 | 2019-05-13 | 2019-08-20 | 2019-08-28 | [11 empty] | NA
151112 | 17/LO/1476 | 224732 | A phase 2a Study in Adult Volunteers with Sickle Cell Anaemia - 001 | No |  | 12 |  |  | 2019-04-30 | 2019-08-28 | 2017-10-19 | 2019-03-09 | 2019-09-09 | 2019-09-19 | [10 empty] | NA
151113 | 19/LO/0180 | 201748 | Transplant Antibody Mediated Rejection: Guiding Effective Treatments Study 1 (TAR:GET-1 Study) | No |  |  |  |  | 2019-08-12 | 2019-08-28 | 2019-04-17 | [13 empty] | NA
151114 | 19/LO/0945 | 262119 | The TRAUMA INtramuscular Tranexamic Acid Clinical Trial-Trauma-INTACT | No |  |  |  |  | 2019-07-29 | 2019-08-28 | 2019-08-06 | [13 empty] | NA
151115 | 19/WM/0251 | 264348 | RAINBOW . | No |  |  |  |  | 2019-08-27 | 2019-08-29 |  |  |  |  | Y | [9 empty] | Neither
151116 | 17/NW/0637 | 229352 | OUTREACH study: Urine analysis and antihypertensive treatment | No |  |  |  |  | 2019-05-14 | 2019-09-03 | 2017-12-20 | [13 empty] | NA
151117 | 19/LO/1240 | 263231 | Study of different combinations of treatments for people with hep B | No |  |  |  |  | 2019-07-02 | 2019-09-03 | 2019-08-22 | [13 empty] | NA
151118 | 19/WA/0222 | 266983 | APD334-301 - ELEVATE UC 52: Etrasimod v Placebo for Ulcerative Colitis | No |  |  |  |  | 2019-03-05 | 2019-09-03 | 2019-09-02 | [13 empty] | NA
151119 | 18/SS/0132 | 271988 | PiCSO-AMI-I (Scotland specific application) | No |  |  |  |  | 2019-09-04 | 2019-09-04 | 2019-07-16 | [13 empty] | NA
151120 | 19/LO/1026 | 249627 | Famciclovir for Epstein-Barr virus in MS | No |  |  |  |  | 2019-06-28 | 2019-09-09 | 2019-09-09 | [13 empty] | NA
151121 | 19/EM/0264 | 266058 | FAME: Fractured Ankle Management Evaluation | No |  |  |  |  | 2019-09-09 | 2019-09-10 | 2019-09-03 | [13 empty] | NA
151122 | 19/EE/0290 | 263484 | ORATORIO HAND | No |  |  |  |  | 2019-05-20 | 2019-09-11 |  |  |  |  | Y | [9 empty] | Neither
151123 | 19/WA/0209 | 266031 | ASICS v1.0 | Yes | 2019-10-02 | 12 | 9 | 21 | 2019-07-16 | 2019-09-11 | 2019-09-04 | 2019-09-23 | 2019-09-23 | 2019-09-26 | [10 empty] | NA
151124 | 19/LO/0262 | 253945 | Ripple Mapping Guided Early Ventricular Tachycardia Ablation | No |  | 2 |  |  | 2019-05-02 | 2019-09-16 | 2019-03-19 | 2019-09-18 | 2019-09-18 | [11 empty] | NA
151125 | 19/SC/0050 | 259683 | PiCSO-AMI-I | No |  |  |  |  | 2019-09-04 | 2019-09-17 | 2019-07-16 | [13 empty] | NA
151126 | 19/SC/0467 | 266684 | contRAst-1 | No |  |  |  |  | 2019-09-17 | 2019-09-17 |  |  |  |  | Y | [9 empty] | Neither
151127 | 19/LO/1153 | 262506 | Fostamatinib disodium in the treatment of wAIHA | No |  |  |  |  | 2019-06-18 | 2019-09-19 | 2019-09-16 | [13 empty] | NA
151128 | 19/NW/0482 | 269475 | Kepler | No |  |  |  |  | 2019-07-12 | 2019-09-23 | 2019-09-27 | [13 empty] | NA
151129 | 19/LO/0351 | 256743 | M16-011: Risankizumab compared to placebo in PsA patients (DMARD-IR) | No |  |  |  |  | 2019-06-12 | 2019-09-25 | 2019-07-03 | [13 empty] | NA
151130 | 19/LO/0352 | 257478 | M15-998: Risankizumab compared to placebo in PsA patients (Bio-IR) | No |  |  |  |  | 2019-06-12 | 2019-09-25 | 2019-07-02 | [13 empty] | NA
151131 | 18/YH/0477 | 253254 | A Phase 3 study of Zanubrutinib compared with Ibrutinib | No |  |  |  |  | 2019-02-01 | 2019-09-26 | 2019-01-23 | [13 empty] | NA
151132 | 19/LO/0952 | 262142 | Phase 3 Study of Pembrolizumab plus Docetaxel in mCRPC | No |  | 4 |  |  | 2019-04-01 | 2019-09-26 | 2019-08-14 | 2019-09-20 | 2019-09-30 | [11 empty] | NA
151133 | 19/SC/0311 | 262176 | ASEPTIC | No |  |  |  |  | 2019-07-17 | 2019-09-27 | 2019-08-07 | [13 empty] | NA
Note on A1: System generated field
Note on G1: System generated field. Please check your dates if value is negative.
Note on J1: Format dd/mm/yyyy.
Note on K1: Format dd/mm/yyyy.
Note on L1: Format dd/mm/yyyy.
Note on M1: Format dd/mm/yyyy.
Note on N1: Format dd/mm/yyyy.
Note on O1: Format dd/mm/yyyy.